## Notes
WORKBOOK FOR THE CALCULATION OF CONSULTING ENGINEER'S FEES IN TERMS OF THE GUIDELINE FOR SERVICES AND FEES PUBLISHED BY ECSA AS AMENDED BY DPW
NOTES PERTAINING TO THE COMPLETION OF THE WORKBOOK.
GROUND RULES
1 | One has to refer to the Letter of Invitation and the relevant published Guidelines for Engineering fees as amended , and use a copy of the relevant Guidelines which has been marked up to show the revised Fee scale to ensure that the correct fee scale is used.
2 | Engineers deal with work contained in two main types of projects: Engineering and Multi-disciplinary. Ensure that you select the correct fee calculator for the type of contract you are dealing with. Select only the "Engineering project" as the type of project if no principal agent and/or quantity surveyor is appointed on the project. Quantity surveyors are responsible for all bills of quantities for all disciplines on Multi-disciplinary projects.
3 | The value of the works relating to a particular part of the project will have to include the relevant portions of the Preliminaries and CPA extracted from the project value and then allocated to each category value
4 | In practice, the calculator calculates a Basic fee for a consultant based on the value of the works relating to that particular discipline
5 | The Basic fee for a consultant is proportioned between the different categories of work and then the relevant fee factors applied to those types of the work.
6 | The first portion of the fee calculator contains the amounts relating to a given discipline which have been extracted from a project and which is not subject to any factors.
7 | If the project or contract consists entirely of the work comprising one discipline, then you use the entire cost of the contract, allocating portions of the value to the relevant categories, otherwise, one must extract from the project values, the value of the works relating to a particular discipline, and then allocate portions of that value to the various categories which will attract different fee factors.
8 | In some cases more than one of the fee factor multipliers may have to be applied to the same portion of the works, and these factors have to be dealt with separately in the fee calculations.
9 | Principal Agent: A separate fee will be calculated for such an appointment, because the fee is based on the value of the works (1% of the total value of the works). This procedure is NOT a fee factor multiplier to be applied to the basic fee. N/A
10 | Only in case of engineering projects an amount not exceeding 6% of the basic fee and calculated on a time basis is allowed for the responsibilities of the "agent of the client" in accordance with the OHSA. Only if the motivation of the consulting engineer for a larger fee is approved, may he be paid more.
11 | Only in case of engineering projects an amount of 7% of the basic fee is allowed for the execution of targeted procurement.
12 | Electronic engineering work is not a separate discipline but one combined with Electrical engineering work.
13 | The dates must be typed in as follows: dmmmyy i.e. "25aug05"
14 | When typing amounts only type the value. No "R" in front and no spaces between the numbers.
PROCEDURE TO FOLLOW IN POPULATING THE WORKBOOK:
1 | Start by opening the worksheet "Input Data"
2 | Some comments or notes with arrows pointing to certain cells are displayed to guide the user, but they will not be printed.
3 | Only coloured cells require input from the Consulting Engineer/Project manager
4 | Access to any cells within the workbook, which do not require to be populated, have been protected - do not try to access/open any uncoloured cells on any of the worksheets.
5 | Populate all yellow coloured cells. Arrows, tab- or enter keys or mouse can be used to move around the worksheet (i.e. to cells to which access are possible).
6 | Input the dates in the following format: "ddmmmyy" (13sep11).
7 | Certain cells will reflect Error-message in red bold type or #Div/0-messages. These will start to disappear once the required cells have been populated with correct information. If such cells have been populated with incorrect information, the Error-messages will remain. The #Div/0 will equally disappear as the worksheets are populated - except in unused fields.
8 | Open the disbursement worksheets one by one and populate them with the correct information. Please note that the amounts previously claimed for disbursements must be added by hand at the end of each table. The total previous payment must also be added by hand on the "Previous Payment" worksheet.
9 | After all information has been entered into the workbook, set the print areas in each of the worksheets (File: Set Print Area). Print Areas to cover all the data which is required to be printed for the purposes of the fee invoice submission in each of the worksheets. Empty rows may be hided for the purpose of saving paper (otherwise a host of empty rows and columns will be unnecessarily printed).
10 | Finally open the relevant "invoice" worksheet, go to the "File" command on toolbar, choose "Print" - this will print the final invoice. Do the same with the other data sheets which are then required to be appended to the invoice to be presented to the Project manager.
11 | This workbook makes provision for 36 payments. From experience this should be enough. If not, the matter must be reported to the Firm, who can take same up with the designer/compiler of the workbook.
12 | The sheets and formula fields in the calculators are protected so that one should just be able to enter the data and assume that the results are correct
13 | Project managers are advised to re-enter the data (at least for the Schedules) into their personal copies of the spread sheets to check the fee accounts, because the calculators used by other person might have been changed inadvertently!
(1) Multi-Disciplinary Project means a project comprising building work, together with its associated engineering work, where the engineer is subject to the authority of another professional acting as the Principal Agent while financial and administrative matters are dealt with by another professional
C | THE FEE ACCOUNT
No fee account shall be submitted to the DPW Project Manager without all the relevant information and the documents as listed below attached and of which examples and forms, form part this document :
(a) | Covering letter and TAX invoice - must be signed by a Principal/Director of the Consultant Firm
(b) | Summary of the Fee Claim: Annexure A3
(c) | Trip sheet: Annexure A5: Claims for Subsistence and Travelling. This form shall be completed by the person during each trip.
(d) | A copy of the Appointment letter from the Client must be attached to the first fee account.
(e) | The completed Site Staff request and approval (PRM033: ) must be attached to each account when costs for Site Staff is claimed
(f) | The Record Drawings/As-Build's, must be attached to the final fee account as well as all drawings issued during the contract
(g) | The Record Drawings/As-Build's, must be attached to the final account as well as all drawings issued during the contract
1 | NOTE:
For any information, clarification or assistance please phone Ms Magda van Es at 012 452 0446 or 082 887 1705 - E-mail magda@virtualconsulting.co.za or Charles Beaurain @ 0823907612/0125676957
cse09
see10

## Input Data
PLEASE READ THE NOTES (1st SHEET) BEFORE STARTING TO POPULATE THE SHEETS. COMPLETE ALL YELLOW CELLS PLEASE !!!
STRUCTURAL ENGINEERING
ENGINEERING PROJECT: 2012 NDPW FEES
Version: 1.1 2012-10
| DPW FILE NUMBER: |  |  | DPW PROJECT MANAGER
| WCS NUMBER |  |  | TEL NO
| WCS CONTRACT NUMBER |  |  | CELL
| DRAWING NUMBER |  |  | FAX
| DISCIPLINE APPOINTED | STRUCTURAL ENGINEERING |  | E-MAIL ADDRESS
| TYPE OF PROJECT: | ENGINEERING PROJECT | E
| PENALTY APPLIED (Excl VAT) | No |  | 1
SERVICE: DESCRIPTION
CONSULTANT NAME
| POSTAL ADDRESS: |  |  |  | CODE
| CONSULTANT OFFICE ADDRESS |  |  |  | CODE
| TELEPHONE & FACSIMILE NUMBERS |  | CELL PHONE NO |  | FACSIMILE NO:
E-MAIL ADDRESS
| VAT REGISTRATION NO: |  | 0 | CLIENT | NATIONAL DEPARTMENT OF PUBLIC WORKS
| COMPANY REGISTRATION NUMBER |  | <--ERROR
DATE APPOINTED :
| FEES CODE (YEAR) | 2012 | 2 | POSTAL ADDRESS
Fee in accordance with the National Department of Public Works Scope of Engineering Services and Tariff of Fees for Persons Registered in terms of the Engineering Profession Act, 2000 (Act No. 46 of 2000) dated 1 January 2012 |  |  |  | POST OFFICE
POSTAL CODE
|  |  |  | VAT REGISTRATION NO: | NOT REGISTERED
OFFICE ADDRESS/ BUILDING NAME
TARIFF OF FEES TO APPLY : |  | USE TIME BASED FEES |  | STREET & NO
| PERCENTAGE OF FEE TENDERED | 100 | % | TOWN/CITY
| DATE OF INVOICE |  |  | CODE
| CLAIM NO: |  |  | TEL NO
| CONSULTANT'S REF. NUMBER : |  |  | FAX NO
| INVOICE NO |  |  | FAX-TO-EMAIL
| STAGE | DETAIL DESIGN |  | 3
| PERCENTAGE OF STAGE COMPLETED | 100% | N/A for INCEPTION, CONTRACT ADMINISTRATION or CLOSE-OUT STAGE
| CONSTRUCTION MONITORING ONLY | N
ESTIMATED TOTAL ENGINEERING FEES
|  | PRINCIPAL AGENT (Y/N) | N
|  | TARGETED PROCUREMENT (Y/N) | N
|  | AGENT OF THE CLIENT (OHSA) (Only on Engineering project) (Y/N) | N |  |  | 512000
INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES, ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA DURING CONSTRUCTION STAGE. |  |  | (A) ESTIMATED OR TENDER VALUES (STAGES 1 -4) | (B) ESTIMATED VALUE FOR DESIGN FEES DURING CONSTRUCTION (STAGE 5) | (D) FINAL MEASURED VALUES INCL. CPA & P&G (STAGE 6 ONLY) | VALUE FOR CALCULATION PURPOSES
ESTIMATES OR TENDER VALUES? |  | TENDER VALUES | 1
1. VALUE OF WORK NOT AFFECTED BY ANY FACTORS |  |  | 0 |  |  | 0
2. VALUE OF DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN 0.25. |  |  | 0 |  |  | 0
3. VALUE OF ALL ALTERATIONS TO EXISTING FACILITIES NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. |  |  | 0 | 1000000 |  | 0
4. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. | [5 empty] | 0
5. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING FACILITIES AFFECTED BY BOTH 0.33 AND 1.25 FACTORS. | [5 empty] | 0
6. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATES AFFECTED BY BOTH 0.33 AND 0.25 FACTORS. | [5 empty] | 0
7. VALUE OF WORK IN DUPLICATED EXISTING FACILITIES AFFECTED BY BOTH 1.25 AND 0.25 FACTORS. | [5 empty] | 0
8. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25, 0.33 AND 0.25 FACTORS. | [5 empty] | 0
TOTAL VALUE OF WATER & WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR. (Carried over from "WTW Input" sheet) |  |  | 0 | 0 | 0 | 0
TOTAL VALUE OF ALL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE |  |  | 0 | 1000000 | 0 | 0
1. TOTAL REINFORCED CONCRETE & STRUCTURAL STEEL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1 (2) OF THE GAZETTE. |  |  | 0 | 0 |  | 0
1. TOTAL COST OF THE WORKS COMPRISING THE PROJECT, INCLUDING P&G & CPA. (Only if the engineer is appointed as principal agent) |  |  | 0 | 0 |  | 0
PAGE II OF INPUT DATA
CONTRACT ADMINISTRATION & INSPECTION AND CLOSE-OUT STAGES (INTERIM PAYMENTS) ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA |  |  |  |  | (C) VALUE OF COMPLETED WORK (STAGE 5 & 6) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF WORK COMPLETED NOT AFFECTED BY ANY FACTORS | [5 empty] | 0
2. VALUE OF ALL ALTERATIONS TO EXISTING FACILITIES COMPLETED NOT AFFECTED BY ANY FACTOR OTHER THAN THE 1.25. |  |  |  |  | 1000000 | 0
VALUE OF WATER & WASTEWATER TREATMENT WORKS COMPLETED AFFECTED BY THE 1.25 FACTOR. (Carried over from the "WTW Input" sheet) |  |  |  |  | 0 | 0
VALUE OF ALL WORK COMPLETED, APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE |  |  |  |  | 1000000 | 0
1. VALUE OF REINFORCED CONCRETE & STRUCTURAL STEEL WORK COMPLETED APPROPRIATE TO CLAUSE 4.2.1 (2) OF THE GAZETTE. | [5 empty] | 0
1. TOTAL COST OF THE WORKS COMPRISING THE PROJECT COMPLETED, DURING CONSTRUCTION & COMPLETION STAGES INCLUDING P&G & CPA. (Only if the engineer is appointed as principal agent) | [5 empty] | 0
Note on F11: THE TOTAL NUMBER OF DAYS MUST BE INSERTED (ACCUMULATIVE) OTHERWISE INSERT "1"
Note on H11: AMOUNT APPROVED BY THE D: PM
Note on D18: BEAURAIN: Type "None" if not registered otherwise insert the registration number.
Note on D21: ACCORDING TO YOUR CONTRACT WITH DPW.
Note on D27: Insert the percentage tendered . In case of an appointment i.t.o the Standard Letter of Appointment, insert 100.
Note on G51: Charles beau rain: The total final value in H50 must be = H58

## Worked Example
PLEASE READ THE NOTES (1st SHEET) BEFORE STARTING TO POPULATE THE SHEETS. COMPLETE ALL YELLOW CELLS PLEASE !!!
CIVIL & STRUCTURAL ENGINEERING
|  |  | USE MULTI-DISCIPLINARY PROJECT INVOICE!!! |  |  | Version: 1.1 2012-10
| DPW FILE NUMBER: | A6089/002/9 |  | DPW PROJECT MANAGER | Paul Mashinga
| WCS NUMBER | 79867 |  | TEL NO | 012 337 2345
| WCS CONTRACT NUMBER | 2 |  | CELL | 082 699 3459
| DRAWING NUMBER | CE 56789/001/6 |  | FAX | 086 610 0300
| DISCIPLINE APPOINTED | CIVIL & STRUCTURAL ENGINEERING |  | E-MAIL ADDRESS | Paul.mashinga@dpw.gov.za
| TYPE OF PROJECT: | MULTI-DISCIPLINARY PROJECT | B
| PENALTY APPLIED | Yes | NO OF DAYS | 30 | RATE | 500
| SERVICE: DESCRIPTION | Nelspruit Police Station
| CONSULTANT NAME | John Engineer CC
| POSTAL ADDRESS: | P O Box 11111, Boksburg |  |  | CODE | 1034
| CONSULTANT OFFICE ADDRESS | Brightstar building 214, Peach str 1023, Boksburg |  |  | CODE | 1002
| TELEPHONE & FACSIMILE NUMBERS | 011 769 3456 | CELL PHONE NO | 082 344 6756 | FACSIMILE NO: | 011 769 3011
| E-MAIL ADDRESS | je@telkom.net
| VAT REGISTRATION NO: | 12345678 | 12345678 | CLIENT | NATIONAL DEPARTMENT OF PUBLIC WORKS
| COMPANY REGISTRATION NUMBER | 400-45678-10
| DATE APPOINTED : | 2012-04-03
| FEES CODE (YEAR) | 2012 | 1 | POSTAL ADDRESS | PRIVATE BAG X65
Fee in accordance with the National Department of Public Works Scope of Engineering Services and Tariff of Fees for Persons Registered in terms of the Engineering Profession Act, 2000 (Act No. 46 of 2000) dated 1 January 2012 |  |  |  | POST OFFICE | PRETORIA
|  |  |  | POSTAL CODE | 0001
|  |  |  | VAT REGISTRATION NO: | NOT REGISTERED
|  |  |  | OFFICE ADDRESS/ BUILDING NAME | CENTRAL GOVERNMENT OFFICES
TARIFF OF FEES TO APPLY : |  | PERCENTAGE BASED FEES |  | STREET & NO | 445 PRETORIUS STREET
| PERCENTAGE OF FEE TENDERED | 100 | % | TOWN/CITY | PRETORIA
| DATE OF INVOICE | 2012-11-30 |  | CODE | 0002
| CLAIM NO: | 10 |  | TEL NO | 012 337 2000
| CONSULTANT'S REF. NUMBER : | Service DPW567/102 |  | FAX NO | 012 337 3276
| INVOICE NO | DPW/001 |  | FAX-TO-EMAIL | 086 666 0000
| STAGE COMPLETED | CLOSE OUT |  | 6
| PERCENTAGE OF STAGE COMPLETED | 100% | N/A for INCEPTION, CONTRACT ADMINISTRATION or CLOSE-OUT STAGE
| CONSTRUCTION MONITORING ONLY | N
| ESTIMATED TOTAL ENGINEERING FEES | 450000
|  | PRINCIPAL AGENT (Y/N) | Y
|  | TARGETED PROCUREMENT (Y/N) | Y
|  | AGENT OF THE CLIENT (OHSA) (Only on Engineering project) (Y/N) | Y |  |  | 512000
INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES, ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA DURING CONSTRUCTION STAGE. |  |  | (A) ESTIMATED OR TENDER VALUES (STAGES 1 -4) | (B) ESTIMATED VALUE FOR DESIGN FEES DURING CONSTRUCTION (STAGE 5) | (D) FINAL MEASURED VALUES INCL. CPA & P&G (STAGE 6 ONLY) | VALUE FOR CALCULATION PURPOSES
ESTIMATES OR TENDER VALUES? |  | TENDER VALUES | 2
1. VALUE OF WORK NOT AFFECTED BY ANY FACTORS |  |  | 2100000 | 2100000 | 2100000 | 2100000
2. VALUE OF DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN 0.25. |  |  | 1000000 | 1000000 | 1000000 | 1000000
3. VALUE OF ALL ALTERATIONS TO EXISTING FACILITIES NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. |  |  | 900000 | 900000 | 900000 | 900000
4. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. |  |  | 800000 | 800000 | 800000 | 800000
5. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING FACILITIES AFFECTED BY BOTH 0.33 AND 1.25 FACTORS. |  |  | 700000 | 700000 | 700000 | 700000
6. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATES AFFECTED BY BOTH 0.33 AND 0.25 FACTORS. |  |  | 600000 | 600000 | 600000 | 600000
7. VALUE OF WORK IN DUPLICATED EXISTING FACILITIES AFFECTED BY BOTH 1.25 AND 0.25 FACTORS. |  |  | 500000 | 500000 | 500000 | 500000
8. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25, 0.33 AND 0.25 FACTORS. |  |  | 400000 | 400000 | 400000 | 400000
TOTAL VALUE OF WATER & WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR. (Carried over from "WTW Input" sheet) |  |  | 4500000 | 4500000 | 4500000 | 4500000
TOTAL VALUE OF ALL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE |  |  | 11500000 | 11500000 | 11500000 | 11500000
1. TOTAL REINFORCED CONCRETE & STRUCTURAL STEEL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1 (2) OF THE GAZETTE. |  |  | 2000000 | 2000000 | 2000000 | 2000000
1. TOTAL COST OF THE WORKS COMPRISING THE PROJECT, INCLUDING P&G & CPA. (Only if the engineer is appointed as principal agent) |  |  | 15000000 | 15000000 | 15000000 | 15000000
PAGE II OF INPUT DATA
CONTRACT ADMINISTRATION & INSPECTION AND CLOSE-OUT STAGES (INTERIM PAYMENTS) ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA |  |  |  |  | (C) VALUE OF COMPLETED WORK (STAGE 5 & 6) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF WORK COMPLETED NOT AFFECTED BY ANY FACTORS |  |  |  |  | 6100000 | 6100000
2. VALUE OF ALL ALTERATIONS TO EXISTING FACILITIES COMPLETED NOT AFFECTED BY ANY FACTOR OTHER THAN THE 1.25. |  |  |  |  | 900000 | 900000
VALUE OF WATER & WASTEWATER TREATMENT WORKS COMPLETED AFFECTED BY THE 1.25 FACTOR. (Carried over from the "WTW Input" sheet) |  |  |  |  | 4500000 | 4500000
VALUE OF ALL WORK COMPLETED, APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE |  |  |  |  | 11500000 | 11500000
1. VALUE OF REINFORCED CONCRETE & STRUCTURAL STEEL WORK COMPLETED APPROPRIATE TO CLAUSE 4.2.1 (2) OF THE GAZETTE. |  |  |  |  | 2000000 | 2000000
1. TOTAL COST OF THE WORKS COMPRISING THE PROJECT COMPLETED, DURING CONSTRUCTION & COMPLETION STAGES INCLUDING P&G & CPA. (Only if the engineer is appointed as principal agent) |  |  |  |  | 15000000 | 15000000
Note on F10: THE TOTAL NUMBER OF DAYS MUST BE INSERTED (ACCUMULATIVE) OTHERWISE INSERT "1"
Note on H10: AMOUNT APPROVED BY THE D: PM
Note on D17: BEAURAIN: Type "None" if not registered otherwise insert the registration number.
Note on D20: ACCORDING TO YOUR CONTRACT WITH DPW.
Note on D26: Insert the percentage tendered . In case of an appointment i.t.o the Standard Letter of Appointment, insert 100.
Note on E35: Charles beau rain: Only ="Y" when specifically appointed as Principal agent.
Note on E37: Charles beau rain: Only ="Y" when specifically appointed as Principal agent.

## Civ_Struct_Eng_Tax Invoice
TAX INVOICE
TO | [10 empty] | STRUCTURAL ENGINEERING | ENGINEERING PROJECT: 2012 NDPW FEES |  |  |  | Version: 1.1 2012-10
[11 empty] | CLAIM NO: | 0 |  |  | DATE OF INVOICE | 0
WCS NO: | 0 | WCS CONTRACT NO |  |  |  |  | 0 | [6 empty] | DRAWING NO: | 0
SERVICE: | 0
CLIENT | NATIONAL DEPARTMENT OF PUBLIC WORKS | [8 empty] | FILE NUMBER: |  | 0 | VAT REGISTRATION NO: |  | NOT REGISTERED
ADDRESS | 0 | [8 empty] | POST OFF |  | 0 |  |  | CODE | 0
OFFICE ADDRESS. | 0 | [8 empty] | TOWN |  | 0 |  |  | CODE | 0
BUILDING NAME | 0 | [9 empty] | TEL | 0 | FAX 1 | 0 | FAX2 | 0
PROJECT MAN: | 0 | [6 empty] | Tel | 0 |  | Cell | 0 | E-MAIL | 0
FROM
CONSULTING ENG. | 0 | [12 empty] | INVOICE NO | 0
POSTAL ADDRESS: | 0 | [13 empty] | CODE | 0
OFFICE ADDRESS. | 0 | [13 empty] | CODE | 0
| VAT REGISTRATION NO: | 0 | [10 empty] | COMPANY REGISTRATION NUMBER | 0
DATE APPOINTED : | 0 | [13 empty] | CELL | 0
CONSULTANT REF | 0 | [10 empty] | TEL | 0 |  | FAX | 0
TARIFF OF FEES TO APPLY : |  | USE TIME BASED FEES | [10 empty] | E-MAIL | 0
STAGE COMPLETED: | DETAIL DESIGN | [9 empty] | ESTIMATED TOTAL VALUE OF ENGINEERING WORK |  |  |  |  | 0
TOTAL VALUE OF REINFORCED CONCRETE & STRUCTURAL STEEL : | [8 empty] | 0 |  | ESTIMATED TOTAL VALUE OF PROJECT |  |  |  |  | 0
FEES (a) INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [15 empty] | 0
DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN .25. | [15 empty] | 0
ALTERATIONS TO EXISTING FACILITIES NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. (Including concrete cladding) | [15 empty] | 0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. | [15 empty] | 0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING FACILITIES AFFECTED BY 0.33 & 1.25 FACTORS. | [15 empty] | 0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATES AFFECTED BY 0.33 & .25 FACTORS. | [15 empty] | 0
DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25 & .25 FACTORS. | [15 empty] | 0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25, 0.33 & 0.25 FACTORS. | [15 empty] | 0
[14 empty] | SUB-TOTAL |  | 0 | 0
ADDITIONAL FEE FOR REINFORCED CONCRETE & STRUCTURAL STEEL WORK
ADDITIONAL FEE | [15 empty] | 0
PRINCIPAL AGENT FEES | [15 empty] | 0
WATER AND WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR | [15 empty] | 0
[15 empty] | TOTAL PERCENTAGE BASED FEES FOR INCEPTION, PRELIMINARY DESIGN: DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES (a) | 0
FEES (b) CONTRACT ADMINISTRATION & INSPECTION AND CLOSE OUT STAGES
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [15 empty] | 0
WORK ON ALTERATIONS TO EXISTING FACILITIES | [15 empty] | 0
[14 empty] | SUB-TOTAL |  | 0
ADDITIONAL FEE FOR REINFORCED CONCRETE & STRUCTURAL STEEL WORK
ADDITIONAL FEE | [15 empty] | 0
PRINCIPAL AGENT FEES | [15 empty] | 0
WATER AND WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR | [15 empty] | 0
[14 empty] | TOTAL PERCENTAGE BASED FEES FOR CONTRACT ADMINISTRATION & INSPECTION AND CLOSE OUT STAGES (b) |  | 0
(c) FEE FOR TARGETED/PREFERENTIAL PROCUREMENT | [14 empty] | ( c ) | 0
[15 empty] | TOTAL PERCENTAGE BASED FEES FOR ALL STAGES ((a)+(b)+(c)) | 0
[13 empty] | % OF STANDARD FEES TENDERED FOR PROFESSIONAL SERVICES | 100% | DUE | 0
FEE (d): TIME BASED FEES
REPORT STAGE (If specifically appointed for this service only) | [8 empty] | Report: Time Based fees |  |  | Total |  |  | = | 0
MAXIMUM FOR "AGENT OF THE CLIENT" |  |  |  | 1 | x | 0% | x | 55% | x | 0 | = | 0 |  | CLAIM | = | 0
CONSTRUCTION MONITORING & OTHER | [8 empty] | Time Based fees: Other |  |  | Total |  | CLAIM | = | 0
[12 empty] | TOTAL FEES (d) TIME BASED |  |  |  | 0
[14 empty] | TOTAL PERCENTAGE BASED AND TIME BASED FEES |  | 0
[14 empty] | LESS PENALTY |  | 0
[14 empty] | TOTAL PERCENTAGE BASED AND TIME BASED FEE CLAIM |  | 0
FEE (e): FEES FOR EXPENSES AND COSTS (DISBURSEMENTS)
SUBSISTENCE & TRAVELLING CHARGES |  | (Not applicable in case of a tender for professional services) | [13 empty] | 0
TYPING, DUPLICATING, COVERS & BINDERS & PRINTS | [15 empty] | 0
SITE STAFF CHARGES | [15 empty] | 0
SURVEY, SOIL TESTS AND OTHER CHARGES | [15 empty] | 0
[8 empty] | TOTAL FEES (e) EXPENSES AND COSTS (DISBURSEMENTS) | [7 empty] | 0
[10 empty] | TOTAL FEES DUE |  | (EXCL VAT) |  |  |  | 0
[10 empty] | LESS TOTAL PREVIOUS PAYMENTS (EXCL VAT) | [5 empty] | 0
0
|  |  | PLUS VAT @ |  |  |  |  | 14% |  | OF |  | 0 |  |  |  | 0
[11 empty] | PLUS NON TAXABLE EXPENSES |  |  |  |  | 0
AMOUNT DUE | [15 empty] | 0
PAGE 2 OF INVOICE
CONSULTING ENGINEER
| SIGNATURE: | [9 empty] | DATE:
for OFFICE use only:
ACCOUNTANT:
| CERTIFIED CORRECT: | [9 empty] | DIRECTOR:
| DATE: | [9 empty] | DATE:
COMMENTS
for OFFICE use only:
Budget | Payment categories
Payments | Calculated fees, Other fees & Add Services | Time Based Fees |  |  | Subsitence, Travelling, etc. |  |  | Typing, duplicating, etc |  | Site Staff & Other charges |  | VAT |  | Less Penalty Applied | Non-Taxable | Total R c
Previous | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Current | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Gross | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Budget | [15 empty] | 0
CALCULATIONS
BASIC FEE
BASIC FEE (Clause 4.2.1 (1) of the Guideline) | [9 empty] | 0 | + | 12.5% | x | 0 | )}= | 0
ADDITIONAL FEE FOR REINFORCED CONCRETE & STRUCTURAL STEEL. (Clause 4.2.1 (2)) | [9 empty] | 0 | + | 5% | x | 0 | )}= | 0
[13 empty] | TOTAL BASIC FEE |  |  | 0
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [9 empty] | 55% | x { | 0 | x | 0 |  | 0
0
DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN .25. | [7 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
ALTERATIONS TO EXISTING FACILITIES NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. (Including concrete cladding) | [7 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. | [7 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING FACILITIES AFFECTED BY 0.33 & 1.25 FACTORS. | [5 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATES AFFECTED BY 0.33 & .25 FACTORS. | [5 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25 & .25 FACTORS. | [5 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING FACILITIES AFFECTED BY 1.25, 0.33 & 0.25 FACTORS. |  |  |  | 0 | x | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
[14 empty] | SUB-TOTAL |  | 0
ADDITIONAL FEE FOR REINFORCED CONCRETE & STRUCTURAL STEEL WORK | [9 empty] | 55% | x { | 0 | x | 0 |  | 0
0
PRINCIPAL AGENT FEES | [7 empty] | 100% | x | 0% | x | 55% | x { | 0 | )}= | 0
WATER AND WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR | [11 empty] | 1.25 | x | 0 |  | 0
[15 empty] | TOTAL PERCENTAGE BASED FEES FOR INCEPTION, PRELIMINARY DESIGN: DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES (a) | 0 | 0
FEES (b) CONTRACT ADMINISTRATION & INSPECTION AND CLOSE OUT STAGES
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [9 empty] | 0% | x { | 0 | x | 0 |  | 0
0
WORK ON ALTERATIONS TO EXISTING FACILITIES | [7 empty] | 0 | x | 0% | x { | 0 | x | 0 |  | 0
0
[14 empty] | SUB-TOTAL |  | 0
ADDITIONAL FEE FOR REINFORCED CONCRETE & STRUCTURAL STEEL WORK | [9 empty] | 0% | x { | 0 | x | 0 |  | 0
0
PRINCIPAL AGENT FEES | [7 empty] | 0% | x | 0% | x | 0% | x { | 0 | )}= | 0
WATER AND WASTEWATER TREATMENT WORKS AFFECTED BY THE 1.25 FACTOR | [11 empty] | 0% | x | 0 |  | 0
[14 empty] | TOTAL PERCENTAGE BASED FEES FOR CONTRACT ADMINISTRATION & INSPECTION AND CLOSE OUT STAGES (b) |  | 0 | 0
(c) FEE FOR TARGETED/PREFERENTIAL PROCUREMENT | [7 empty] | 100% | x | 0 | x | 55% | x { | 0 | )}= | 0 | 0
[14 empty] | TOTAL PERCENTAGE BASED PROFESSIONAL FEES DUE |  | 0 | 0

## Scales
2012 Scales
SCALE_2012SE1 | CIVIL AND STRUCTURAL ENGINEERING PROJECTS |  |  | APPORTIONMENT OF THE DESIGN STAGE
0 | 512000 | 0 | 12.5% | Stage | Description | Apportionment |  | Progress | Factor
512000 | 1280000 | 64000 | 12.5% | Stage 1 | Inception | 5% | x | 100% | 5%
1280000 | 6300000 | 160000 | 10% | Stage 2 | Preliminary Design: Concept and Viability | 20% | x | 100% | 25%
6300000 | 12850000 | 662000 | 9% | Stage 3 | Design Development | 30% | x | 100% | 55%
12850000 | 32000000 | 1251500 | 8% | Stage 4 | Documentation and Procurement | 0% | x | 100% | 55%
32000000 | 64000000 | 2783500 | 6%
64000000 | 385500000 | 4703500 | 5.5%
385500000 | 1000000000 | 22386000 | 5% |  | Inception | 5
[5 empty] | Preliminary Design: Concept and Viability | 20
[5 empty] | Design Development | 30
SCALE_2012SE2 | ADDITIONAL DESIGN FEE ON REINFORCED CONCRETE & STRUCTURAL STEEL |  |  |  | Documentation and Procurement | 15
0 | 512000 | 0 | 5% |  |  | 70
512000 | 1280000 | 25600 | 5%
1280000 | 6300000 | 64000 | 4.5%
6300000 | 12850000 | 289900 | 4%
12850000 | 32000000 | 551900 | 3%
32000000 | 64000000 | 1126400 | 2%
64000000 | 385500000 | 1766400 | 1.5%
385500000 | 1000000000 | 6588900 | 1.5%

## Previous Claims
PREVIOUS CLAIMS |  |  |  | INPUT ALL INFORMATION FOR THE WHOLE PROJECT
ATTACHED TO CLAIM NO |  |  | 0 | WCS NO | 0 | VAT REGISTRATION |  |  | Y
CLAIM NO | DATE | TOTAL AMOUNT PAID, (Incl VAT & Non Taxable) | TOTAL AMOUNT PAID, (Excl VAT, Excl Non Taxable) | TOTAL NON-TAXABLE AMOUNT PAID | TOTAL AMOUNT PAID (Excl VAT) | CLAIM NO | DATE | TOTAL AMOUNT PAID, (Incl VAT & Non Taxable) | TOTAL AMOUNT PAID, (Excl VAT, Excl Non Taxable) | TOTAL NON-TAXABLE AMOUNT PAID | TOTAL AMOUNT PAID (Excl VAT)
1 |  |  | 0 |  | 0 | CARRIED OVER |  | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 38 |  | 0 | 0 | 0 | 0
3 |  | 0 | 0 | 0 | 0 | 39 |  | 0 | 0 | 0 | 0
4 |  | 0 | 0 | 0 | 0 | 40 |  | 0 | 0 | 0 | 0
5 |  | 0 | 0 | 0 | 0 | 41 |  | 0 | 0 | 0 | 0
6 |  | 0 | 0 | 0 | 0 | 42 |  | 0 | 0 | 0 | 0
7 |  | 0 | 0 | 0 | 0 | 43 |  | 0 | 0 | 0 | 0
8 |  | 0 | 0 | 0 | 0 | 44 |  | 0 | 0 | 0 | 0
9 |  | 0 | 0 | 0 | 0 | 45 |  | 0 | 0 | 0 | 0
10 |  | 0 | 0 | 0 | 0 | 46 |  | 0 | 0 | 0 | 0
11 |  | 0 | 0 | 0 | 0 | 47 |  | 0 | 0 | 0 | 0
12 |  | 0 | 0 | 0 | 0 | 48 |  | 0 | 0 | 0 | 0
13 |  | 0 | 0 | 0 | 0 | 49 |  | 0 | 0 | 0 | 0
14 |  | 0 | 0 | 0 | 0 | 50 |  | 0 | 0 | 0 | 0
15 |  | 0 | 0 | 0 | 0 | 51 |  | 0 | 0 | 0 | 0
16 |  | 0 | 0 | 0 | 0 | 52 |  | 0 | 0 | 0 | 0
17 |  | 0 | 0 | 0 | 0 | 53 |  | 0 | 0 | 0 | 0
18 |  | 0 | 0 | 0 | 0 | 54 |  | 0 | 0 | 0 | 0
19 |  | 0 | 0 | 0 | 0 | 55 |  | 0 | 0 | 0 | 0
20 |  | 0 | 0 | 0 | 0 | 56 |  | 0 | 0 | 0 | 0
21 |  | 0 | 0 | 0 | 0 | 57 |  | 0 | 0 | 0 | 0
22 |  | 0 | 0 | 0 | 0 | 58 |  | 0 | 0 | 0 | 0
23 |  | 0 | 0 | 0 | 0 | 59 |  | 0 | 0 | 0 | 0
24 |  | 0 | 0 | 0 | 0 | 60 |  | 0 | 0 | 0 | 0
25 |  | 0 | 0 | 0 | 0 | 61 |  | 0 | 0 | 0 | 0
26 |  | 0 | 0 | 0 | 0 | 62 |  | 0 | 0 | 0 | 0
27 |  | 0 | 0 | 0 | 0 | 63 |  | 0 | 0 | 0 | 0
28 |  | 0 | 0 | 0 | 0 | 64 |  | 0 | 0 | 0 | 0
29 |  | 0 | 0 | 0 | 0 | 65 |  | 0 | 0 | 0 | 0
30 |  | 0 | 0 | 0 | 0 | 66 |  | 0 | 0 | 0 | 0
31 |  | 0 | 0 | 0 | 0 | 67 |  | 0 | 0 | 0 | 0
32 |  | 0 | 0 | 0 | 0 | 68 |  | 0 | 0 | 0 | 0
33 |  | 0 | 0 | 0 | 0 | 69 |  | 0 | 0 | 0 | 0
34 |  | 0 | 0 | 0 | 0 | 70 |  | 0 | 0 | 0 | 0
35 |  | 0 | 0 | 0 | 0 | 71 |  | 0 | 0 | 0 | 0
36 |  | 0 | 0 | 0 | 0 | 72 |  | 0 | 0 | 0 | 0
37 |  | 0 | 0 | 0 | 0 | 73 |  | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 0 | Total VAT | 0 | 0 | 0 | 0 | 0

## WTW Input
INPUT VALUES FOR WATER AND WASTE WATER TREATMENT WORKS ONLY
|  |  | STRUCTURAL ENGINEERING |  |  | DATE OF INVOICE | 0
|  |  | ENGINEERING PROJECT: 2012 NDPW FEES |  |  |  | Version: 1.1 2012-10
WCS NO: |  | 0 |  |  | DETAIL DESIGN |  | STAGE
| CLAIM NO: |  |  | 0
CONSULTANT |  | 0
SERVICE | 0
INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES, ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA DURING CONSTRUCTION STAGE.AND ARE AFFECTED BY THE ADDIONAL FEE FACTOR OF 1.25. |  |  |  | (A) ESTIMATED OR TENDER VALUES (STAGES 1 -4) | (B) ESTIMATED VALUE FOR DESIGN FEES DURING CONSTRUCTION (STAGE 5) | (D) FINAL MEASURED VALUES INCL. CPA & P&G (STAGE 6 ONLY) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF WATER & WASTE WATER TREATMENT WORKS NOT AFFECTED BY OTHER FACTORS | [6 empty] | 0
2. VALUE OF W&WW. T. W. DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN 0.25. | [6 empty] | 0
3. VALUE OF ALL ALTERATIONS TO EXISTING W. & WW. T. W NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. | [6 empty] | 0
4. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN W. & WW. T. W NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. | [6 empty] | 0
5. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING W. & WW. T. W AFFECTED BY 0.33 AND 1.25 FACTORS. | [6 empty] | 0
6. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN W. & WW. T. W DUPLICATES AFFECTED BY 0.33 AND 0.25 FACTORS. | [6 empty] | 0
7. VALUE OF WORK IN DUPLICATED EXISTING W. & WW. T. W AFFECTED BY 1.25 AND 0.25 FACTORS. | [6 empty] | 0
8. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING W. & WW. T. W AFFECTED BY 1.25, 0.33 AND 0.25 FACTORS. | [6 empty] | 0
TOTAL VALUE OF ALL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GUIDELINE. (Carried over to the Main Input sheet) |  |  |  | 0 | 0 | 0 | 0
CONTRACT ADMINISTRATION & INSPECTION AND CLOSE-OUT STAGES (INTERIM PAYMENTS) ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA AND ARE AFFECTED BY THE ADDIONAL FEE FACTOR OF 1.25. | [5 empty] | (C) VALUE OF COMPLETED WORK (STAGE 5 & 6) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF W & WW T W COMPLETED NOT AFFECTED BY OTHER FACTORS | [6 empty] | 0
2. VALUE OF ALL ALTERATIONS TO EXISTING W & WW T W COMPLETED ALSO AFFECTED BY THE 1.25 FACTOR | [6 empty] | 0
TOTAL VALUE OF ALL W & WTW WORK COMPLETED, APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE. Carried over to the "Main Input" sheet) | [5 empty] | 0 | 0

## Worked Example(WTW)
INPUT VALUES FOR WATER AND WASTE WATER TREATMENT WORKS ONLY
|  |  | CIVIL & STRUCTURAL ENGINEERING |  |  | DATE OF INVOICE | 2012-11-30
|  |  | ENGINEERING PROJECT: 2012 NDPW FEES |  |  |  | Version: 1.1 2012-10
WCS NO: |  | 79867 |  |  | CLOSE OUT |  | STAGE
| CLAIM NO: |  |  | 10
CONSULTANT |  | John Engineer CC
SERVICE | Nelspruit Police Station
INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES, ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA DURING CONSTRUCTION STAGE.AND ARE AFFECTED BY THE ADDIONAL FEE FACTOR OF 1.25. |  |  |  | (A) ESTIMATED OR TENDER VALUES (STAGES 1 -4) | (B) ESTIMATED VALUE FOR DESIGN FEES DURING CONSTRUCTION (STAGE 5) | (D) FINAL MEASURED VALUES INCL. CPA & P&G (STAGE 6 ONLY) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF WATER & WASTE WATER TREATMENT WORKS NOT AFFECTED BY OTHER FACTORS |  |  |  | 1000000 | 1000000 | 1000000 | 1000000
2. VALUE OF W&WW. T. W. DUPLICATES NOT AFFECTED BY ANY FACTOR OTHER THAN 0.25. |  |  |  | 200000 | 200000 | 200000 | 200000
3. VALUE OF ALL ALTERATIONS TO EXISTING W. & WW. T. W NOT AFFECTED BY ANY FACTOR OTHER THAN 1.25. |  |  |  | 300000 | 300000 | 300000 | 300000
4. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN W. & WW. T. W NOT AFFECTED BY ANY FACTOR OTHER THAN 0.33. |  |  |  | 400000 | 400000 | 400000 | 400000
5. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING W. & WW. T. W AFFECTED BY 0.33 AND 1.25 FACTORS. |  |  |  | 500000 | 500000 | 500000 | 500000
6. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN W. & WW. T. W DUPLICATES AFFECTED BY 0.33 AND 0.25 FACTORS. |  |  |  | 600000 | 600000 | 600000 | 600000
7. VALUE OF WORK IN DUPLICATED EXISTING W. & WW. T. W AFFECTED BY 1.25 AND 0.25 FACTORS. |  |  |  | 700000 | 700000 | 700000 | 700000
8. VALUE OF MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING W. & WW. T. W AFFECTED BY 1.25, 0.33 AND 0.25 FACTORS. |  |  |  | 800000 | 800000 | 800000 | 800000
TOTAL VALUE OF ALL WORK BY THE ENGINEER APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GUIDELINE. (Carried over to the Main Input sheet) |  |  |  | 4500000 | 4500000 | 4500000 | 4500000
CONTRACT ADMINISTRATION & INSPECTION AND CLOSE-OUT STAGES (INTERIM PAYMENTS) ALL VALUES MUST INCLUDE RELEVANT PROPORTION OF P&G AND CPA AND ARE AFFECTED BY T | [5 empty] | (C) VALUE OF COMPLETED WORK (STAGE 5 & 6) | VALUE FOR CALCULATION PURPOSES
1. VALUE OF W & WW T W COMPLETED NOT AFFECTED BY OTHER FACTORS | [5 empty] | 2000000 | 2000000
2. VALUE OF ALL ALTERATIONS TO EXISTING W & WW T W COMPLETED ALSO AFFECTED BY THE 1.25 FACTOR | [5 empty] | 2500000 | 2500000
TOTAL VALUE OF ALL W & WTW WORK COMPLETED, APPROPRIATE TO CLAUSE 4.2.1.(1) OF THE GAZETTE. Carried over to the "Main Input" sheet) | [5 empty] | 4500000 | 4500000

## WTW Calculations
CALCULATIONS FOR WATER AND WASTE WATER TREATMENT WORKS
STRUCTURAL ENGINEERING
[9 empty] | ENGINEERING PROJECT: 2012 NDPW FEES | [7 empty] | Version: 1.1 2012-10
| CLAIM NO: | 0 | [13 empty] | DATE OF INVOICE | 0
WCS NO | 0 | [5 empty] | DETAIL DESIGN | [7 empty] | STAGE
SERVICE: | 0
| CONSULTING ENG | 0
| INVOICE NUMBER: | 0
[12 empty] | TOTAL VALUE OF ENGINEERING WORK : |  |  |  |  | 0
[12 empty] | TOTAL VALUE OF WORKS : |  |  |  |  | 0
BASIC FEE FOR WATER AND WASTE WATER TREATMENT WORKS
BASIC FEE | [10 empty] | 0 | + | 12.5% | x | 0 | )}= | 0
FEES (a) INCEPTION, PRELIMINARY DESIGN: CONCEPT AND VIABILITY, DETAIL DESIGN, DOCUMENTATION AND PROCUREMENT STAGES
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [10 empty] | 55% | x { | 0 | x | 0 |  | 0
0
DUPLICATES IN W&WWTW FACILITIES NOT AFFECTED BY ANY FACTOR OTHER THAN .25. | [8 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
ALTERATIONS TO EXISTING W&WWTW FACILITIES ALSO AFFECTED BY 1.25 FACTOR. | [8 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN W&WWTW FACILITIES ALSO AFFECTED BY 0.33 FACTOR | [8 empty] | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN EXISTING W&WWTW FACILITIES ALSO AFFECTED BY BOTH 0.33 & 1.25 FACTORS. | [6 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATES IN W&WWTW FACILITIES ALSO ALSO AFFECTED BY BOTH 0.33 & .25 FACTORS. | [6 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
DUPLICATED EXISTING W&WWTW FACILITIES ALSO AFFECTED BY BOTH 1.25 & .25 FACTORS. | [6 empty] | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
MASS CONCRETE FOUNDATIONS, BRICKWORK AND CLADDING IN DUPLICATED EXISTING W&WWTW FACILITIES ALSO AFFECTED BY 1.25, 0.33 & 0.25 FACTORS. |  |  |  |  | 0 | x | 0 | x | 0 | x | 55% | x { | 0 | x | 0 |  | 0
0
FEE FOR PRELIMINARY DESIGN, DESIGN & TENDER AND WORKING DRAWING STAGES FOR WATER AND WASTE WATER TREATMENT WORKS | [16 empty] | 0
FEES (b) CONTRACT ADMINISTRATION & INSPECTION AND CLOSE OUT STAGES
WORK NOT AFFECTED BY ANY OTHER FACTORS. | [10 empty] | 0% | x { | 0 | x | 0 |  | 0
0
ALTERATIONS TO EXISTING W&WWTW FACILITIES ALSO AFFECTED BY 1.25 FACTOR. | [8 empty] | 0 | x | 0% | x { | 0 | x | 0 |  | 0
0
| FEE FOR CONSTRUCTION AND COMPLETION STAGE OF WATER AND WASTE WATER TREATMENT WORKS | [15 empty] | 0
|  |  | TOTAL FEE FOR WATER AND WASTE WATER TREATMENT WORKS ONLY | [13 empty] | 0

## Summary A3
ANNEXURE A3
SUMMARY OF FEE ACCOUNT
[5 empty] | CLAIM No : | 0 |  |  | Date | : | 0
| Name of Service |  | : | 0
|  |  |  | WCS | 0
| Name of Consultant Firm |  | : | 0
| Address of Consultant Firm |  |  | 0 | [5 empty] | PC | 0
| Departmental File Ref |  | : | 0 |  |  | Our Ref No. | : | 0
| VAT Registration No. |  | : | 0 |  |  | Tax Invoice No. | : | 0
| 1. PROFESSIONAL FEES | [9 empty] | Total (No VAT)
SCHEDULE
| Tariff of Fees |  | : | Percentage based fees |  |  | (From Tax Invoice) |  |  |  | 0
[7 empty] | Less Penalty Applied |  |  |  | 0
[7 empty] | Cumulative to date Amount |  | This Claim Amount
V | Time Basis Fee |  | :
|  | Agent of the Client (OHSA) |  |  |  |  | 0 |  | 0
|  | Report Fee |  |  |  |  | 0 |  | 0
|  | Construction Monitoring (If applicable) |  |  |  |  | 0 |  | 0
|  | Other - Specify |  |  |  |  | 0 |  | 0
| Less : | Report Fee now Included in Tariff |  |  |  |  | 0 |  | 0
[6 empty] | TOTAL TIME BASIS FEE THIS CLAIM: | 0 |  | 0 |  | 0
Disbursements
| 2. DISBURSEMENTS | [5 empty] | Cumulative to date Amount |  | This Claim Amount
W | Subsistence & Travelling |  | : |  |  |  | 0 |  | 0
X | Typing, Duplicating, binding & Printing | [5 empty] | 0 |  | 0
|  | TOTAL DISBURSEMENTS THIS CLAIM: |  |  |  |  | 0 |  | 0 |  | 0
| 3. SITE STAFF, SURVEYS & TESTS | [5 empty] | Site Staff, Tests & Other
[7 empty] | Cumulative to date Amount |  | This Claim Amount
Y | Site Staff | [5 empty] | 0 |  | 0
Y | Survey, & Soil Testing | [5 empty] | 0 |  | 0
| TOTAL SITE STAFF, TESTS & OTHER THIS CLAIM: | [5 empty] | 0 |  | 0 |  | 0
Z | [5 empty] | Plus: Airport TAX & other TAX : no VAT Claimable: | 0 |  | 0 |  | 0
[6 empty] | TOTAL EXPENSES TO DATE: | 0 |  | 0
|  |  |  | TOTAL | [6 empty] | 0
|  |  |  | Plus : | 14% | VAT x | 0 |  |  |  | 0
|  |  |  | PLUS NON VAT ITEMS | [6 empty] | 0
|  |  |  | AMOUNT OF THIS CLAIM No : | [6 empty] | 0
NOTE: COMPLETE ONLY THE APPROPRIATE SECTIONS

## Time Based
SCHEDULE V: TIME BASED FEES
INPUT ALL INFORMATION FOR THE WHOLE PROJECT | [7 empty] | NOTE: ALL ITEMS MUST EXCLUDE VAT
|  | Claim No: |  | 0 | PROJECT NO: | 0
Approval |  | Date | Describe | Approval | Date | Describe
A |  |  |  | D
B |  |  |  | E
C |  |  |  | F
1. AGENT OF THE CLIENT FEES CALCULATED ON TIME BASIS: TO BE CAPPED ON 6% OF BASIC FEES
Claim No | Date | Name | Designation | Task | Reason | Hours | Rate (R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Agent of the client: Time Based fees Excl. VAT | 0
Previously claimed
2. Report stage (Only if specifically appointed as such)
Claim No | Date | Name | Designation | Task | Reason | Hours | Rate (R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Report: Time Based fees Excl. VAT | 0
Previously claimed
3. Construction monitoring (only after written approval)
Claim No | Date | Name | Designation | Task | Reason | Hours | Rate (R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Construction monitoring: Time Based fees Excl. VAT | 0
Previously claimed
4. Other
Claim No | Date | Name | Designation | Task | Reason | Hours | Rate (R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Other: Time Based fees Excl. VAT | 0
Previously claimed
[7 empty] | Cumulative Report Stage, Construction monitoring & Other TOTAL Excl. VAT | 0
[7 empty] | Previously claimed (Including for Agent of the Client) | 0

## Subsistence & Travelling
SCHEDULE W: SUBSISTENCE & TRAVELLING EXPENSES | [5 empty] | (Import information from Trip Sheet Form A5)
INPUT ALL INFORMATION FOR THE WHOLE PROJECT |  |  |  |  | NOTE: ALL ITEMS MUST EXCLUDE VAT
Claim No |  |  | 0 |  |  |  | WCS NO: |  | 0
1. Travelling Time
A. By private car
Trip No | Date | Name | Designation |  | From | To | Vehicle | Reason |  |  | Total Hours | Hours claimed* | Rate (R) | Amount Claimed
1 | [11 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[12 empty] | 0 |  | 0
[13 empty] | Cumulative Travelling Time claim Excl. VAT | 0
Previously claimed
B. **By Airways - Including time travelled by own or hired car or shuttle. Attach all air ticket receipts and other relevant documents
| OUTWARD JOURNEY |  |  |  |  | RETURN JOURNEY |  |  |  |  | Travelling time (hrs.)
Trip No. |  |  | First destination | Second Destination | Arrival date & time at second destination | Date & Time | Depart from | First destination | Second Destination | Arrival date & time at second destination |  | Hours claimed* | Rate (R) | Amount Claimed
| Date & Time | Depart from
1 | 2012-10-06 06:00 | Home | OR Tambo | CPT RM | 2012-10-06 11:45 | 2012-10-07 16:00 | CPT RM | CPT Airport | Home | 2012-10-07 21:15 | 11 | 11 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[11 empty] | 0 | 0 |  | 0
[13 empty] | Cumulative Travelling Time for air travel claim Excl. VAT | 0
Previously claimed
[13 empty] | Cumulative Total Travelling Time Excl. VAT | 0
[13 empty] | Total Previously claimed | 0
[13 empty] | Total this claim | 0
2. Motor Vehicle Expenses [Up to 3000 cc engine capacity]
| Vehicle A | Make: | Toyota | [5 empty] | Engine Capacity: | 1600
| B | Make: | [6 empty] | Engine Capacity:
| C | Make: | [6 empty] | Engine Capacity:
Trip No | Date | Name | Reason | Vehicle | From |  | Destination |  |  | Parking Charges | Toll Gates | Total Distance | Rate/km ( R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[13 empty] | Cumulative Motor Vehicle Expenses Excl. VAT | 0
Previously claimed
3. Subsistence Charges [See your letter of appointment. Use either Table 4 or Table 5, not both]
Trip No | Date | Name |  | Designation |  | City / Town |  | Invoice No. |  | Hotel Name |  | Total Days | Total Hours | Amount Claimed
[13 empty] | Cumulative Subsistence Charges Excl. VAT | 0
Previously claimed
4. Other Transport/Air/Bus/Hired vehicle/other
Trip No | Date | Name | Designation | From | To | Service Provider |  | Flight No Outward |  | Flight No Return | Invoice Number |  | Invoice Date | Amount Claimed
[13 empty] | Cumulative Public Transport Excl. VAT | 0
Previously claimed
[13 empty] | Cumulative Travelling & Other Transport Total Excl. VAT | 0
[13 empty] | Previously claimed | 0
[13 empty] | Total this claim | 0
** Air travel: travel time on ticket ± 1.5 hours allowed
over and above flight travel time.
(± 1 hour booking in and ± 0.5 hour collecting Luggage)

## Trip Sheet
|  |  | TRIP SHEET: SUBSISTENCE & TRAVELLING COSTS: | [8 empty] | ANNEXURE A5
|  |  | (Refer to Letter of Appointment) (Excluding Site Staff) | [9 empty] | Sheet
|  |  |  | Attached to Claim No |  |  |  | : | 0 |  |  | Trip No :
[8 empty] | WCS No: | 0 |  |  | Dated :
Purpose of Journey |  |  | :
Staff Member |  |  | :
TRIP DETAILS |  | * Away from Office only applicable for more than 24 hours only
A. AIR TRAVEL TRIP DETAILS | [6 empty] | First desti- |  | Travel | (Applicable for Air travel) |  |  | Second | Arrival time
|  |  | Depart time |  | Depart from |  | nation |  | time to | **Airport | Duration | Tvl time | Desti- | at second
| Date |  | Office/home |  | Office/home |  | Airport |  | 1st des | Time | of Flight | 2nd des | nation | destination
Outward
Return
[9 empty] | (a) | (b) | (c) | (d) |  | Hours
** Air travel: travel time on ticket ± 1.5 hours allowed | [8 empty] | Total Travelling Time (a) + (b) + (c) + (d) |  |  |  |  | 0
over and above flight travel time. | [12 empty] | Days | Hours
(± 1 hour booking in and ± 0.5 hour collecting Luggage) | [9 empty] | *Away from office |  |  | 0
B. MOTOR VEHICLE TRIP DETAILS
| Outward Journey | [6 empty] | Return Journey |  |  |  | Travel-
Departure |  |  | Arrival |  |  |  | Departure |  |  | Arrival |  | ling | *Away from office
Time | Date |  | Time |  | Date |  | Time |  | Date | Time | Date | Time | Days | hours
Totals
1. SUBSISTENCE AND TRAVELLING TIME CHARGES
Subsistence charges/Special daily allowance * | [8 empty] | 2. TRAVELLING TIME CHARGES
Time Away |  |  | Subsistence |  | Amount |  |  |  | Distance to Destination ± |  |  |  |  | km
Days | Hours |  | Rate |  | Claimed |  |  |  | Travelling time less 2 hours per return trip
0 |  |  |  | /d | 0 |  |  |  | Total | Total | less | Total | Travel | Amount
0 | Spec Allow |  |  | /d | 0 |  |  |  | hrs Tvl | Trips | 2hrs/trip | hours | Rate | Claimed
| 0 | hrs |  | /hr | 0
Spec Allow | 0 | hrs |  | /hr | 0 |  |  |  | 0 | Trip |  | 0 |  | 0
|  |  | 1. Total |  | 0 | [6 empty] | 2. Total |  | 0
3. MOTOR VEHICLE CHARGES
From | Outward |  | Return | [5 empty] | Vehicle | Capac. | Rate | Toll Gate |  | Amount
To | Journey |  | Journey |  | Site |  | Total | km | Type | cc | Cents | VAT | Charge | VAT Excl
Pretoria
Polokwane |  | km |  | km |  | km | 0 | km | Sedan |  |  | 14% |  | 0
[9 empty] | Petrol |  |  |  | 0
[12 empty] | 3. Total |  | 0
4. ACCOMMODATION
Date |  |  | City/Town |  |  |  | Name of Supplier |  |  |  | Invoice Number |  |  | Amount
0
5. PUBLIC TRANSPORT CHARGES
Date |  |  |  | Car Hire : Company | [5 empty] | Invoice Number |  |  | Total | Amount
[13 empty] | 4 | 0
6. Flight Numbers | [13 empty] | Cost of
| Return |  | Outward Journey | [5 empty] | Return Journey |  |  |  | Total | Ticket(s)
[13 empty] | 5 (a) | 0
|  |  | Plus : | Airport Tax |  |  |  |  | (No VAT Claimable) |  |  |  | 5 (b) | 0
[9 empty] | TOTAL : Airport Tax (No VAT) |  |  |  | 5 (b) | 0
[9 empty] | TOTALS 1 - 5 (Carried : Annex A5(A)) |  |  |  |  | 0
* | Only actual costs are payable in respect of absence from office of less than 24 hours. (Attach invoices)
Should the daily tariff as set out in Table 4 be inadequate, substantiated actual costs plus a special daily allowance as shown in Table 5 for incidental expenses, may be claimed. Please note that you may only claim according to Table 4 or Table 5. (In case of Table 5 - submit invoices) Accommodation should be limited to the equivalent of a three star hotel and no alcoholic beverages or entertainment costs may be claimed for.
Note on O4: USE ONLY ONE FORM PER TRIP PLEASE

## Typing, Duplicating, & Printing
SCHEDULE X: TYPING, DUPLICATING & PRINTING
INPUT ALL INFORMATION FOR THE WHOLE PROJECT |  |  |  |  | NOTE: ALL ITEMS MUST EXCLUDE VAT
| Claim No: | 0 |  | WCS NO | 0
1. Typing
Claim No | Date | Description of Document: |  |  |  |  | Pages | Rate | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[8 empty] | Cumulative Typing Total | 0
Previously claimed
2. Duplicating
Claim No | Date | Description of Document |  |  |  | Pages | Copies | Rate | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[8 empty] | Cumulative Duplicating Total | 0
Previously claimed
3. Covers and Binders
Claim No | Date | Description of Document |  |  |  |  | No of Documents | Rate | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[8 empty] | Cumulative Covers & Binders Total | 0
Previously claimed
4. Printing Costs
Claim No | Date | Delivered to | No of Prints | Drawing Numbers |  | Size | Type | Rate | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[8 empty] | Cumulative Printing Total | 0
Previously claimed
Cumulative Typing Duplicating & Printing costs Excl VAT | [8 empty] | 0
[8 empty] | Previously claimed | 0

## Site staff & Other
SCHEDULE Y: SITE STAFF & OTHER CHARGES
INPUT ALL INFORMATION FOR THE WHOLE PROJECT |  |  |  |  | NOTE: ALL ITEMS MUST EXCLUDE VAT
Claim No: |  |  | 0 |  | WCS No | 0
A: Part Time Supervision
Claim No | Month | Name | Designation |  | Approved Hours | Claimed Hours | Rate (R) | Amount
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Part Time Supervision Excl VAT | 0
Previously claimed
B: Full Time Supervision
Claim No | Date | Name |  | Designation |  | Portion claimed % | Approved Remuneration | Amount
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Full Time Supervision Excl VAT | 0
Previously claimed
C: Travelling expenses
Claim No | Date | Name |  | Distance approved km | Distance km | Vehicle cc | Tariff (R) | Amount
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Travelling expenses | 0
Previously claimed
[7 empty] | Cumulative Site Staff Charges Excl VAT | 0
[7 empty] | Previously claimed | 0
D: Survey, Soil Tests and Other Charges
Claim No | Date | Description |  | Invoice or TMB Number | Laboratory/ Place | Number of tests | Approved rate (R) | Amount Claimed
0
0
0
0
0
0
0
0
0
0
[7 empty] | Cumulative Survey, Soil Tests and Other Charges Excl VAT | 0
Previously claimed
[7 empty] | Cumulative Site Staff, Soil Tests & Other Charges Excl VAT | 0
[7 empty] | Previously claimed | 0

## Non Taxable
SCHEDULE Z: NON-TAXABLE EXPENSES
INPUT ALL INFORMATION FOR THE WHOLE PROJECT
Claim No: |  |  | 0 |  |  | WCS NO | 0
1. Non Taxable Services
Claim No | Date | City/Town/Site name |  |  | Reference No | Description |  |  | Amount Claimed
[8 empty] | Cumulative Non Taxable Expenses Total | 0
Total Previous Payments Received for this item
[8 empty] | Non-taxable Expenses Total for this invoice | 0
Non Taxable Expenses could include any of the following [This list is not exclusive]:
A. |  | Airport tax |  | C. | Hotel levy |  | E.
B. |  | Re-Fuel charges |  | D. | Other |  | F.
Note on J19: Enter the total amount of all previous payments on this item here as well as on the Previous Payments sheet.