INTRODUCTION / PREFACE

The aim of this manual is to serve as a guide to the functions, duties and responsibilities of consulting civil engineers in the execution of projects for the Department of Public Works.  There has been a growing need by the Department of Public Works to improve on the manual by:

a)	Magnifying the roles and responsibilities of entities involved in the execution of projects for 	the Department.

b) 	Ensuring compliance with statutory legislation governing the execution of projects by the Department.

c) 	Generally improving quality and ensure successful implementation of projects with regards to budget and time.

d) 	Attempting to improve the quality of life, skills base of communities through implementation of projects where possible in order to create:

•	sustained service delivery, growth and job creation to address unemployment and poverty as well as the scarce and critical skills needed to meet the AsgiSA (Accelerated and shared growth initiative for South Africa) objectives.

•	relief to the poor and unemployed through temporary but useful work, which has the added benefit of transferring of skills and seeks to engage with institutions of higher learning to ensure a constant supply of suitably qualified built environment practitioners

The Guideline Scope of Services and Tariff of Fees for Persons Registered in terms of the Engineering Profession Act 2000 published annually as well as The Engineering Profession Act 2000 (Act No. 46 of 2000) amongst other legislation, form the basis of the manual.  To ensure uniformity and consistency, the manual assumes the same definitions, interpretation, philosophy of these documents as far as possible (unless where indicated otherwise).  In keeping with the above, the manual has been structured as follows:

- Section A:  General Procedures

- Section B:  Inception Stage

- Section C:  Concept and Viability and Design development Stages

- Section D:  Documentation and Procurement

- Section E:  Contract Administration and Inspection and Close-out Stages

- Section F:  Design Guide

- Section G:  Relevant PRM-forms

- Section H:  Reference Documents