PW347/2012

DEPARTMENT OF PUBLIC WORKS

CIVIL ENGINEERING MANUAL

APRIL 2012

Section A

General Procedures

Section B

Inception

Section F

Design Guide

Section H

Reference Documents

Section E

Construction: Contract

Administration, Inspection,

Variations and Close-out

Section D

Documentation and

Procurement

Section C

Concept and Viability and

Design Development

Section G

Relevant PRM-form

Section D

Documentation and

Procurement

PW347/2012

DEPARTMENT OF PUBLIC WORKS

CIVIL ENGINEERING MANUAL

APRIL 2012

Section A

General Procedures

Section B

Inception

Section F

Design Guide

Section G

Relevant PRM-form

Section H

Reference Documents

Section E

Construction: Contract

Administration, Inspection,

Variations and Close-out

Section D

Documentation and

Procurement

Section C

Concept and Viability and

Design Development

| CONTENTS LIST |  |  |
| --- | --- | --- |
| SECTION | DESCRIPTION | PAGE COLOUR |
|  | INTRODUCTION | White |
| A | GENERAL PROCEDURE General Procedure | White |
| B | INCEPTION STAGE 1: Inception Annexure: Section B | Blue |
| C C1 C2 | DESIGN: CONCEPT AND VIABILITY (PRELIMINARY DESIGN) AND DESIGN DEVELOPMENT (DETAIL DESIGN) STAGE 2: Concept and Viability (Preliminary design) STAGE 3: Design Development (Detail design) | Green |
| D | DOCUMENTATION AND PROCUREMENT STAGE 4: Documentation and Procurement Annexure: Section D | Pink |
| E E1 E2 E3 | CONSTRUCTION: CONTRACT ADMINISTRATION, INSPECTION, VARIATIONS AND CLOSE-OUT STAGE 5: Contract Administration and Inspection Variations STAGE 6: Close-out Annexure: Section E | Yellow |
| F | DESIGN GUIDE | Green |
| G | RELEVANT PRM-FORMS | White |
| H | REFERENCE DOCUMENTS | White |

INTRODUCTION

The purpose of this manual is to serve as a guide to the functions, duties and responsibilities of consulting civil engineers in the execution of projects for the Department of Public Works.

The format of the manual is in accordance with the “Guideline Scope of Services and Tariff of Fees for Persons Registered in terms of the Engineering Profession Act, 2000 (Act No. 46 of 2000)” published every year by ECSA in the Government Gazette, adapted by the Department in its document “Scope of Engineering Services and Tariff of Fees for Registered Professionals”, at the beginning of each year, to suit its requirements.

The manual covers for the following types of appointments:

Comprehensive projects:  Building contracts – JBCC

Engineering projects:  Civil contracts – GCC

Repair and maintenance projects – GCC.

In keeping with the above, this manual is structured as follows:

SECTION A:  GENERAL PROCEDURE

As the title implies this section contains information on procedures and other information of a general nature which, will impact on the consulting civil engineer in the execution of his duties.

As such, it contains inter-alia:

Definitions

Information pertaining to:

Relationships and procedures applicable to dealings with the Department, the Client/User Department and other consultants

Forms of contract

Financial and quality control

Procedures relating to remuneration

Drawings.

SECTIONS B to E

Sections B to E focus on the services to be provided by the consulting civil engineer in the execution of the project(s) for which he/she is appointed to take the project through to successful completion of construction.

In order to follow a logical approach the six stages of a project identified in the “National Department of Public Works: Scope of Engineering Services and Tariff of Fees for Registered Professionals” are grouped according to the specific phase of a project where approval, by the responsible Departmental Project Manager, is required before proceeding to the next stage with the project.

The stages have therefore been grouped in the following sections:

Section B:	Inception

Stage 1:  Inception

Section C:	Design

Stage 2:  Concept and viability (Preliminary design)

Stage 3:  Design development (Detail design)

Section D:	Documentation and Procurement

Stage 4: Documentation and procurement

Section E:	Construction

Stage 5:  Contract Administration and Inspection

Stage 6:  Close-out.

SECTION B:  INCEPTION

Stage 1:  Inception

The primary aims of this stage are to:

Establish client requirements and preferences (Project brief)

Assess user needs and options

Assess the suitability of the site and site conditions – dolomite, taking into account the Site Clearance Certificate issued by the Departmental Town Planning Directorate

Assess special actions that may be required to develop the brief on the site

Prepare an inception report dealing with the above.

SECTION C:  DESIGN (CONCEPT AND VIABILITY (Preliminary Design) and DESIGN DEVELOPMENT (Detail Design))

In accordance with the approach of grouping of activities, this section consists of the two stages associated with the design of the civil engineering services associated with the project by the consulting civil engineer.

Stage 2:  Concept and viability (Preliminary design)

This stage involves the preparation and finalisation of the project concept in accordance with the brief as well as the investigations and assessments carried out during the inception stage.  This includes:

A concept design report – viability, preliminary design, process design

Preliminary programme and estimate.

Stage 3:  Design development (Detail design)

In this stage, the concepts developed in the preliminary design stage, and agreed with the Departmental Project Manager are further developed into detailed designs and specifications that are suitable for:

The preparation of the tender enquiry documents

Obtaining the necessary approval from the relevant authorities

Preparing detailed cost estimates.

SECTION D:  DOCUMENTATION AND PROCUREMENT

Stage 4:  Documentation and procurement

This stage entails preparation of the procurement and construction documentation, confirming and implementing the procurement strategies and lay out of procedures for effective and timeous procurement of necessary resources for execution of the project.

SECTION E:  CONSTRUCTION (CONTRACT ADMINISTRATION, INSPECTION AND CLOSE-OUT)

In accordance with the approach of grouping of activities, this section consists of the two stages associated with the construction phase of the civil engineering services associated with the project as well as the roles and responsibilities of the consulting civil engineer during the construction of the project.

Stage 5:  Contract Administration and Inspection

This stage sets out the duties and responsibilities of the consulting civil engineer relating to the supervision of the construction of the works for which the consulting civil engineer has been appointed and which have been included in the documentation as approved by the Departmental Project Manager.  This also includes his responsibilities in ensuring that the Contractor(s) comply with all the relevant acts and statutory regulations, e.g. National Water Act (Act 36/1998), Occupational Health and Safety Act (Act 85/1993), etc.

The Consultant Engineer’s functions in respect of the administration of the contract and construction monitoring of the works are laid down in principle in Section X1 of the Consultant's Letter of Appointment.

Variations

Variations from the original contract bill of quantities stem mainly from changes to Client Department requirements, instructions of the Department, incomplete design or unexpected site or other environmental situations.  These variations can either be minor, in which case they can be rectified within the project scope, or major, requiring Departmental authorization.

Every precaution must be taken to minimise variations to the contract.  The Consultant must ensure that all possible work, which is necessary to complete the project according to the required standards, is detailed and scheduled in the bill of quantities and to ensure that the anticipated work is covered by the budget for the project.  No variations due to bad design or work that could have been foreseen are allowed.  Variations will only be allowed in cases where totally unforeseen work is encountered or where the Client requires changes to the original design.

Stage 6:  Close-out

The finalisation of the project is reached with the fulfilment and completion of the project close-out – including necessary documentation to facilitate effective completion – as well as handover and operation of the project.

SECTION F to H

Sections F to H contain guidelines, directives, reference documents to assist the consulting civil engineer to successfully deliver the services to take the project through to successful completion of construction.

It consists of the following sections:

Section F:	Design Guide

Section G:	Relevant PRM-forms

Section H:	Reference documents.

SECTION F:  DESIGN GUIDE

The aim of the design guide section is to provide the consulting civil engineer with information, design figures and guidelines based on experiences of the Department applicable to the design of civil engineering services most frequently encountered on its projects.

It is not a design manual but a guideline document, which is not necessarily comprehensive or applicable to all projects.

SECTION G:  PRM-FORMS

The PRM-forms are pro-forma documents used by the Department for project management.

All the PRM000civ-forms presented in this section are available on the Departmental web-site http://www.publicworks.gov.za, Item 4, under the heading Civil Engineers (not yet).

SECTION H:  REFERENCE DOCUMENTS

In Sections A to E reference is made to various other documents to be consulted in the use of this Manual for Civil Engineers 2011.  These documents are revised from time to time and the latest available version must be used.

GENERALITY OF TERMS

The following is valid in this document, except where the context requires or indicates otherwise:

The masculine includes the feminine,

the singular includes the plural, and

any reference to a natural person includes a juristic person.

The use of this manual or any section thereof or any of the guideline documents referred to in the manual or any part thereof does not exempt the Consultant of his/her professional responsibilities in the execution of his/her duties in terms of his/her brief.

SECTION A:  GENERAL PROCEDURE

CONTENTS

Item	Page

A.1	SECTION A:  GENERAL PROCEDURE	11

A.2	INTRODUCTION	11

A.3	THE MANUAL	11

A.4	DEFINITIONS (in alphabetical order)	11

A.4.1	Client/User Department	11

A.4.2	Comprehensive Project	11

A.4.3	Consultant	11

A.4.4	Department	12

A.4.5	Departmental Project Manager	12

A.4.6	Director-General	12

A.4.7	DPW-04: (EC) Contract Data:  JBCC 2000 Principal Building Agreement (Edition 4.1 of March 2005)	12

A.4.8	DPW-05:  (EC) CONTRACT DATA - (GCC (2004) 1st EDITION: 2004)	12

A.4.9	Employer	12

A.4.10	Engineer	12

A.4.11	Engineer’s Representative/Resident Engineer	12

A.4.12	Engineering Project	12

A.4.13	GCC 2004	12

A.4.15	Letter of Appointment	13

A.4.16	Project Execution Plan	13

A.4.17	Principal Agent / Lead Consulting Engineer	13

A.4.18	PRM-forms	13

A.4.19	PW371: Specification of Materials and Methods to be used	13

A.4.20	QS003:  JBCC PBA Preliminaries	13

A.5	THE EMPLOYER	13

A.6	APPOINTMENT	13

A.7	THE AGREEMENT	14

A.8	THE BRIEFING MEETING (PROJECT INITIATION MEETING) (PRM013civ)	14

A.9	APPROVAL	15

A.9.1	Official Approval	15

A.9.2	Approval by a Client/User Department	15

A.10	COMMUNICATION WITH THE CLIENT/USER DEPARTMENT	15

A.11	PROGRESS REPORTS	15

A.12	FINANCIAL CONTROL	15

A.12.1	General		15

A.12.2	Departmental Budget	15

A.12.3	Approved Cost Limit (PRM018civ)	15

A.13	QUALITY ASSURANCE PLAN	16

A.14	CONSULTANT TEAM (PRM006civ)	16

A.14.1	Appointment of other Consultants	16

A.14.2	Liaison with Consultants	16

A.14.3	Differentiation of the responsibilities of Civil and Structural Engineers	17

A.15	USE OF SPECIALISTS	17

A.15.1	Appointment of other Consultants	17

A.15.2	Use of Specialists	17

A.16	FORMS OF CONTRACT	17

A.16.1	Civil Engineering Contract	18

A.16.2	Nominated Sub-contract to Building Contract	18

A.16.3	Civil Work Included in Building Contract (Comprehensive Contract)	18

A.16.4	Separate Mechanical and/or Electrical Contract	18

A.17	CONSTRUCTION MONITORING	19

A.18	DRAWINGS	19

A.19	TRAVELLING PROCEDURES AND COSTS	19

A.20	SUBMISSION OF ACCOUNTS	19

A.20.1	Form of Submission	19

A.20.2	Claims for Subsistence and Travelling	19

A.20.3	Claims for Other Disbursements	19

A.20.4	Fees on Contract Price Adjustments	19

- SECTION A:  GENERAL PROCEDURE

- INTRODUCTION

This section contains information on procedures and other general information which will have an impact on the consulting civil engineer in the execution of his duties.

- THE MANUAL

The purpose of this Manual is to serve as a guide to the functions, duties and responsibilities of Consulting Civil Engineers (herein referred to as "The Consultant") in the design, documentation and administration of projects for the Department of Public Works (herein referred to as "The Department').

- DEFINITIONS (in alphabetical order)

The meaning of the terms not defined below will be the same as defined in the GCC 2004 and the JBCC 2000 documents.

The following words, expressions and abbreviations shall have the meanings assigned to them except where the context requires otherwise:

  - Client/User Department

Refers to the designated occupant(s) / user(s) of the facility upon completion of the project under consideration.

Any communication between the Consultant and the Client / User Department, must be arranged through the Departmental Project Manager. In addition, any requests for amendments to the approved design from the Client / User Department must be referred by the Client / User Department to the Departmental Project Manager whose written authority must be obtained before such additions / alterations can be effected.

  - Comprehensive Project

Refers to a project comprising building work together with its associated engineering work, where the engineer is subject to the authority of another professional acting as the Principal Agent.  This professional is then responsible for financial and administrative matters relating to the project.

The engineer is however still responsible for all matters relating to the civil engineering aspects of the project including inter-alia the preparation of the estimated cost of the work, preparation of specifications and schedules of quantities and general administration of the civil portion of the contract thereafter.  The main difference between the engineering project described under A.4.12 is that the engineer will report to the responsible Principal Agent, on all matters relating to the financial (cost and variations) and administrative control including progress, while at the same time keeping the Departmental Project Manager informed at all times.

The majority of projects administered by the Department will be in the form of comprehensive projects.

  - Consultant

The Consultant is the Consulting Civil Engineering Firm (and/or Consulting Civil Engineers) appointed by the Department in terms of the Letter of Appointment to execute the work for which this Manual is intended for.

  - Department

“Department” refers to the National Department of Public Works.

  - Departmental Project Manager

Duly appointed and authorised person authorised to oversee overall execution and implementation of the project on behalf of the Department.  All liaison and communication with regards to the implementation of the project must be conducted through the Departmental Project Manager.

  - Director-General

The person appointed as Head of Department, of the Department of Public Works.

  - DPW-04: (EC) Contract Data:  JBCC 2000 Principal Building Agreement (Edition 4.1 of March 2005)

The JBCC 2000 Principal Building Agreement as amended by the Department of Public Works, mainly applicable to Building Contracts.

  - DPW-05:  (EC) CONTRACT DATA - (GCC (2004) 1st EDITION: 2004)

The General Conditions of Contract for use in connection with Works of Civil Engineering Construction (1st Edition, 2004); issued by the South African Institution of Civil Engineers as amended by the Department.

  - Employer

The sole Employer is the Department of Public Works as represented by the Director General or duly authorised representatives.

  - Engineer

The “Engineer” means the natural or juristic person or partnership named as the Engineer in the Contract Data (see Annexure D2) for the supervision and management of the Engineering Works undertaken by the Contractor (Service Provider).

  - Engineer’s Representative/Resident Engineer

A person appointed from time to time by the Engineer to represent the Engineer on the Construction Site and as approved by the Department.

  - Engineering Project

Means a project of which the scope comprises mainly engineering work of one discipline and all financial and administrative matters are dealt with by the responsible consulting engineer or where the responsible engineer will act as principal agent where other disciplines are also involved.

  - GCC 2004

The General Conditions of Contract issued by the South African Institution of Civil Engineers for use in connection with Works of Civil Engineering Construction (1st Edition, 2004).

  - Letter of Appointment

Document from the Department appointing a Consultant to perform the work under consideration.  After acceptance by the Consultant in writing, this shall constitute an agreement between the Department and the Consultant. In cases where a special agreement is entered into, variations in procedure (if required) will be stated accordingly.

  - Project Execution Plan

The Project Execution Plan (PEP) is a program showing sequencing of planned events on a timescale and deliverables in conjunction with the projected / anticipated cash flows over the duration of the project.

The PEP, once approved by the Departmental Project Manager shall form part of the agreement referred to in the letter of appointment.  Thereafter, the PEP shall consist as a living document whereby, it shall serve as part of the project management tool i.t.o planning, meeting of targets etc.  The PEP where required, shall be revised accordingly in each and every stage of the project.

  - Principal Agent / Lead Consulting Engineer

Is a Consultant (not necessarily a Consulting Civil Engineering Firm) appointed by the Department, to act as the co-ordinator and team leader in a project team consisting of consultants in a project?  In a multi-disciplinary building project, this role is normally and preferably fulfilled by the Consulting Architecture Firm.  However, if so decided by the Department, the Consultant Structural Engineering Firm (and/or Consultant Structural Engineer) can act as the Principal Agent / Lead Consultant for the Department.

The Letter of Appointment from the Department and the resultant briefing meeting by the Departmental Project Manager should clarify this matter.  Where clarity is required, the Departmental Project Manager must be engaged.

  - PRM-forms

These are Pro-forma documents used by the Department for Project Management, available on the Departmental website http://www.publicworks.gov.za.

  - PW371: Specification of Materials and Methods to be used

The Department’s “Specification of Materials and Methods to be used”.

  - QS003:  JBCC PBA Preliminaries

The Department’s “Preliminaries etc. forming part of Bills of Quantities”.

- THE EMPLOYER

The Employer for the work is the Director-General: National Department of Public Works or his authorised representative.  The Consulting Engineer will deal with the Employer through the Departmental Project Manager as set out in this manual.

- APPOINTMENT

The letter of invitation to perform professional services (generally referred to as “the Letter of Appointment”) together with the associated Annexures.  This forms a binding contract between the Department and the consulting engineering firm as soon as the consultant accepts the invitation in writing.

The Consultant and the Departmental Project Manager will initial each page at the bottom right corner as well as all applicable changes/amendments made to the original contract documentation.

- THE AGREEMENT

Where the Department’s standard letter of invitation forms the basis of the appointment, the Consultant is required to execute the work in accordance with this manual and with such supplementary instructions as the Department may issue from time to time.  In cases where a special agreement is entered into, this will state any variations in procedure, which may be required.

The standard Letter of Appointment (agreement) consists of the following:

The appointment letter itself

| Section A | : | General Conditions and Information |
| --- | --- | --- |
| Section B | : | Reimbursement tariffs for typing, printing, duplicating work and forwarding |
| Section C | : | Travelling and subsistence arrangements and tariffs on charges |
| Section D | : | Indemnification of the Department by firms with limited liability |
| Section E | : | Conditions applicable to the appointment of firms in association |
| Section F | : | Competencies and/or resources required by the agent in terms of and as stipulated in the Construction Regulations, 2003 to fulfil the duties and responsibilities as the Department's "agent" in terms of these Regulations |
| Section X1 | : | Extent of civil engineering appointment |
| Section X2 | : | Professional fees in respect of an engineers appointment (all disciplines) |
| Appendix "A" | : | 2010 NDPW - Scope of Engineering Services and Tariff of Fees |
| Appendix "N" | : | Briefing document, if applicable |

After appointment, the Consultant shall compile a Project Execution Plan (PEP) indicating cash flows as well as explaining the work program.  This document, once approved, will form part of the agreement.

Remuneration tables referred to in the appointment letter are available on the Departmental website, i.e. http://www.publicworks.gov.za.

- THE BRIEFING MEETING (PROJECT INITIATION MEETING) (PRM013civ)

See also Section B.2.

The meeting / consultation held by the Department through the Departmental Project Manager with the Consultant after acceptance of the appointment by the Consultant.  At this stage, the Consultant shall advice the Department pertaining to the following:

Partner / Director that will oversee the project overall

Project team, including professional registered personnel within the employ of the Consultant's practice that will oversee, supervise and assume responsibility for the project.

Minutes of this meeting shall be kept and forwarded to the Departmental Project Manager. It shall be expected that the project team proposed by the Consultant be directly involved on the project. Secondly, changes to the project team .personnel must be communicated to the Departmental Project Manager immediately if any.

- APPROVAL

  - Official Approval

The Consulting Engineer may not proceed from one stage to another without the written consent of the Departmental Project Manager.  He must obtain prior approval before undertaking any survey, soil testing, travelling, etc.  See also Section A.15 in this regard.  All communication between parties shall be via the Departmental Project Manager.

  - Approval by a Client/User Department

Approval of any proposals by a Client/User Department - either verbally or in writing – is not binding on the Director-General and does not relieve the Consultant in any way of the responsibility for obtaining written approval of any proposals from the Departmental Project Manager.  The responsibility for the design of the project remains in all instances with the engineer – see also Section 9 of the Construction Regulations.

- COMMUNICATION WITH THE CLIENT/USER DEPARTMENT

Any discussions between the Consultant and the Client/User Department must be arranged through the Departmental Project Manager.  Any requests from Client/User Departments for amendments to the approved design must be referred by the Client/User Department to the Departmental Project Manager and his written authorisation/approval obtained before such additions/alterations may be incorporated in the design proposals.

- PROGRESS REPORTS

In order to monitor strict adherence to the time schedule required for compliance with the documentation programme laid down in terms of the Consultant's Letter of Appointment or as provided at the briefing the Consultant is required throughout the design and documentation stages to render to the Department progress reports to the last working day of each month on the form PRM014/6civ.  In completing the form, special attention must be drawn to any delays or changes in the estimated cost of the service and the cause thereof.

- FINANCIAL CONTROL

  - General

Financial control is done by the Project Manager on a dual basis, i.e. construction (execution) costs and professional fees, including travelling cost, supervision, etc.

  - Departmental Budget

The Department makes a cost provision for each of its projects for budgeting purposes.  The Consultant is required to design the project as economically for operational efficiency as possible.

  - Approved Cost Limit (PRM018civ)

With approval of the various project stages, an estimate of cost will concurrently be approved and the Consultant is required to adhere strictly to this cost limit – subject to escalation in costs or such deviation as approved by the Departmental Project Manager.  Such estimates shall include preliminary and general costs and an estimate of Contract Price Adjustment based on the formula below, but exclude any amounts for professional fees, travelling, supervision, etc. for which the Department will make its own allowance.

CPA = 85% x i x TP x [(T/2) + 3]

| Where: | i | = | Estimated rate of inflation |
| --- | --- | --- | --- |
|  | TP | = | Tender Price (estimate) |
|  | T | = | Time for completion (months) |

The Consultant must ensure that the design is comprehensive, as no allowance shall be made for any contingencies.

- QUALITY ASSURANCE PLAN

Consultants appointed by the Department are expected to have a Quality Assurance Plan to ensure that designs and overall quality of the work is according to acceptable standards. The Quality Assurance Plan shall be compliant with the latest edition of the SASS ISO 9001 (SANS9001). The Quality Assurance Plan (and/or Quality Assurance / Management Certifications from accredited service providers) shall form part of the agreement referred to in item A.2.6 above,

In the event that a Consultant that does not have a Quality Assurance Plan (and/or Quality Assurance / Management Certification) is appointed, such Consultant shall be expected to make a presentation to the Department indicating (i) actions / plans taken by the Consultant to ensure that it is rectified and (ii) date by which such a plan shall be in place.

- CONSULTANT TEAM (PRM006civ)

  - Appointment of other Consultants

Appointment of other Consultants, i.e., architects, quantity surveyors, other engineering disciplines involved in the project, are separately appointed by the Departmental Project Manager and briefed accordingly in terms of their scope of work, terms of agreement, departmental standards and technical aspects of the work.

  - Liaison with Consultants

In terms of their several agreements, all consultants are required to liaise closely with one another during all stages of the project and to keep each other fully informed of all relevant developments.  This liaison will be done via the Departmental Project Manager.  Direct liaison between consultants will only take place as determined by the Departmental Project Manager.

In cases where a Lead Consultant/Principal Agent is appointed, the Departmental Project Manager can delegate certain liaison and co-ordination functions to the Lead Consultant/ Principal Agent.

Designs must be co-ordinated with that of the other members of the design team (where applicable) before submission of proposals.  The Consultant shall not accept instructions from other consultants with regarding design standards, the extent of his brief and changes to approved proposals without the prior approval of the Departmental Project Manager.

Co-ordination between consultants must be such that work is not duplicated, as the Department will not remunerate twice for the same work.

  - Differentiation of the responsibilities of Civil and Structural Engineers

The Department expects that the issue of responsibility/liability between the Civil- and Structural Engineer(s) to be without ambiguity at inception of the Preliminary Design Report process and before a construction contract is awarded.

At the first briefing meeting, the Departmental Project Manager will spell out the different responsibilities of the civil and structural engineer.

To clarify the above, the Department would hold the structural engineer responsible for the design performance of building(s), even if earthworks were carried out under the “footprint” of the structure.  It is, therefore, the prerogative of the structural engineer to verify/accept work done under the earthworks phase of the contract.

The Civil Engineer will be responsible for the balancing of earthwork quantities and the Structural Engineer will be responsible for the bearing capacity and related specifications of earthworks under the footprint of a structure.

Although the above depends to a large extent on a well coordinated design, specification(s), drawings and supervision, the Department does not accept split responsibility in this regard.  Should the building for instance crack in due time, the structural engineer would be held responsible.

- USE OF SPECIALISTS

  - Appointment of other Consultants

Appointment of other Consultants, i.e., architects, quantity surveyors, other engineering disciplines involved in the project, are separately appointed by the Departmental Project Manager and briefed accordingly in terms of their scope of work, terms of agreement, departmental standards and technical aspects of the work.

  - Use of Specialists

If the services of a specialist consultant are required, at least three (3) quotations for these shall be sourced and submitted to the Departmental Project Manager for approval. Specialist services shall include (amongst others) the following:

Geotechnical Investigations (PRM011Aciv).

Site surveys

Traffic Impact Studies

Hydrological studies, etc.

Detection of underground services (electrical, water, sewerage, etc)

Design of fire water services (major services, three (3) quotations required)

Fire specialist may be appointed on large projects when necessary.

- FORMS OF CONTRACT

The service for which the Consultant is appointed will be executed by contract in one or more of the ways indicated below.

The Department will decide in due course what form of contract will be applied.  The Consultant’s recommendations in this regard should be included in the Preliminary Design Report and will be taken into consideration.

  - Civil Engineering Contract

In this instance, the applicable contract document for the preparation and administration of the contract is GCC 2004.

Tender documents including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared by the Consultant, and submitted to the Departmental Project Manager in draft form.  After approval, the Department will arrange for the invitation of tenders, submit these to the Consultant for recommendation, and accept a tender according to the tender procedures of the Department.

  - Nominated Sub-contract to Building Contract

Follow the same procedure as in paragraph A.16.1 except that after acceptance by the Department’s tender a procedure, the successful tenderer becomes a nominated sub-contractor to the main contractor.

  - Civil Work Included in Building Contract (Comprehensive Contract)

The majority of projects administered by the Department will be in the form of comprehensive contracts.

The applicable contract document for the preparation and administration of the contract is DPW-04 (EC):  Contract Data: JBCC 2000 Principal Building Agreement (Edition 4.1 of March 2005 as amended by the Department).

Civil engineering services are included in the building contract.  Contract drawings and technical specifications are prepared by the Civil Engineer and submitted to the Principal Agent/Project Leader, who will arrange to have these included in the main building documentation after approval.

The engineer is however still responsible for the preparation of the estimated cost of the work, preparation of schedules of quantities and general administration of the civil part of the contract thereafter.  The main difference between the engineering project described under A.4.2 is that the engineer in this instance will report to the responsible Principal Agent, on all matters relating to the financial (cost and variations) and administrative control including progress, while at the same time keeping the Departmental Project Manager informed at all times.

Although the defects liability period (maintenance period) on a building contract is normally three (3) months, the civil portion will be subject to a defects liability period of twelve (12) months.

  - Separate Mechanical and/or Electrical Contract

In certain circumstances (for example pump station installations), it may be expedient to have a separate mechanical/electrical subcontract.  Tender documents including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared in draft by the Mechanical/Electrical Consultant, and submitted to the Principal Agent in draft form.  The Principal Agent will thereafter be responsible for the compilation of the Tender Document.  After approval, the Department will arrange for the invitation of tenders, submit these to the Consultant for recommendation, and accept a tender through the Department’s tender procedures.

- CONSTRUCTION MONITORING

The Consultant will be required to supervise the construction of the works for which he has been appointed and which have been included in the documentation as approved by the Departmental Project Manager (see Section E).  The Consultant will also ensure that the Contractors comply with all the relevant acts and statutory regulations, e.g. National Water Act (Act 36 of 1998), Occupational Health and Safety Act (Act 85 of 1993), etc.

- DRAWINGS

In this regard, please refer to Annexure D4 of this manual.

- TRAVELLING PROCEDURES AND COSTS

The Consultant is referred to Section C of the Letter of Appointment.

- SUBMISSION OF ACCOUNTS

  - Form of Submission

All accounts must be submitted on the forms available from the Departmental website http://www.publicworks.gov.za.  Where relevant, these must be accompanied by invoices.  Please note that only the appropriate forms must be completed.

The Consultant must ensure that the fee account used is in accordance with the Consultant's Letter of Appointment.

  - Claims for Subsistence and Travelling

Such claims must be submitted as soon as possible after the journey has been made and in no circumstances later than three (3) months after the date thereof.

  - Claims for Other Disbursements

Such claims must be submitted as soon as possible after the event or as soon as receipt of invoices, but not more frequently than monthly.

  - Fees on Contract Price Adjustments

Fees are to be determined on the final value of the works and if applicable, calculated according to the stipulations in the Consultant's Letter of Appointment.