# SECTION B:  INCEPTION

CONTENTS

Item	Page

B.1	PROCESS CHART	2

B.2	INTRODUCTION	3

B.3	SIGNED AGREEMENT	3

B.4	PROJECT BRIEFING MEETING (PROJECT INITIATION MEETING)	3

B.5	PROJECT INCEPTION REPORT	3

B.5.1	Contents of report	3

B.5.2	Checklist	6

B.5.3	Number of copies	6

B.5.4	Civil engineering project	6

B.5.5	SITE CLEARANCE.	7

B.6	PROGRESS REPORTS	7

ANNEXURES:  SECTION B	8

1.	ANNEXURE B1:  SITE SURVEY (see Town Planning site 
clearance report)	9

2.	ANNEXURE B2:  GEOTECHNICAL INVESTIGATION	11

3.	ANNEXURE B3:  SOILS INVESTIGATION	14

4.	ANNEXURE B4:  FLOOD LINE DETERMINATION	15

5.	ANNEXURE B5:  SITE CLEARANCE CERTIFICATE (EXAMPLE)	16

STAGE 1:  INCEPTION

PROCESS CHART

| No. | Task/Event/ Activity/Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
| 1 | Signed agreement: | 3.2.1 (6) | B.3 | Department/ Consultant | User Department/ Local Authority/ Region Office |
|  | Conclude the terms of agreement |  | A.6 and A.7 |  |  |
| 2. | Briefing meeting: Agreed scope of services and scope of work required | 3.2.1 (1-3), (5) | B.4 A.8 | Department/ Consultant | Client/User Department |
| 3. | Project Inception Report: | 3.2.1 (7-9), (10) | B.5 | Consultant | User Department/ Local Authority/ Region Office |
|  | - Report on project, site and functional requirements | 3.2.1 (7) |  | Consultant |  |
|  | - Schedule of required surveys, tests and investigations | 3.2.1 (4) |  | Consultant Department | Other Consultants |
|  | - Schedule of consents and approval |  |  | Consultant | Other Government Departments/ Local Authorities |

INTRODUCTION

The primary focus of this stage is to:

Establish client requirements and preferences (Project brief);

Assess user needs and options;

Hand over the departmental Site Clearance Certificate to the Consultant (Annexure B5)

Confirm the suitability of the site in all respects including Dolomite Status Certificate (PRM011Aciv);

Assess special actions that may be required to develop the brief on the site;

Prepare a project inception report dealing with the above.

SIGNED AGREEMENT

The letter of invitation to perform professional services (generally referred to as “the Consultant's Letter of Appointment”) together with the associated sections, forms a binding contract between the Department and the consulting engineering firm the moment the consultant accepts the invitation in writing to perform such professional services.

The Consultant and the Departmental Project Manager will initial each page at the bottom right corner as well as all applicable changes/amendments made to the original contract documentation.

Where the Department’s standard Letter of Appointment forms the basis of the commission, the consultant is required to execute the work in accordance with this manual and with such supplementary instructions as the Department may issue from time to time.  In cases where a special agreement is entered into, this will state any variations in procedure, which may be required.

PROJECT BRIEFING MEETING (PROJECT INITIATION MEETING)

After acceptance of the appointment, the consultant is required to arrange a consultation/briefing meeting with the Departmental Project Manager.

At this meeting, a clear project brief will be developed and the scope of services and scope of work required will be defined.  He must also clear all discrepancies between the brief and his appointment.  The Consultant is to submit to the Department, in writing, a list of Professional Engineer/s/Technologist/s who will be responsible for controlling the service and inform the Department immediately of any changes during the project period.

The Site Clearance Certificate from the Departmental Town Planning Directorate must be obtained from the Project Manager at this meeting.  See Annexure B5.

Minutes of this meeting must be kept and forwarded to the Departmental Project Manager.

PROJECT INCEPTION REPORT

  - Contents of report

In the Project Inception Report (PIR) particular attention is paid to the suitability of the site, bulk and existing services, the presence of servitudes/necessity of acquiring servitudes or extra land as well as problems that may arise from adjoining sites.

The Project Inception Report will consist of an executive summary, followed by the report, which will include the following sections at least:

| Contents of Project Inception Report (PIR) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. |  | Section | Description |  | Comments |  |
| 1. |  | Introduction | - Appointment |  | - Describe the work to be performed |  |
|  |  |  | - Project Name, WCS No. and Departmental file reference No. |  | - Use the project name as on the Consultant's Letter of Appointment |  |
|  |  |  | - Purpose of project |  | - General description of the project. |  |
|  |  |  | - Project location and available information |  | - Municipal area and nearest town – access to the site, etc. |  |
|  |  |  | - Scope of work - Project Execution/Implementation Plan (PEP/PIP) |  | - Discuss of the full extent of the project, i.e. limits of design, other designs affected, etc. |  |
|  |  |  | - Adequacy of budget allocation |  | - Discuss the financial requirements and spending program |  |
|  |  |  | - OHS Act and Construction Regulations requirements |  | - Outline how the relevant Construction Regulations will be met |  |
| 2. |  | Project site and functional requirements | Taking into account the site clearance certificate provided by the Departmental Town Planning Section: |  |  |  |
|  |  |  | - A discussion of the existing land uses and anticipated future land use |  | - Although the consulting engineer is not responsible for the preparation of the site clearance certificate he/she is required to assess the site to determine to what extent the site affects the provision of civil engineering services and/or to what extent the provision of the civil engineering services will affect the functionality of the site with special attention to dolomite. |  |
|  |  |  | - Comments on the suitability of the extent of the site for the development, e.g.: |  |  |  |
|  |  |  | - Effect of topography on development |  |  |  |
|  |  |  | - Areas for water and sewage treatment plants (if required) |  |  |  |
|  |  |  | - Area for retention ponds, attenuation dams for storm water (if required) |  |  |  |
|  |  |  | - Area for disposal of waste (if required) |  | - Discuss waste issues with local authorities |  |
|  |  |  | - Comments on source of bulk services |  |  |  |
| 3. |  | Impact on environment and water related matters | - A summary of the environmental scan/ Environmental Impact Assessment (EIA) done |  |  | - See Section F.12 |
| 4. |  | Geotechnical/ Geological Discussion | A discussion of geotechnical/geological factors influencing the project with special attention to: |  |  | Annexure B2 and B3 Manuals/technical notes: |
|  |  |  | - Dolomite areas |  |  | - PW344 – Appropriate Development of Infrastructure on Dolomite |
|  |  |  | - Problematic soils areas |  |  | - PW2006/1 – Identification of Problematic Soils in Southern Africa. The compliance certificate for dolomite areas must be bound into this report |
|  |  |  | Highlight the possible impact on the provision of civil engineering services |  |  |  |
| No. |  | Section | Description | Comments |  |  |
| 5. | Hydrological discussion |  | A discussion of the hydrological aspects which may influence the project with special attention to: |  |  |  |
|  |  |  | - The location of the relevant - 1 in 5/10/50/100-year flood line | - Establish all relevant flood lines |  |  |
|  |  |  | - Disposal of storm water from the site | - Establish the capacity of the existing storm water system to ensure proper outflow |  |  |
|  |  |  | - Dealing with external storm water flowing onto the site |  |  |  |
|  |  |  | - Underground water sources (boreholes) | - Quantity and quality available |  |  |
| 6. | Traffic Impact Studies |  | - Discussion of the effect of traffic on the proposals | - If necessary, link to local authority studies |  |  |
| 7. | Other possible aspects that may arise as a result of or impact on the project |  | A discussion of possible impact of: | - Where applicable, the onus is on the consulting engineer to identify what servitudes and/or way-leaves are required to provide civil engineering services to the site |  |  |
|  |  |  | - Location of and possible relocating of existing services |  |  |  |
|  |  |  | - Affected/required way-leaves/servitudes |  |  |  |
|  |  |  | - Properties affected |  |  |  |
|  |  |  | - Topography |  |  |  |
|  |  |  | - Climate | - SA Weather Bureau |  |  |
| 8. | Liaison with parties concerned |  | Report on the outcome of discussions with: |  |  |  |
|  |  |  | - The relevant authorities (Municipal) regarding: | - These discussions must be confirmed in writing to ensure that the additional capacity needed is set aside for this project - Water, sewerage and storm water connection points. |  |  |
|  |  |  | - Service connections |  |  |  |
|  |  |  | - Effluent/storm water disposal |  |  |  |
|  |  |  | - Regulatory or statutory requirements |  |  |  |
|  |  |  | - The public and stakeholder groups |  |  |  |
| 9. | Schedule of required surveys tests and investigations |  | Recommendations regarding the requirements of the services of a specialist consultant for inter alia: | - Also refer to: Section A.15 and Annexure B1, B2 and B3 |  |  |
|  |  |  | - Geotechnical investigations | - With approval of the involvement of a specialist for any of the above by the Departmental Project Manager, three (3) quotations for these services must be obtained and submitted to him/her for approval |  |  |
|  |  |  | - Traffic impact studies |  |  |  |
|  |  |  | - Site surveys |  |  |  |
|  |  |  | - Hydrological studies, e.g. flood line determinations |  |  |  |
|  |  |  | - Water pressure recordings at municipal service connection points, etc |  |  |  |
|  |  |  | - Location of existing services |  |  |  |

| No. | Section | Description | Comments |
| --- | --- | --- | --- |
| 10 | Socio Economic Aspects | - Employment status - Skills Capacity - Training and transfer of skills | Address unemployment and poverty in South Africa, provides relief to the poor and unemployed and support training initiatives Address the scarce and critical skills needed and transferring of skills, |
| 11. | List of drawings | Drawings to form part of the report include: | Where available and applicable: |
|  |  | Location of: |  |
|  |  | - Flood line | - The consultant will conduct a search for, obtain, investigate and collate available data, drawings and plans impacting on the works - Actual drawings can be bound in separate volume |
|  |  | - Servitudes and way leaves |  |
|  |  | - Possible local authority connection points |  |
|  |  | - Water source and sewerage and storm water discharge points (if not from local authority) |  |
|  |  | - Vehicular access |  |
|  |  | Possible locations for: |  |
|  |  | - Water and sewerage treatment works | - Take due cognizance of dolomite |
|  |  | Attenuation retention dams for storm water |  |
|  |  | - Refuse disposal |  |
|  |  | Areas of site which are not suitable for development |  |
| 12 | Project Execution/ Implementation Plan | Revise all key components of the PEP: - Progress - Cash flow - Safety - Socio economic aspects etc. | The PEP/PIP must be updated continuously in order to be able to address all possible problems up front |

  - Checklist

The consultant will draft a checklist of the abovementioned items and indicate on the list that the items have been addressed. The checklist must be attached to the Project Inception Report which will be returned to the consultant should such a checklist not be included.

  - Number of copies

Three (3) copies of the Project Inception Report are required.

  - Civil Engineering Project

In the case of a civil engineering project on an existing site, e.g. water and sewage treatment works, upgrading of water and storm water reticulation and sewers, rehabilitation of roads and streets, etc., unless otherwise instructed, the Project Inception Report will form part of the Concept and Viability Report (Preliminary Design Report)  as described under Section C.

All three (3) reports or any two (2) of the reports may be combined.  The Departmental Project Manager will make this decision during the development of the “agreed services and scope of work”.

In the case of a combined report, the checklist will include all the aspects detailed underthe various reports.

  - SITE CLEARANCE.

The site assessment report from the Engineer must consider all ecological, social and economic aspects and must contain a detailed site description, the site history, the land-use type or restriction and any potential effects of contaminants on human health, the environment, or any other structures and property.

A site assessment must be undertaken by an independent and suitably qualified person, who must conduct a public participation process including at least one public meeting and an advertisement in local media.

All supporting documents, including the site assessment report, the notice and details of the public participation process and the minutes and attendance registers of such meetings must be submitted to the Minister or member of executive council (MEC) within fourteen (14) days of receiving notification to conduct a site assessment.

## PROGRESS REPORTS

Monthly progress reports (PRM014/6civ) are to be submitted in duplicate to the Departmental Project Manager not later than the seventh (7th) day of each month.

ANNEXURES:  SECTION B

CONTENTS

Item	Page

ANNEXURES:  SECTION B	8

1	ANNEXURE B1:  SITE SURVEY (see Town Planning site clearance report)	9

2	ANNEXURE B2:  GEOTECHNICAL INVESTIGATION	11

3	ANNEXURE B3:  SOILS INVESTIGATION	14

4	ANNEXURE B4:  FLOOD LINE DETERMINATION	15

5	ANNEXURE B5:  SITE CLEARANCE CERTIFICATE (EXAMPLE)	16

# ANNEXURE B1:  SITE SURVEY (see Town Planning site clearance report)

(The civil engineer must take cognizance of Section A, paragraph 15 regarding the appointment of surveyors.)

The two (2) primary objectives of the site survey are to provide:

A comprehensive plan of the site, showing all the necessary detail and data required for the design and accurate placing of the proposed structure/project;

Permanently marked and accurately fixed (in plan and level) survey stations to be used for any future setting out, control of construction and subsequent monitoring.

Communicate with the local community to address ways of alleviation of unemployment and poverty through job creation as well as the transferring of scarce and critical skills needed to meet the AsgiSA objectives with this project and:

- Location of the works

- Benefits of this project to the community

- Any objections regarding the project

The following detail has to be surveyed:  See also the Site Clearance Report from the Town Planning Section:

All natural and manmade features that may have an impact on the placing of the project.

Contours to 0,25m vertical intervals on a scale of 1:500 and to 0,50m on a scale of 1:1,000 with supplementary spot heights wherever the contours are unable to portray ground shapes faithfully.  Frequent spot heights will be given on features such as roads, railways, bridges, etc. where elevations may be necessary for engineering design.  Tachometric spot heights will be taken on all changes of slope, on top of ridges and in the bottom of valleys.

Positions of survey stations and details of survey beacons used for the survey.

Rivers, streams, springs, canals, dams, pans, marshes and areas subject to tidal flooding together with names and direction of flow, as appropriate.

Highest known flood levels of main streams, as close as can be determined from local evidence or information.  The source of such information and the specific point and date concerned must be indicated on the plan.

High tide marks as well as high water marks of rivers, streams and dams.

A description of the bed of stream, e.g. sandy, boulders, solid rock, silted, etc.

Forest, bush, shrub, plantations, orchards, avenues, hedges, individual trees which are landmarks, or the preservation of which may be demanded for scenic purposes, etc.

Cultivated lands (differentiating between dry and irrigated), rocky outcrops and hard or continuous rock, cliffs, sand dunes, etc.

Eroded areas and gullies.

Above ground and/or exposed water mains, sewers, storm water pipes, gas, petroleum and other services.

Power and telephone lines, showing individual poles or pylons in their surveyed positions.

Underground pipe lines, cables and other buried services – of which the positions will be determined from local authorities and surface indications, e.g. manholes, cable markers, etc., if such services will be affected by the planned construction.

Other underground services, e.g. signal cables, telephone cables, sewers, storm water pipes, etc.

Manholes.

Spot heights.

Road levels.

Cuttings and banks (road and rail).

Fences and property beacons.

Culvert dimension will be given.

Natural drainage and drainage improvements.

Structures affected by planning.

Existing access to adjoining properties.

Position of foundation test holes with reduced ground levels if available.

North point.

Any special features.

Road and footpaths, differentiating between blacktop and other surfaces as well as between national, provincial and other roads.

Structures, with details regarding the openings, sizes, structure number and type of construction where such a structure has a bearing on the site.

Drainage and irrigation furrows.

All individual buildings - differentiating between types of construction and stating the general use of the building/groups of buildings other than dwellings (e.g. store, school, etc.).

National monuments and buildings or structures of historical interest.  Describe briefly.

Gates and fences - differentiating between ordinary, stock proof, jackal proof, security fences, etc.

Stone, brick or any other type of walls.

Wells, boreholes, windmills.

Quarries, tunnels, mine workings, etc.

Graves and cemeteries.

All cadastral and servitude information will be shown in the surveyed area, together with the names of owners and municipal boundaries, if applicable.

Approval will be obtained from the Department in cases where it is difficult to supply cadastral information and where such data can be omitted without detrimental effect.

# ANNEXURE B2:  GEOTECHNICAL INVESTIGATION

A number of phases are normally included in the investigation.  The phases include a desk study, site reconnaissance, preliminary fieldwork, detailed investigation and verification of conditions during construction.  The process may be iterative in certain instances, with some phases being repeated prior to final site selection and commencement of detailed investigation.  See PW344 regarding dolomite.  The following serves as a guide to the information, which is obtained in the various phases:

Desk study

Topographical maps and aerial photographs should be consulted to gain information on the general topography and prominent features.

Geological maps should be consulted to gain information on the basic geology and possible dolomite areas.

Local authorities and other organizations should be approached to establish whether they know about and/or have records available on investigations conducted in the area.

The government mining engineer should be approached for information on mining operations where such operations are known to have been undertaken.

The study of overlapping aerial photographs through a stereoscope may be of value in identifying geological features such as faults, dykes, geological boundaries, dolomite, etc. as well as soil types and drainage patterns.  These features are often not apparent in the field.

Site reconnaissance

A site reconnaissance should be undertaken in order to gain geotechnical information from visible features, establish the suitability of various geophysical testing methods and investigate accessibility for drilling equipment.

Geophysical investigations

Wherever practicable, a geophysical investigation will be undertaken.  This investigation will comprise a seismic/resistivity/gravimetric/electromagnetic evaluation of the subsurface conditions of sufficient extent and depth in order to assist in the selection of the most economic detailed investigation as well as in the placing of foundations.

It should be noted that a proper geophysical investigation could substantially reduce the number of boreholes required at any site.

Drilling will only be required if the footprint of the structure is fixed.

Detailed investigations – Exploratory holes

The purpose of exploratory holes is to permit visual examination, testing of the in-situ material and for the recovery of samples.

Hand or machine (back actor) excavated test pits should generally be put down first, followed by large diameter auger holes and finally small diameter cored holes.  Planning should be flexible in such a way that when receiving new/additional information, the work can be varied as necessary.

Adequate direction and supervision of the work by competent staff with appropriate knowledge and experience as well as the authority to decide on variations to the investigation when required, is essential in order to obtain the greatest benefit from the investigation.

Logging and profiling

This work will be carried out in accordance with the following:

A guide to soil profiling for civil engineering purposes.

A guide to core logging for civil engineering purposes.

A guide to percussion borehole logging.

Produced by the South African Institute for Engineering and Environmental Geologists (SAIEG), South African Institute of Civil Engineers (SAICE) Geotechnical Division and Association of Engineering Geologists (AEG) (1993), edited by ABA Brink and RM Bruin.

Format of report

The geotechnical report will provide clear guidance to the engineer, enabling him to select the most appropriate solutions and foundation types.  The report should quantify the parameters required for the design of the proposed foundation and embankments.

The report, together with the inspection of the site, will provide the contractor with sufficient information to reasonably anticipate any problems that may occur during the execution of the works.  This will enable the contractor to tender a realistic price for the construction of the work and to select the most appropriate equipment and techniques therefore.

The report will be compiled under the following headings and will include - but not be limited to the following, as relevant:

Introduction

Terms of reference;

Description of the planning stage, and the purpose for which the investigation was conducted.

Description of the site(s)

Location of the site(s);

Accessibility of the site(s);

Traffic ability of the site for construction equipment;

Listing of sources where data is available or was obtained from;

Description of regional geology, vegetation, drainage and other general features of importance.

Investigations carried out

Name(s) of firm(s) responsible for the field work (consultant, contractor);

Name(s) of person(s) responsible for the interpretation of the geophysical work and for the profiling;

Dates when the work was conducted;

Description of the types of field work undertaken and equipment used.

Investigation results

Description of the soils encountered - identifying their stability or potential problems they may present, e.g. tendency to heave, collapse, settle, etc.;

Description of hard rock geology - identifying the type, quality, degree of weathering, fracturing, etc.;

Description when potential for boulders and/or other obstructions to deep seated foundations;

Description of the problems experienced or to be expected;

Description of ground water and expected variations;

Field and laboratory testing carried out i.e.:

Types of tests conducted on the respective materials;

Results obtained and their reliability.

Recommendations

Type of foundation best suited;

Expected bearing capacity and settlement for the respective materials on which founding could be considered;

Friction values and rock socket parameters for the design of piles;

Precautionary measures;

Construction sequences.

References

Listing of standards used for the classification of materials in respect of soil condition and rock hardness.

Annexure

Locality plan to appropriate scale;

Results of geophysical investigations;

Borehole, auger hole and test pit logs;

Photographs of borehole cores recovered;

Laboratory test results;

Drawings to scale showing the location - including levels of all positions investigated physical features of the site and setting out points.

# ANNEXURE B3:  SOILS INVESTIGATION

SOILS INVESTIGATION

In-situ testing of soils for the construction of embankments, roads, etc. as well as testing of soils for the construction of embankments, roads, etc. in borrow pits are described in “TRH 14:  Guidelines for road construction materials”.

Borrow pits and/or quarries should be identified and investigated during the project design stage.  The Mnerals Act No. 50 of 1990 controls the exploitation of materials.  It is a requirement that a Standard Environmental Management Programme be lodged with the relevant Regional Director of the Department of Mineral Resources.

# ANNEXURE B4:  FLOOD LINE DETERMINATION

Flood line determination

The determination of flood lines is usually based on the routing of storm water through the water course (drainage way).  The capacity of a natural channel (or any channel for that matter) is affected by the interaction of local features and the gradually varying flow profile.  Bakhmeteff (1932), Chow (1959), Henderson (1966) and French (1994) have addressed the routing problem.  Their classifications of the flow profiles are well documented.  Several computer programs are available to aid in the determination of water surface profiles.

# ANNEXURE B5:  SITE CLEARANCE CERTIFICATE (EXAMPLE)

Please provide the project manager responsible for the planning, tender and construction phase immediately with this certification and the attached information. This site clearance includes crucial information for planning, tender and construction that must be used, noted or adhered to by the project manager, the design team and contractor.

This site release and clearance certificate is limited to the specified intended development site only. Any works or activity proposed outside of the above specified works or site, be it capital works or repair and renovations will be subject to further clearance from the Directorate Town Planning Services. Any new land use on the site by the same or another client department will require a further site clearance.

Please take note that delays with the implementation of the proposed development will inevitably cause the availability, feasibility and legalization of the intended development on the site to be compromised or lapse.

………………………………………………..

DIRECTOR: TOWN PLANNING SERVICES

DATE OF ISSUE: ……………………….....