# SECTION C:	DESIGN: CONCEPT AND VIABILITY (PRELIMINARY DESIGN) AND DESIGN DEVELOPMENT (DETAIL DESIGN)

CONTENTS

Item	Page

C.1	STAGE 2:  CONCEPT AND VIABILITY(Preliminary design) STAGE 3:  DESIGN DEVELOPMENT (Detail Design)	2

C.1.1	PROCESS CHART	2

C.1.2	INTRODUCTION	2

C.1.3	REFERENCES	3

C.1.3.1	List of Documents	3

C.1.4	STAGE 2:  CONCEPT & VIABILITY (Preliminary Design)	4

C.1.4.1	Concept Design Report (CDR)	4

C.1.4.2	Sketch Plan Meeting (Checklist)	8

C.1.4.3	Checklist	8

C.1.4.4	Number of copies	8

C.1.4.5	Civil Engineering Project	9

C.1.4.6	Progress reports	9

C.1.4.7	Environmental Management Plan (EMP)	9

C.2	STAGE 3:  DESIGN DEVELOPMENT (DETAIL DESIGN)	9

C.2.1	Design development stage	9

C.2.1.1	Progress reports	10

C.2.1.2	Design calculations	10

ANNEXURES:  SECTION C	11

1.	ANNEXURE c1:  sKETCH plan check list	12

STAGE 2:  CONCEPT AND VIABILITY(Preliminary design)
STAGE 3:  DESIGN DEVELOPMENT (Detail Design)

PROCESS CHART

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees | Manual |  |  |
| 1. | Concept design | 3.2.2 (1-12) | C.1.4.1 | Consultant | Department, User Department, local and other authority and other consultants |
|  | Concept design report |  | Section F | Sketch Plan Committee |  |
|  | Schedule of further surveys etc. |  |  |  |  |
|  | Process design |  |  |  |  |
|  | Sketch plan approval |  |  |  |  |
|  | Refine concept design |  |  |  |  |
|  | Compliance with EPWP |  |  |  |  |
|  | Contract subdivision |  |  |  |  |
|  | Cost estimates |  |  |  |  |
| 2. | Design Development | 3.2.3 (1-9) | C.2 | Consultant | Department, User Department, local and other authority and other consultants |
|  | Design Drawings |  |  |  |  |
|  | Outline specifications |  |  |  |  |
|  | Local and other authority submission drawings and reports |  |  |  |  |
|  | Detailed estimate of construction costs |  |  |  |  |

INTRODUCTION

This section comprises Stage 2: Concept Design (Preliminary Design) and Stage 3: Design Development (Detail Design).

Stage 2 consists of the preparation and finalisation of the project concept in accordance with the brief, the investigations and the assessments carried out during the assessment stage, including:

A concept design report – viability, preliminary design, process design;

Preliminary programme and estimate.

In Stage 3, the concepts as developed and agreed with the Departmental Manager in the concept and viability stage (preliminary design) are further developed into detailed designs and specifications that are suitable for:

The preparation of the tender enquiry documents;

Obtaining the necessary approval from the relevant authorities;

Preparing detailed cost estimates.

REFERENCES

List of Documents

Below is a list of documents related to the work to be performed by the Consultant

| DOCUMENT NUMBER | DESCRIPTION | SHORT NAME |
| --- | --- | --- |
| DPW-04 (EC) | DPW-04-EC: Contract Data: JBCC 2000 Principal Building Agreement (Edition 4.1 Of March 2005 as amended by the Department) | DPW-04: Contract Data: JBCC |
| DPW-05 (EC) | DPW-05:(EC) Contract Data- (GCC (2004) 1st Edition: 2004 as amended by the Department) | DPW-05: Contract Data GCC 2004 |
| DPW-23 (EC) | Schedule of Imported Materials and Equipment | DPW-23(EC) |
| FP09E | Standard Specification for Security Equipment | FP09E: Security Equipment |
| No number | Guidelines for The Implementation Of Labour Intensive Infrastructure Projects Under The Expanded Public Works Programme (EPWP) | EPWP: Labour Intensive Infrastructure Projects |
| No number | Manual for Consulting Structural Engineers | Consulting Structural Engineers |
| PA-16.2 (EC) | Tender and Contract Conditions Pertaining to Contract Participation Goal (Participation Of Targeted Enterprises) | PA-16.2 (EC): Targeted Procurement |
| PW147 | Manual for Private Architects | PW147: Consulting Architects |
| PW1544 | HIV/AIDS Specification for Civil Contracts | PW1544: HIV/AIDS |
| PW2006/1 | Identification of Problematic Soils in Southern Africa: Technical Notes for Civil and Structural Engineers | PW2006/1: Problematic Soils |
| PW2011/1 | Small Waste Water Treatment Works | PW2011/1: SWWTW |
| PW326 | Manual for Electrical/Electronic and Mechanical Consulting Engineers | PW326: Electrical Electronic and Mechanical Consulting Engineers |
| PW331 | Standard Specification for Electrical Installations and Electrical Equipment Pertaining to mechanical Services | Electrical Installations Pertaining to mechanical Services |
| PW338 | Fire Security Standard Technical Specification for an Automatic Sprinkler Fire Extinguishing System | PW338: Automatic Sprinkler system |
| PW338 | Fire Security Standard Technical Specification for a Pump Installation for Automatic Sprinkler Fire Extinguishing System F.P.O/82/6E | PW338: Automatic Sprinkler Pump Installation |
| PW340 | Fire Security Schematic Diagram for a Fire Pump | PW340: Automatic Sprinkler Pump Diagram |
| PW342 | Installation | PW342 – Civil Services for Prisons |
| PW343 | Guidelines For The Design Of Civil Services For Prisons | PW343: Building Specifications |
| PW344 | Appropriate Development Of Infrastructure On Dolomite: Manual For Consultants | PW344: Dolomite manual |
| PW345 | Standard Specification For Domestic And Fire Water Storage and Fire Water Supply For Public Buildings | PW345: Domestic and Fire Water |
| PW346 | Example of Bills of Quantities & Specification for Comprehensive Services Incorporating Electrical Installations | PW346: BOQ & Specification: Comprehensive Services Electrical Installations |
| PW348 | Drainage Details | PW348: Drainage systems |
| PW349 | Guide For Architects Concerning Drainage Water Supply and Storm water Drainage | PW349: Water Drainage |
| PW371 | Specification of Materials and Methods to be used | PW371: Materials and Methods |
| PW377 | Hardware Sample List | PW377: Hardware Samples |
| QS 001 | Manual For Consultant Quantity Surveyors | QS 001: Manual: Consultant Quantity Surveyors |
| QS 002 | Procurement Documentation Guidelines for Building Contracts | QS 002: Procurement Document Guideline |
| QS 003 | Preliminaries for Inclusion in Bills Of Quantities and Lump Sum Documents Based On The JBCC Series 2000 Documentation | QS 003: Preliminaries for BOQ and Lump Sum - JBCC Series 2000 |

Most of these documents are posted on the DPW website:  	
http://www.publicworks.gov.za/consultantsguidelines.html

The other documents can be provided by the Departmental Project Manager.

STAGE 2:  CONCEPT & VIABILITY (Preliminary Design)

Concept Design Report (CDR)

The main aim of the Concept Design Report is to:

set out and to develop the design concepts and other proposals on which it is intended to base the design of the civil engineering services for the project, with compliance to the outcome of discussions with the various parties involved in the project;

identify any further testing surveys and/or testing investigations which may be necessary.

The Concept Design Report will consist of an Executive Summary, followed by the report, which will include but not limited to, at least the following sections:

| Concept Design Report (CDR) |  |  |  |
| --- | --- | --- | --- |
| No. | Section | Description | Comments |
| 1. | Introduction | Appointment Project Name, WCS No. and Departmental reference No. Purpose of project Project location and available information Scope of work | Describe the work to be performed Use the project name as on the Consultant's Letter of Appointment General description of the project Municipal area and nearest town - access to the site, etc. Discuss of the full extent of the project, i.e. limits of design, other designs affected, etc. |
| 2 | Description of project | A detail description of the project, including discussion and motivation of design approach outlined in the concept design report. |  |
| 3 | Design standards | Access to the site Road/streets cross sections (width, cross-fall, camber etc. Placing of services within the road reserve Obtain Dolomite Status Certificate (PRM011Aciv) Promotion of labour intensive construction and small contractor development in design | Red book – Guidelines for Human Settlement Planning and design – SAICE PW344 Dolomite Manual CIDB practice manuals: Implementing employment intensive road works Labour-based methods and technologies - SAICE Guidelines for the implementation of labour intensive projects under EPWP - PWD The consulting civil engineer will employ the services of a specialist to advise him on the provision of fire water services - Section A15. |
| 4. | Concept Design | A discussion of the design concepts envisaged for the civil engineering services for the project with special reference to: (Motivations for deviations from the norms) | Section F: Design Guide Annexure B2 and B3 |
|  |  | Design approaches to civil engineering services including the following: | Applicable guidelines/practice manuals/specifications, including: |
|  |  | Water Consumption, standards and peaks : | Local geotechnical/soil conditions: |
|  |  | Consumption figures and peak factors and periods calculation of pipe diameters Approach to distribution (fire and domestic water) Storage Water auditing requirements. Process approaches for water and/or sewage treatment works (if required) | Annexure B2 and B3 PW344 - Appropriate Development of Infrastructure on Dolomite PW2006/1 - Identification of Problematic Soils in Southern Africa Design guidelines/practice manuals: Section F PW2011/1 - Small water treatment works PW342 - Civil services for prisons Red book - Guidelines for Human Settlement Planning and design - SAICE |
|  |  | Water treatment approach |  |
|  |  | Sewerage: |  |
|  |  | Discharge figures and peak factors and periods Approach to treatment and discharge of effluent – blue drop status |  |
|  |  | Road/streets and storm water: Traffic load parameters and use factors Road/street surfacing and structure Road geometric design (width, cross-fall/camber, etc.) Method of managing and disposing of storm water |  |
|  | Concept design (continued) | Effect on the design concepts of: Topography including flood line Local geotechnical/soil conditions PW 2006/1 Local authority services (if required) Existing servitudes/way-leaves Existing services |  |
|  |  | Provision of water services for fire protection The guideline/practice manuals to be applied to the design | PW345 - Domestic and Fire water The consulting civil engineer will employ the services of a specialist to advise him on the provision of fire water services |
|  |  | Promotion of labour intensive construction and small contractor development in design | CIDB practice manuals: Implementing employment intensive road works Labour-based methods and technologies - SAICE |
|  |  |  | Guidelines for the implementation of labour intensive projects under EPWP-PWD |
|  |  |  | The consulting civil engineer will clearly state the design parameters he intends to apply in the development of his design and to what extent they address the aims and objectives of the EPWP |
| 5. | Schedule of further surveys tests and investigations | Recommendations regarding the requirements of the services of a specialist Consultant for inter alia: |  |
|  |  | Geotechnical investigations | PW2006/1 Problem soils |
|  |  | Dolomite | PW344 Dolomite Manual |
|  |  | Traffic impact studies Site surveys Hydrological studies, e.g. flood line determinations Water pressure recordings at municipal service connection points, etc. | If the involvement of a specialist for any of the above is approved by the Departmental Project Manager, three (3) quotations must be obtained for these services and submitted to him for approval |
| 6. | Impact on Environment | A Pre-Environmental Impact Assessment (EIA) Checklist must be submitted to the Department of Environmental Affairs (DEA) if doubt exists whether the EIA process has to be followed In the event that the EIA process has to be followed, a complete Scoping Report, based on a Plan of Study approved by DEA, is needed. An EIA is only needed if requested by DEA. | No project should be embarked upon beyond Stage 2, unless these aspects have been addressed Follow up on feedback from DEA. |
| 7. | Expropriation or Servitudes required | The Consultant will: Advise the Departmental Project Manager of any additional land that needs to be acquired or any servitudes or way-leaves that are required for the provision of the civil engineering services for the project Provide the Departmental Project Manager with the motivation therefore and the necessary details to enable the Department to make the required acquisitions and/or arrangements | No project should be embarked upon beyond Stage 2, unless these aspects have been addressed |
| 8. | Design proposals and comparison of alternatives | The design proposals as set out in the Concept Design Report will be further developed and alternative designs will be included in the Preliminary Design Report including a comparison of the different alternatives. Process designs regarding alternatives for water and sewage treatment works will clearly indicate, inter-alia: The power requirement for the operation of the process The susceptibility of the process to power outages The skills level required of the operator In the case of the security of water for fire fighting purposes the following will be expanded on: Method of ensuring that the required volume of water is available at the required pressure How power outages will be dealt with | These designs will be developed to an extent where the Departmental project manager can make an informative decision as to the design to be developed in Stage 3, taking into account the life cycle cost estimate for the various alternatives. |
| 9. | Compliance with EPWP Principles | The Consultant shall: Identify the activities suitable for the promotion of employment creation Provide estimates of the employment opportunities for the activities under the various alternative designs Report on the local skill base Report on training programs and initiatives | CIDB practice manuals Labour-based methods and technologies - SAICE Guidelines for the implementation of labour intensive projects under EPWP – PWD Training interventions The consulting civil engineer will clearly state the design parameters he has applied in the development of his design and to what extent they address the aims and objectives of the EPWP. |
| 10. | Contract subdivision | The consultant will make recommendations regarding: The number of civil contracts within the project, and The type of contracts e.g.: Separate contract Part of main contract Nominated sub-contract etc. | The current preference of the Department is comprehensive projects |
| 11. | Cost estimate | Life-cycle cost of the alternative designs/proposal will be included in the PDR. | Including for mechanical/electrical equipment, pumps, etc. Methods such as cost benefit ratio encouraged |
| 12. | List of drawings | Drawings to form part of the report include: | Drawings can be bound separately |
|  |  | - Water layout | Area for treatment works Pipe sizes, material, flows, velocities |
|  |  | - Sewerage layout | Pipe sizes, flows Velocities Longitudinal, section, cross section, geometric method of discharge of effluent |
|  |  | - Roads/streets and storm water - Roads and Parking area layout | Basic layout and geometric layout Long section and cross section, geometric layout Typical-cross-section indicating proposed surfacing and layers |
|  |  | - Storm water layout | Typical cross-section of road reserve indicating proposed positions of all services; method of dealing with and disposing of storm water. Pipe sizes, materials and design flow. Storm water management plan |
| 13. | Project Implementation Plan | Revise all key components of the PEP: Progress Cash flow Safety Socio economic aspects etc. | Progress on key components. The PEP must be updated continuously in order to be able to address all possible problems up front |

Sketch Plan Meeting (Checklist)

Annexure C1 show the requirements to attend to for the purposes of the Sketch plan meeting

Checklist

The consultant will draft a checklist of the abovementioned items, indicating that the items have been addressed and attach the checklist to the Concept Design Report and Preliminary Design Report.  These reports will be returned to the consultant should such a checklist not be included.

Number of copies

Four (4) copies of the Concept Design Report and Preliminary Design Report are required.  Form PRM016/7civ will be forwarded with the Preliminary Design Report and distributed by the Project Manager as follows:

Director:  Civil and Structural Engineering:  		Two (2) copies

Client:  		One (1) copy

Project Manager:  		One (1) copy

Three (3) copies of the final drawings to:

Archive:  		One (1) copy

Client:  		One (1) copy

Project Manager:  		One (1) copy.

Civil Engineering Project

In the case of a civil engineering project on an existing site, e.g. water and sewage treatment works, upgrading of water and storm water reticulation and sewers, rehabilitation of roads and streets, etc., the Concept Design Report and Preliminary Design Report will be combined in a single report, unless instructed otherwise.

Taking into account the comment in Section B.5.4, it is therefore possible that all three (3) reports (Project Inception Report, Concept Design Report and Preliminary Report) or any two (2) of the reports may be combined.

This decision will be made by the Departmental Project Manager during the development of the “agreed services and scope of work” – Section B.3.

In the case of a combined report, the checklist will include all the aspects detailed under the various reports.

Progress reports

Monthly progress reports (PRM014/6civ) are to be submitted in duplicate to the Departmental Project Manager, not later than the seventh (7th) day of each month.

Environmental Management Plan (EMP)

No project should be embarked upon beyond this stage, unless the Record of Decision emanating out of the above, has been filed with the consultant.  If the civil engineering work is a sub-component of a larger project, the consultant will insist to be presented with proof that a Record of Decision is on file and be ensured of how it influences his design.  The relevant stipulations in the Record of Decision must be incorporated into the contract specifications.

STAGE 3:  DESIGN DEVELOPMENT (DETAIL DESIGN)

The consultant may not proceed with Stage 3 without written approval of the Departmental Project Manager, after consultation with the Department’s Directorate:  Civil Engineering.

Design development stage

In this stage, the consultant will:

Develop the approved concept developed in Stage 2 and approved by the Departmental Programme Manager to finalise the design;

Prepare outline specifications;

Prepare drawings and reports for local and other authority’s and get their approval, i.e. fire fighting;

Prepare an estimate of construction costs;

Prepare drawings required for tender purposes.

This will involve:

| Design development stage |  |  |  |
| --- | --- | --- | --- |
| No. | Description | Activities | Comments |
| 1. | Development of concept of approved preliminary design | Develop the preliminary design incorporating the comments of the various parties involved in the project, as approved by the Departmental Project Manager for the civil work. Prepare development design drawings including draft technical details and specifications for each of the civil engineering contracts (if more than one). Review and evaluate design and outline specifications in collaboration with the Departmental Project Manager and exercise cost control. | Ensure comments from the Sketch Plan Committee are incorporated in the design. |
| 2. | Local authority drawings | Submit the necessary design documentation to local and other authorities as required for acceptance – responsibility still lies with the Engineer. | New structures, water treatment plants, roads, etc. |
| 3. | Final design and specifications | Prepare final design and outline specifications for each of the civil engineering contracts (if more than one). | No deviation may be made from the design as discussed and agreed with the Departmental Project Manager without his consent. |
| 4. | Estimate of construction costs | Estimated contract value for each of the civil engineering contracts. |  |
| 5. | Schedule of drawings | Drawings required for tendering on the specific contract (including locality plan). | Actual drawings can be bounded separately. |

Progress reports

Monthly progress reports (PRM014/6civ) are to be submitted in duplicate to the Departmental Project Manager, not later than the 7th day of each month.

Design calculations

The consultant will exercise all reasonable skill, care and diligence in the execution of his work.  He will be responsible for breach of professional duty by reason of any error, omission or neglect by him regarding the work performed by him or done by sub-designers and/or additional service providers while under his auspices.

Design calculations must be systematically done and kept.  They will be kept and safeguarded for at least ten (10) years by the Consultant.

The Department reserves the right to request all calculations as well as to have any plans and calculations submitted by the consultant checked and inspected - with the knowledge of the consultant - by another consulting firm or any other person or firm.

ANNEXURES:  SECTION C

CONTENTS

Item	Page

ANNEXURES:  SECTION C	11

1.	ANNEXURE c1:  sKETCH plan check list	12

ANNEXURE c1:  sKETCH plan check list

PRM016/7civ/1

## ANNEXURE C1:  SKETCH PLAN CHECK LIST (CONCEPT AND VIABILITY STAGE) - (CIVIL ENGINEERING) - See/complete original form in section G

- PRM016/7civ:  SKETCH PLAN COMMITTEE MANUAL

SKETCH PLAN COMMITTEE MANUAL 2008 (Vers 7 Sep 09)

See part 6.4.3 page 33 to 40 for Civil Engineering:

6.4.3.1. Cover Page for Distribution to DPW Civil Engineer PRM 16/07

This form must be completed and signed by the Consultant Civil Engineer.  Attach form to the outside of the set of documentation for distribution purposes.

| WCS No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REFERENCE No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONSULTANT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tel: |  |  |  |  |  |  |  |  |  |  | Fax: |  |  |  |  |  |
| ITEM DESCRIPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO. |  |
| - The Concept and Viability has been completed in terms of conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Concept and Viability report has been attached, see attached guideline and also refer to the engineer’s manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The design has been coordinated with architect. Note: see engineer’s manual for preliminary design documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The departmental engineer has been consulted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The departmental engineer’s comments has been incorporated into the design, if not, state reasons below: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Dolomite Status Certificate is attached. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  |  |  |  |  |  |  | SIGNATURE |  |  |  |  |  |  |  |  |
| FIRM |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |
| For completion by the Principal Agent/Consultant/Architect /Engineer : |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES |  | NO |  |
| One set of architectural/Engineering drawings has been attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  |  |  |  |  | SIGNATURE |  |  |  |  |  |  |  |  |  |  |
| DESIGNATION |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |
| For completion by the: DPW Civil Engineer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| For Sketch Plan purposes the recommendation to the SPC Chairperson is : |  |  |  |  |  |  |  |  |  |  | ACCEPT/NOT ACCEPT the Sketch Plan design submitted. |  |  |  |  |  |  |  |
| NAME |  |  |  |  |  |  |  |  |  |  | SIGNATURE |  |  |  |  |  |  |  |
| DESIGNATION |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |
| COPY ON SKETCH PLAN FILE? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

General Comment

The Department of Public Works has a large and diverse property portfolio.  Various Departmental Guidelines have been prepared to assist Professional Consultants in the design and documentation of NDPW Projects.  They provide direction and guidance on DPW’s requirements and enable Consultants to efficiently translate them into acceptable design solutions.

The Guidelines are not intended to replace the level of initiative, competence and care as expected of consultants in the performance of their duties.  Consultants are encouraged to carefully consider the merits of the Design Guidelines in the context of the needs of individual projects.  If a Consultant considers a guideline not to be appropriate and that a more suitable solution is available, proposals to this effect should be raised for consideration by the Department.

In the absence of express written approval for a deviation from Departmental guidelines, the Department will assume that the requirements contained in the various Design Guidelines have been fully addressed and incorporated in the proposed Design Solution and Specifications.

Design calculations and investigations should be performed through all stages in an orderly, logical way.  They should not only allow the design engineer to arrive at conclusions sufficient to lead to the preparation of detailed drawings, but their final form should reflect neat and systematic thought processes.  At any time in the future someone wanting to check back on the original design should be able to find out what the design engineer was trying to achieve and what design standards he used.

The engineer must take particular care in presenting the work connected with his design to ensure that:

The design processes themselves are orderly, legible and logical so that the engineer charged with the checking should be able to follow them with ease;

The technical and academic quality is acceptable; and

Adequate draughting standards are complied with.

The Preliminary Design Report (PDR) gives the designer the opportunity to set out the design considerations and obtain approval for proposed deviations from Departmental standards.  Where various options exist to arrive at a suitable design solution, the Department can select the preferred configuration based on information presented in the PDR.  To enable the Departmental Civil Engineer to endorse the civil design at Sketch Plan Stage, the designer must have submitted a PDR documenting all facets of the design, to the Department.

The following section proposes a checklist that should be completed by the Project Manager and Professional Consultant to ensure that the Departmental Civil Engineer has sufficient project detail to enable him to check the design proposal:

Proposed Sketch Plan Checklist for the Civil Engineering portion of the design

(Note: 	Although not specifically related to the Civil Engineering, the EIA and Heritage requirements of a project as well as any interface with Service Providers and Municipalities must be addressed in detail at sketch plan stage as they could have a substantial impact on the cost of the works.)

The checklist is generic and some of the listed items/activities may not be applicable to the particular project under review.  Provision must be made for a response of Not Applicable and perhaps In Process.  Generally most of the aspects should be addressed in the PDR but it can be possible that some of the processes haven’t been taken to conclusion (EIA for example) before submitting the PDR.  An objective decision on allowable exclusions will have to be made by the Project Manager after consultation with the Departmental Civil Engineer so that the Sketch Plan approval is not delayed.

SKETCH PLAN (DESIGN DEVELOPMENT) STAGE - (CIVIL ENGINEERING)

The questions/statements below require a Yes /No /Not Applicable response:

| 1. General |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | The Project Manager briefed Departmental Civil Engineer on client requirements and facility configuration. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The Civil Consultant has discussed design options/details with the Departmental Civil Engineer. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Environmental Impact Assessment: |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  | i) | Application for exemption was made. |  |  |  |  |  |  |  |  |  |  |  |
|  | ii) | Scoping report was compiled and submitted. |  |  |  |  |  |  |  |  |  |  |  |
|  | iii) | Full EIA process is required by DEAT and has been initiated. |  |  |  |  |  |  |  |  |  |  |  |
|  | iv) | ROD was obtained. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Have the requirements of the local municipality been established and taken into consideration in the design proposal? |  |  |  |  |  |  |  |  |  |  |  |
|  |  | If a services report is required by the Municipality or Service Provider has it been compiled and submitted? |  |  |  |  |  |  |  |  |  |  |  |
| 2. Preliminary Design Report (PDR) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | A Preliminary Design Report (PDR) has been drafted in accordance with Clause B 1.4 of PW347 – Civil Engineering Manual, and has been forwarded to Departmental Civil Engineer. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The PDR includes the following: |  | YES |  |  |  | NO |  |  |  | N/A |  |
| a). General |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A Clear description of required facilities as defined by the Client Department. Definition includes function and purpose of facilities; the number and classes of occupants; periods of usage and usage patterns; all farming, abattoir or business activities listed separately. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation by the Architect or Principal Agent that the description of the facility in the Engineer’s PDR is accurate and complete. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Append letter of confirmation to the report. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A summary of the Site Clearance information from the Site Clearance Report-Town Planning; problems identified at site clearance stage. |  |  |  |  |  |  |  |  |  |  |  |
| a). General (Continue) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Locality of project including a large scale - provincial locality map and a small scale map showing locality in town. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Design criteria clearly referenced to Departmental or other guideline documentation. Deviations from standards clearly indicated and motivated. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Recommendations and motivation for further investigations, surveys and servitudes. |  |  |  |  |  |  |  |  |  |  |  |
| b). Water Supply |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | A preliminary assessment of water use as defined by the function or purpose of the facility. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Water demand per category calculated and presented in tabular form. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Tabled calculation of peak factors with reference to Departmental guidelines. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Local Fire Authority regulations and degree of assistance available from the Authority. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The facility classification in terms of fire risk. Tabled fire flow requirements with reference to Departmental or Fire Authority standard. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Layout drawing with position of municipal hydrants adjacent to site. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation in writing from municipality of sufficient capacity in the municipal water supply infrastructure. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of investigations (diurnal flow and pressure readings) confirming the capacity of the municipal infrastructure. (Alternative to the written confirmation from municipality above). |  |  |  |  |  |  |  |  |  |  |  |
|  |  | As-built data of Municipal water supply infrastructure. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of surveys, investigations, methodology and assumptions if as-built data is not available. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Verification of municipal water connection cost and the possibility of bulk water contribution cost. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A copy of the Service Level Agreement with the Service Provider is appended to this report. (Alternative to the verification of connection and bulk costs). |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Special requirements of the municipality and how these requirements have been incorporated in the design proposal. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Where borehole water is to be utilized, test results from yield and quality tests. Recommendations on usage and abstraction rates by Geo-hydrologist. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The conceptual design of river abstraction method. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A recommendation on licensing requirements to utilize borehole or river water. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposals on water treatment, including disinfection, of borehole and river water. Results of the water quality analysis. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Water Storage requirements and proposal. Specific requirements of the user-department or requirements for fire fighting. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation that elevated storage towers are listed in EIA. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposed layout of water reticulation and placing of services. Pipe networks, ring mains etc. shown on sketch drawings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Water supply design standards i.t.o materials, hydraulic specification, velocity, pressure limits and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Specifications of materials, valves, air valves, PRV’s, water meters etc. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Placement of water meters to monitor water usage. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | General arrangement and design basis for water supply pump stations, including operational control and standby capacity. |  |  |  |  |  |  |  |  |  |  |  |
| c). Storm Water |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Summary of statistical data of the nearest rainfall station. |  |  |  |  |  |  |  |  |  |  |
|  |  | The sub-catchment areas are shown on the layout plans. |  |  |  |  |  |  |  |  |  |  |
|  |  | Design criteria and calculation assumptions and methodology. |  |  |  |  |  |  |  |  |  |  |
|  |  | Design storm return period and tabulated runoff per sub-catchment. |  |  |  |  |  |  |  |  |  |  |
|  |  | A description of any specific design requirements in terms of storm water reuse or conduit size limitations. |  |  |  |  |  |  |  |  |  |  |
|  |  | Storm water design standards i.t.o materials, hydraulic specification, velocity, pressure limits and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |
|  |  | Flood line for the 1:100 year storm event shown on the layout plan. |  |  |  |  |  |  |  |  |  |  |
|  |  | Routing of storm water affecting cut and fill slopes on embankments or platforms. |  |  |  |  |  |  |  |  |  |  |
|  |  | Concept design of flood attenuating or control devices as well as a description of storm water management plan. |  |  |  |  |  |  |  |  |  |  |

| d). Sewerage |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | A preliminary assessment of sewer flow as defined by the function or purpose of the facility with tabulated results of calculations and design figures. |  |  |  |  |  |  |  |  |  |  |
|  |  | Table showing criteria and results of the peak factor calculations with reference to Departmental guidelines. |  |  |  |  |  |  |  |  |  |  |
|  |  | General arrangement and design basis for sewerage pump stations; including sump design, instrumentation and standby capacity. |  |  |  |  |  |  |  |  |  |  |
|  |  | Description of the type and capacity of the sewerage collection system. |  |  |  |  |  |  |  |  |  |  |
|  |  | Capacity assessment of municipal sewer or written confirmation of capacity by municipality. |  |  |  |  |  |  |  |  |  |  |
|  |  | Location and accurate level of municipal sewer indicated on the layout drawing. |  |  |  |  |  |  |  |  |  |  |
|  |  | Assessment of sewerage treatment options. |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome of Licensing and sewerage treatment discussions with DWAF. |  |  |  |  |  |  |  |  |  |  |
|  |  | Does the EIA scoping report include the establishment of an on-site sewerage treatment works? |  |  |  |  |  |  |  |  |  |  |
|  |  | If on-site treatment has been proposed with irrigation of the final effluent, is there sufficient land available within the site boundary for irrigation. |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of percolation tests if soak-aways are proposed. |  |  |  |  |  |  |  |  |  |  |
|  |  | Sewerage collection system design standards i.t.o materials, min slopes, hydraulic specification, velocity and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |
|  |  | Specifications of special materials, valves, pumps, macerators, water meters etc. |  |  |  |  |  |  |  |  |  |  |
|  |  | Sewerage connection cost and the possibility of bulk sewer contribution cost. |  |  |  |  |  |  |  |  |  |  |
| e). Roads and Parking |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | The information relevant to vehicular traffic to be accommodated on the site eg. Vehicle type loading, frequency and definition of functional areas. |  |  |  |  |  |  |  |  |  |  |
|  |  | Road classification for different functional users. |  |  |  |  |  |  |  |  |  |  |
|  |  | Local Authority or the road owner’s regulations applicable to access. |  |  |  |  |  |  |  |  |  |  |
|  |  | Bulk contribution cost to municipality for access roads. |  |  |  |  |  |  |  |  |  |  |
|  |  | Results or recommendation on traffic study. |  |  |  |  |  |  |  |  |  |  |
| e). Roads and Parking (Continue) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Applications lodged for way leaves. |  |  |  |  |  |  |  |  |  |  |
|  |  | Road and pavement design criteria. |  |  |  |  |  |  |  |  |  |  |
| f). Earthworks |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Final site layout obtained from Architect. |  |  |  |  |  |  |  |  |  |  |
|  |  | Platform elevations obtained from Architect. |  |  |  |  |  |  |  |  |  |  |
|  |  | Retaining wall requirements communicated with Structural Engineer. |  |  |  |  |  |  |  |  |  |  |
|  |  | Slope stability and method of stabilization detailed and motivated. |  |  |  |  |  |  |  |  |  |  |
|  |  | Preliminary cut and fill volumes calculated and balanced. |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposed design standards for earthworks. |  |  |  |  |  |  |  |  |  |  |
|  |  | Borrow pits and Spoil sites have been identified. |  |  |  |  |  |  |  |  |  |  |
|  |  | Borrow pits and Spoil sites were included in EIA scoping report. |  |  |  |  |  |  |  |  |  |  |
| g). Construction Specifications and Form of Contract |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Construction Standard Specifications e.g. SANS 1200; COLTO. |  |  |  |  |  |  |  |  |  |  |
|  |  | Form and Conditions of contract specified e.g. GCC 2004, JBCC. |  |  |  |  |  |  |  |  |  |  |
| h). Cost Estimate |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Cost estimate and comparison of the various design options. |  |  |  |  |  |  |  |  |  |  |
|  |  | Life cycle cost where needed to motivate between options and select final design configuration. |  |  |  |  |  |  |  |  |  |  |
| i). Appendices |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Confirmation by the Architect or Principal agent that the description in the Engineers PDR is accurate and complete. |  |  |  |  |  |  |  |  |  |  |
|  |  | Summary and Recommendations from Site Clearance Report. |  |  |  |  |  |  |  |  |  |  |
|  |  | EIA – Record Of Decision (ROD). |  |  |  |  |  |  |  |  |  |  |
| i). Appendices (Continue) |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Marked up architects drawings showing concept design and layout of roads and parking; bulk water supply and water reticulation; sewerage reticulation, sewer outfall, sewerage treatment, effluent or alternative sewerage disposal; storm water catchments, collection and conveyance systems. |  |  |  |  |  |  |  |  |  |  |
|  |  | General arrangement of pump stations. |  |  |  |  |  |  |  |  |  |  |
|  |  | Recommendations of Geotechnical Investigations. |  |  |  |  |  |  |  |  |  |  |
|  |  | Recommendations of Traffic Study. |  |  |  |  |  |  |  |  |  |  |
|  |  | Correspondence with Local Municipality including Service Level Agreement (SLA). |  |  |  |  |  |  |  |  |  |  |
|  |  | Correspondence/ ROD - Road Owner. |  |  |  |  |  |  |  |  |  |  |
|  |  | Way leave applications. |  |  |  |  |  |  |  |  |  |  |
|  |  | Photos of typical or specific site characteristics. Results of Water and Sewerage investigation. |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of Water and Sewerage investigation. |  |  |  |  |  |  |  |  |  |  |
|  |  | Explanatory drawings, typical details or typical road cross sections. |  |  |  |  |  |  |  |  |  |  |

j)	Dolomite Issues

- During the design or execution (Construction) stage of the project the Project Manager (PM), consultant team and contractor should be alert and pro-active in locating and/or detecting any trace or sign of the presence of dolomite.

- Should this be found, it must immediately be brought to the attention of the PM and the designated official responsible for dolomite matters at the Regional office/ Head office.

- As and where applicable, appropriate designs/specifications/details for dolomite conditions should conform to the Department’s manual:  “Appropriate development of infrastructure on dolomite”, Document PW 344.

- Should there be any uncertainty about the presence of dolomite and/or unscheduled ground movement event, then such enquiries should be referred to the Directorate: Civil & Structural Engineering at Head Office for further investigation and subsequent certification.