SECTION D:  DOCUMENTATION AND PROCUREMENT:  STAGE 4

CONTENTS

Item	Page

D.1	PROCESS CHART	2

D.2	INTRODUCTION	3

D.3	REFERENCES	3

D.4	SPECIFICATIONS	4

D.5	COORDINATION OF SERVICES AND DISCIPLINES	4

D.6	DETAIL DESIGN DRAWINGS	5

D.7	TENDER/BID DOCUMENTATION	5

D.7.1	Introduction	5

D.7.2	References for Tender/Bid Documentation	5

D.7.3	Building Contracts	5

D.7.4	Engineering Projects	6

D.7.5	Mechanical/Electrical Subcontracts	6

D.7.6	VAT and Contingencies	7

D.7.7	Penalties	7

D.7.8	Securities	7

D.7.9	Limit of Retention	7

D.8	TENDER/BID EVALUATION AND REPORT	8

D.8.1	Tender/Bid Recommendation	8

D.8.2	Contract Documentation	8

ANNEXURES : SECTION D	9

1.	ANNEXURE D1:  SEQUENCE OF PROCUREMENT DOCUMENTS	10

2.	ANNEXURE D2:  CONDITIONS OF CONTRACT	12

3.	ANNEXURE D3:  PROJECT SPECIFICATION CLAUSES	16

4.	ANNEXURE D4:  DRAWINGS	34

5.	ANNEXURE D5:  SITE CLEARANCE CERTIFICATE	39

6.	ANNEXURE D6:  FORM OF GUARANTEE	42

7.	ANNEXURE D7:  PRO FORMA RISK ASSESSMENT REPORT	44

STAGE 4:  DOCUMENTATION AND PROCUREMENT

PROCESS CHART

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
|  | STAGE 4: DOCUMENTATION AND PROCUREMENT |  |  |  |  |
| 1. | Project Specifications Detailed estimates, capital and life cycle costs, financial implications and programmes for implementation of the works | 3.2.4 (2), (3) | D.4 | Consultant | Client/User Department |
| 2. | Coordination of services and disciplines Design and consultants’ meetings | 3.2.4 (1) | D.5 | Consultants & Project Manager | Other Consultants / Client / Local Authority / Regional Office |
| 3. | Detail design drawings Sketch plan Committee approval Detailed cost estimates and adjusted designs | 3.2.4 | D.6 | Consultant | Project Manager / Other Consultants / Sketch Plan Committee |
| 4. | Tender documentation Procurement strategy Assembly of documentation for contractor procurement | 3.2.4 (5), (6) | D.7 | Consultant & Quantity Surveyor | Project Manager |
| 5. | Building contracts | 3.2.4 (6) | D.7.3 | Consultant & Quantity Surveyor | Project Manager |
| 6. | Civil Engineering contracts | 3.2.4 (3) | D.7.4 | Consultant | Project Manager |
| 7. | Mechanical/Electrical subcontract | 3.2.4 (3) | D.7.5 | Consultant & M/E Consultant | Project Manager |
| 8. | Contingencies, Penalties, Securities & Value-added-tax (VAT) | 3.2.4 (3) (5) | D.7.6 D.7.8 | Department, | Consultant, Contractor & SARS |
| 9. | Retention money | 3.2.4 (3) | D.7.9 | Department | Project Manager |
| 10. | Evaluation of Tender Information to the principal consultant and the other consultants as required | 3.2.4 (7), (9) | D.8 | Department & Contractor | Project Manager |
| 11. | Risk Analysis Risk assessment report to the Client | 3.2.4 (7), (8) | D.8 | Consultant | Contractor |

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
| 13. | Recommendation Advice to the client on any alternative designs and tenders Assessment of samples and products for compliance and design intent | 3.2.4 (9), (11), (12) | D.8.1 | Project Manager | Consultant |
| 14. | Priced documentation Assist with the preparation of contract documentation for signature | 3.2.4 (10) | D.8.2 | Project Manager | Consultant |

INTRODUCTION

This stage follows the Design Stage (Stage 3) and covers the preparation of procurement and construction documentation, confirmation and implementation of the procurement strategies and procedures for effective and timeous procurement of necessary resources for execution of the project.

Tender documents including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared by the Consultant, and submitted to the Project Manager.  After approval, the Department will arrange for the invitation of tenders and follow the tender procedures of the Department to accept a tender.  The Consultant may be requested to prepare a risk analysis of one or more of the tenderers before a tender is accepted.

The Standard for Uniformity in Construction Procurement published in terms of the Construction Industry Development Board (CIDB) Act, 2000 (Act No. 38 of 2000), the Standardized Construction Procurement Documents for Engineering and Construction Works as issued by the CIDB and any other relevant documentation pertaining thereto must be studied and all principles in this regard must be applied to all procurement documentation, practices and procedures.

REFERENCES

National Department of Public Works scope of Engineering services and tariff fees for persons registered in terms of the Engineering profession Act, 2000, (Act No. 46 of 2000).

Manual for Project Managers.

General Conditions of Contract 2004 (GCC 2004) as amended by the Department (DPW-05: EC CONTRACT DATA (GCC (2004) 1st EDITION (2004)) “DPW-05 EC (GCC 2004)” or in case of comprehensive projects:

DPW-04: EC Contract Data (JBCC 2000);

Preliminaries for Inclusion in Bills of Quantities and Lump Sum Documents Based on the JBCC Series 2000 Documentation (QS 003);

Specification of Materials and Methods to be Used” (PW371) and/or SABS 1200 (SANS 1200);

SABS 0120 – Part 2 – Section 0, Clauses 4 & 5) (SANS 10120) and the Preamble to the Schedule of Quantities (QS 003);

SABS 1200 LC (SANS 1200 LC) and the Departmental specifications for electrical work;

Procurement of Consulting Engineering Services in the Construction Industry: A Guide for Consulting Engineering Firms.  CESA – Consulting Engineers South Africa (PITT Manual August 2009).

The Departmental website can be visited for all Departmental documentation at:	
http://www.publicworks.gov.za/consultantsguidelines.html

SPECIFICATIONS

The clauses forming Annexure D3 must be considered in compiling the Project Specification (SABS 0120 – Part 2 – Section 0, Clauses 4 & 5) (SANS 10120) and the Preliminaries for Inclusion in Bills of Quantities and Lump Sum Documents Based on the JBCC Series 2000 Documentation (QS 003).

Attention is specifically drawn to the requirements of SABS 1200 LC (SANS 1200 LC) and the Departmental specifications for electrical work with respect to ducting for electrical services.

The Consultant will exercise all reasonable skill, care and diligence in the execution of his work.  He will be responsible for breach of professional duty by reason of any error, omission or neglect by him in connection with the work performed by him or done under its auspices by sub-designers and/or additional service providers.

COORDINATION OF SERVICES AND DISCIPLINES

To control strict adherence to the time schedule required for compliance with the documentation programme and laid down in terms of the Consultant's Letter of Appointment or as provided at the briefing the Consultant is required throughout the design and documentation stages to render to the Department progress reports the Department up to the last working day of each month on the form (PRM014/6civ).

Special attention must be drawn to any delays or changes in the estimated cost of the service and the cause thereof in the completion of the form.

If the service of a Specialist Consultant is required, three (3) quotations for these services must be obtained and submitted to the Departmental Project Manager for approval.  This is applicable for:

Geotechnical investigations

Traffic impact studies

Site surveys

Hydrological studies, etc.

Flood line determination.

The Consultant is responsible for the coordination, detailing and installation with respect to subsurface service ducting for other disciplines/consultants outside buildings.

DETAIL DESIGN DRAWINGS

When instructed to do so, the Consultant must print the following number of tender documents:

| No | Print | Number |
| --- | --- | --- |
| 1. | Contract documents | 25 copies or as otherwise directed |
| 2. | Reduced drawings (A2) | 25 sets or as otherwise directed |

The above must be sent to the office of the Departmental Project Manager referred to in Annexure A of the Consultant's Letter of Appointment, for tender purposes.

The Consultant may retain three (3) contract documents and one set of drawings for contract administration purposes.

TENDER/BID DOCUMENTATION

Introduction

The Departmental Project Manager is responsible for the completion of all procurement forms, as well as for assembling the procurement documents, but the Consultant ascertain himself that the document is assembled correctly, and he has to verify on the form that all the procurement documents are the latest revisions.

The three volume approach has been adopted by the Department for Building Contracts (JBCC) and the single volume approach for Engineering Contracts (GCC).

The Department’s latest policy regarding targeted procurement and the relevant forms shall be incorporated into the document.

References for Tender/Bid Documentation

Documentation shall be based on the General Conditions of Contract 2004 issued by the SAICE, SABS 1200 (SANS 1200), the Departmental Contract Data (DPW-04  and -05) (Annexure D2 – latest revision), preliminaries for inclusion in bills of quantities and lump sum documents based on the JBCC series 2000 documentation (QS 003) and the documents contained in Annexure D1.

Except for the “list of specifications” in Annexure D2.4, the documents contained in Annexure D1 and the contract data (DPW-04 and DPW-05) may in no circumstances be amended.

Building Contracts

Building Contract procurement documents shall be formatted and compiled under the standard headings and sequencing of documents for the three volume approach, as indicated in the QS 002 document.

For more details please see the Department’s Procurement Documentation Guidelines for Building Contracts (QS 002) regarding all the documentation that comprise the tender, on the DPW website.

Tender documents for building contracts including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared in draft format by the Civil Engineer, and submitted to the Departmental Project Manager in draft format.

After approval of the document, the Department will arrange for the invitation of tenders, evaluate and accept a tender through the Department’s tender procedures.

The Consultant may be requested to do a risk analysis on one or more of the tenders for evaluation purposes.

In case of civil work included in a building project the JBCC series 2000 will prevail as adapted by the Department.  Civil engineering services are included in the building contract.  Contract drawings and technical specifications are prepared by the civil engineering consultant and submitted to the principal agent/project leader, who after approval will arrange to have these included in the main building documentation after approval.  Although the defects liability period (maintenance period) on a building contract is normally three (3) months, the civil part will be subject to a defects liability period of twelve (12) months.

Documentation prepared by the Quantity Surveyor will be based on those documents listed in QS 002 except for SABS 1200 (SANS 1200).  The civil engineering consultant will be required to prepare tender drawings and a project specification relating to the civil works only, based on the Department’s “Specification of Materials and Methods to be used” (PW371).

Engineering Projects

The relevant contract procurement documents shall be formatted and compiled under the standard headings and sequencing of documents for the single volume approach.

In case of engineering projects the civil engineering contract (GCC 2004) shall prevail except indicated otherwise by the Department:  tender documents including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared by the consultant, and submitted to the Departmental Project Manager in draft form.  After approval, the Department will arrange for the invitation of tenders, submit these to the Consultant for a risk analysis report, and accept a tender through the Department’s tender procedures.

Mechanical/Electrical Subcontracts

In certain circumstances, for example pump station installations, it may be expedient to have a separate mechanical/electrical subcontract.  Tender documents including drawings, specifications and schedules of quantities as well as an estimate of the cost are prepared in draft form by the mechanical/electrical engineering Consultant, and submitted to the principal agent in draft form.  The principal agent, assisted by the Consultant will thereafter be responsible for the compilation of the tender document.  After approval, the Department will arrange for the invitation of tenders, submit these to the Consultant for a risk analysis report, and accept a tender through the Department’s tender procedures.

The columns for the schedule of quantities and headings shall be in the following order (amendment to SANS 0120 Part 4):

| 1. | Payment Refers to |
| --- | --- |
|  | Reference number or the relevant specification. |
| 2. | Item No. |
|  | Unique payment item number and sub-number and sub-sub-number (alphabetic and Roman numbering should be avoided). |
| 3. | Description |
|  | Sub-sub-number and description of item. |
| 4. | Unit |
|  | Unit of measurement of item. |
| 5. | Quantity |
|  | Quantum of unit of item. |
| 6. | Rate |
|  | Rate to be tendered of item. |
| 7. | Amount |
|  | Product of quantity and rate of item. |

VAT and Contingencies

Contractors must be registered in terms of the Value Added Tax Act, (Act No. 89 of 1991).  Tendered rates and lump sums should make provision for the payment and recovery of any taxes, obligatory levies on all items to which they apply, but exclude Value Added Tax (VAT).  In order to determine the tender sum, VAT will be added to the total sum of the schedule of quantities.  Should the rate at which VAT is charged be increased or decreased by legislation in relation to the rate applicable at the tender closing date, the difference in payment of VAT shall be borne by the Employer or shall be to his benefit.

No provision must be made for a contingency allowance in the contract documents.

Penalties

The penalty for late completion of the contract shall be calculated as described in the “Manual for Consultant Quantity Surveyors on the Preparation of Bills of Quantities 
(QS 001, latest revision)” available from the Departmental website.

In the case of nominated subcontracts, the penalty that applies to the main contract will apply to the subcontract.

Securities

The following percentages of the estimate will be required for security:

| No | Estimate |  |  | Percentage |
| --- | --- | --- | --- | --- |
| 1. | R0.00 | to | R100,00 | 0.0% |
| 2. | R100,001 | to | R1,000,000 | 2.5% |
| 3. | R1,000,001 | to | R3,000,000 | 5.0% |
| 4. | R3,000,001 | to | R5,000,000 | 5.0% to 10.0% according to risk |
| 5. | More than R5,000,000 |  |  | 10.0% |

Limit of Retention

The limit of retention is usually taken as ten (10%) percent of tender price, but may, on large contracts be reduced in consultation with the Departmental Project Manager.

Retention can be increased in lieu of security for contracts with an estimate amount of below R2 million, as follows:

| No | Estimate |  |  | Percentage |
| --- | --- | --- | --- | --- |
| 1. | R100,000 | to | R1,000,000 | 2.5% |
| 2. | R1,000,001 | to | R2,000,000 | 5.0% |

Calling for and the acceptance of tenders is a function of the Department.  To enable the Department to advertise the contract for tender, a Pre-Tender Estimate and Site Clearance (Annexure D5) must be submitted with the printed tender documents.

For tender purposes, the documents to be included in the tender document must be sent to the office of the Departmental Project Manager referred to in Annexure A of the Consultant's Letter of Appointment.  The Consultant may retain three (3) contract documents and one (1) set of drawings for contract administration purposes.

TENDER/BID EVALUATION AND REPORT

The Tender Evaluation Committee of the Department will evaluate the tenders received.  The Consultant will be requested to do a risk analysis of the lowest tender(s) and assess samples and products for compliance and design intent.

Advise the Client on any alternative designs and tenders, but exclude detailed inspection, reviewing and checking of alternative designs and drawings not prepared by the Consultant and submitted by any contractor or potential contractor.

Tender/Bid Recommendation

The Consultant will be expected to conduct a tender site inspection and to report and make recommendations on the acceptance of tenders.  Notices to tenderers (Addendums) must be avoided as far as possible.  If the matter arose from the site inspection that the issuing of a notice to tenderers is essential, it must be approved by the Departmental Project Manager and issued to the tenderers by the Consultant no later than fourteen (14) days before the closing date of the tender.

An agenda must be issued for, and minutes kept of the tender site inspection.  Both these documents will be used for future reference only, and are not contractually binding.

SABS 1200 (SANS 1200) specifications should not be bound into the tender document.

Contract Documentation

No annotations, remarks or alterations whatsoever are to be made in the Priced Schedules, tender form or any other part of the Tender.

All tender documents are to be returned to the Department by hand or registered post.

Please note and attend to paragraph 26 of ST36, “Conditions and Procedures in regard to Tender, Contract and Order” (available from the Chief Director: State Purchases) which states that although prices and names may be made known (on request) at the opening of tenders these may not be disclosed by telephone or other means subsequently.

The Department will arrange for the signing of the Contract documentation after the awarding of the Contract.

ANNEXURES : SECTION D

CONTENTS

Item			Page

ANNEXURES : SECTION D	9

1.	ANNEXURE D1:  SEQUENCE OF PROCUREMENT DOCUMENTS	10

2.	ANNEXURE D2:  CONDITIONS OF CONTRACT	12

3.	ANNEXURE D3:  PROJECT SPECIFICATION CLAUSES	16

4.	ANNEXURE D4:  DRAWINGS	34

5.	ANNEXURE D5:  SITE CLEARANCE CERTIFICATE	39

6.	ANNEXURE D6:  FORM OF GUARANTEE	41

7.	ANNEXURE D7:  PRO FORMA RISK ASSESSMENT REPORT	43

- ANNEXURE D1:  SEQUENCE OF PROCUREMENT DOCUMENTS

SEQUENCE OF PROCUREMENT DOCUMENTS (From QS 002)

The three (3) volume approach has been adopted by the Department for building contracts (JBCC) and the single volume approach for engineering contracts (GCC).

Building contract procurement documents shall be formatted and compiled under the standard headings and sequencing of documents for the three (3) volume approach, as indicated in the table below.

The Departmental Project Manager will be responsible for the completion of all procurement forms, as well as for assembling the procurement documents.

The Consultant Quantity Surveyor must advise and may, wherever required, assist the Departmental Project Manager with the completion of relevant procurement forms.

The Standard for Uniformity in Construction Procurement has no requirement for colour coding component documents.  It is nevertheless recommended that any colour identification of component documents be undertaken in accordance with the provisions of SANS 10403, as the CIDB recognises this standard as best practice.

SANS 10403 suggests that for identification purposes of the various sections, each section may be printed on different coloured paper or be separated by coloured paper.  In this instance, the colours for each subcomponent should be as indicated in the table below.

The Department recommends that the documentation be printed on white paper and be separated by the relevant coloured pages.

The standard headings, sequencing of documents and colour coding for the single volume approach are indicated in the table below.

Note:	The single volume approach is for engineering contract procurement documents only. The table below is included for information purposes only

TABLE: SINGLE VOLUME APPROACH: SEQUENCE OF DOCUMENTS (From QS 002)

| No. | Document |  | Description | Paper Colour |
| --- | --- | --- | --- | --- |
| 1 | Cover page |  | DPW Procurement document cover sheet | White |
| 2 | Table of contents |  | Description of contract at top of page and DPW logo | White |
| 3 | Document breakdown structure |  | Organogram of content | White |
| 4 | 1. | THE TENDER | Description of contract at top of page and DPW logo | White |
| 5 | 1.1 | Tender procedure | Description of contract at top of page and DPW logo | White |
| 6 | PA-04 (EC) |  | Notice of invitation to tender | White |
| 7 | DPW-03 (EC) |  | Tender data | Salmon |
| 8 | 1.2 | Returnable documents | Description of contract at top of page and DPW logo | White |
| 9 | PA-09 (EC) |  | List of returnable documents | White |
| 10 | PA-11 |  | Declaration of interest and bidder’s past supply chain management practices | White |
| 11 | PA-15.1 |  | Resolution of board of directors | White |
| 12 | PA-15.2 |  | Resolution of board of directors to enter into consortia or joint ventures | White |
| 13 | PA-15.3 |  | Special resolution of consortia or joint ventures | White |
| 14 | DPW-15 (EC) |  | Schedule of proposed subcontractors | White |
| 15 | DPW-16 (EC) |  | Site inspection meeting certificate | White |
| 16 | PA-16.1 (EC) |  | Reference points claim form and affidavit | White |
| 17 | PA-14 |  | Medical certificate for the conformation of permanent disabled status | White |
| 18 | DPW-09 (EC) |  | Particulars of tenderers projects | White |
| 19 | DPW-21 (EC) |  | Record of addenda to tender documents | White |
| 20 | DPW-15 (EC) |  | Schedule of proposed subcontractors | White |
| 21 | DPW-22 (EC) |  | Particulars of electrical contractor | White |
| 22 | DPW-23 (EC) |  | Schedule for imported materials and equipment | White |
| 23 | 2. | THE CONTRACT | Description of contract at top of page and DPW logo | White |
| 24 | 2.1 | Agreement of contract data | Description of contract at top of page and DPW logo | White |
| 25 | DPW-07 (EC) |  | Form of offer and acceptance | White |
| 26 | DPW-05: (EC) (project specific) |  | Contract data – (GCC (2004) 1st edition: 2004 | Pink |
| 27 | PA-16.2 (EC) |  | Tender and Contract Conditions pertaining to Contract Participation Goal (Participation of Targeted Enterprises) | White |
| 28 | DPW-10.2 (EC) |  | Variable construction guarantee (GCC (2004) 1st edition: 2004 | White |
| 29 | DPW-10.4 (EC) |  | Fixed construction guarantee (GCC (2004) 1st edition: 2004 | White |
| 30 | 2.2 | Pricing data | Description of contract at top of page and DPW logo | White |
| 31 | PG-02.1 (EC) |  | Pricing instruction - (GCC (2004) 1st edition: 2004 | Yellow |
| 32 | Contents: Bill of Quantities |  | Description of contract at top of page | Yellow |
| 33 | Bill of Quantities |  | Project specific | Yellow |
| 34 | 2.3 | Scope of work | Description of contract at top of page and DPW logo | White |
| 35 | PG-01.1 (EC) |  | Scope of works - (GCC (2004) 1st edition: 2004 | Blue |
| 36 | 2.3.3 | Technical specifications | Description of contract at top of page and DPW logo | White |
| 37 | Technical specifications |  | Specifications as required | White |
| 38 | 2.3.4 | Additional specifications | Description of contract at top of page and DPW logo | White |
| 39 | HIV/AIDS specification and schedules |  | Standard PW1544 specification and schedules | White |
| 40 | Occupational Health & Safety specification |  | Project specific. Prepared by Consultant | White |
| 41 | 2.4 | Site information |  | White |
| 42 | PG-03.1 (EC) |  | Site information - (GCC (2004) 1st edition: 2004 | White |
| 43 | List of drawings |  | Description of contract at top of page and DPW logo | White |
| 44 | Photo report |  | Description at each photo | White |

- ANNEXURE D2:  CONDITIONS OF CONTRACT

CONDITIONS OF CONTRACT

CIVIL ENGINEERING PROJECTS

For the General Conditions of Contract See DPW-05: EC CONTRACT DATA (GCC (2004) 1st EDITION (2004) “dpw05_ec (GCC2004)”, (GCC 2004 Issued by the South African Institution of Civil Engineers) (Newest version))

The Project Manager will provide the Consultant with the latest version of DPW-05 to complete.  (As example, only page 1 of 12 of the document is shown here)

DPW-05:  (EC) CONTRACT DATA- (GCC (2004) 1st EDITION: 2004)

| Project title: | Insert project description |  |  |  |
| --- | --- | --- | --- | --- |
| Tender no: |  |  | Reference no: |  |

|  | PART 1: DATA PROVIDED BY THE EMPLOYER |
| --- | --- |
|  | CONDITIONS OF CONTRACT |
|  | The General Conditions of Contract for Construction Works (2004) [hereinafter referred to as GCC 2004], published by the South African Institution of Civil Engineering, is applicable to this Contract. |
|  | CONTRACT SPECIFIC DATA |
|  | The following contract specific data; amendments; additions; or omissions are applicable to this Contract. |

| CLAUSES | Compulsory Data |
| --- | --- |
| 1.1.14 | “Employer” means the Government of the Republic of South Africa in its Department of Public Works. |
| 1.2.2 | The addresses of the Employer, where the Employer shall receive notices, are as follows: Physical Address: insert physical address insert town insert code Postal Address: insert postal address insert town insert postal code Facsimile: insert fax no Telephone: insert tel no |

| 1.1.15 | The name of the Engineer is: insert name |
| --- | --- |
| 1.2.2 | The address of the Engineer, where the Engineer shall receive notices, are as follows: Physical Address: insert physical address insert town insert code Postal Address: insert postal address insert town insert postal code Facsimile: insert fax no Telephone: insert tel no |
| 1.1.21 | Not applicable to this Contract |

COMPREHENSIVE PROJECTS

The Conditions of Contract for use in connection with works of comprehensive civil engineering construction shall be the DPW-04 (EC): CONTRACT DATA: JBCC 2000 PRINCIPAL BUILDING AGREEMENT (Edition 4.1 of March 2005), document, based on the JBCC series 2000 PRINCIPAL BUILDING AGREEMENT (Edition 4.1 of March 2005)  prepared by the Joint Building Contracts Committee.

The latest version of DPW-04 will be used by the Project Manager and the Quantity Surveyor to complete with the assistance from the Consultant. (Only page 1 of 14 as an example of the document is shown here)

DPW-04 (EC):  CONTRACT DATA: JBCC 2000 PRINCIPAL BUILDING AGREEMENT (Edition 4.1 of March 2005)

| Project title: | Insert project description |  |  |  |
| --- | --- | --- | --- | --- |
| Tender no: |  |  | Reference no: |  |

|  | The Conditions of Contract are clauses 1 to 41 of the JBCC Series 2000 Principal Building Agreement (Edition 4.1 of March 2005) prepared by the Joint Building Contracts Committee. Copies of these conditions of contract may be obtained through most regional offices of the Association of South African Quantity Surveyors, Master Builders Association, South African Association of Consulting Engineers, South African Institute of Architects, Association of Construction Project Managers, Building Industries Federation South Africa, South African Property Owners Association or Specialist Engineering Contractors Committee. |
| --- | --- |

|  | CONTRACT VARIABLES THE SCHEDULE The schedule contains all variables referred to in this document and is divided into part 1: contract data completed by the employer and part 2: contract data completed by the contractor. Part 1 must be completed in full and included in the tender documents. Both the part 1 and part 2 form part of this agreement Spaces requiring information must be filled in, shown as ‘not applicable’ or deleted but not left blank. Where choices are offered, the non-applicable items are to be deleted. Where insufficient space is provided the information should be annexed hereto and cross referenced to the applicable clause of the schedule. Key cross reference clauses are italicised in [ ] brackets |
| --- | --- |

| 42.0 | Part 1: Contract Data completed by the Employer: |
| --- | --- |

| 42.1 | CONTRACTING AND OTHER PARTIES |
| --- | --- |
| 42.1.1 [1.2] | Employer: Government of the Republic of South Africa in its Department of Public Works Postal address: insert postal address insert town insert postal code Tel: insert tel no Fax: insert fax no Physical address: insert physical address insert town insert code |

ADDITIONAL DOCUMENTS FORMING PART OF THE TENDER

All the documents that form part of the tender document are listed in The Procurement Document Guidelines (QS002)

The Departmental Project Manager will give guidance regarding the compilation of the document

LIST OF SPECIFICATIONS

The standard specifications on which this contract is based are the South African Bureau of Standards Standardized Specifications for Civil Engineering Construction SANS 1200, as well as other DPW specifications as listed below.

Although not bound in nor issued with this Document, relevant Sections of the Standardized Specifications of SANS 1200 shall form part of this Contract.

| 1. | SABS 1200 (SANS 1200) | - | Standardised Specifications for Civil Engineering Construction* |
| --- | --- | --- | --- |
| 2. | SANS 10400 | - | The application of the National Building Regulation* |
| 3. | SANS Standard Specifications* |  |  |
| 4. | PW371 | - | Specification of Materials and Methods to be Used.** |
| 5. | PW331 | - | Standard Specification for Electrical Installations and Electrical Equipment pertaining to Mechanical Services - Issue IX (a), December 1998.** |
| 6. | PW354 | - | Standard Electrical Specifications, August 2004* |
| 7. | PW348 and PW349 | - | Guide for architects concerning drainage, water supply and storm water drainage.** |
| 8. | PW1544 | - | HIV Specification for Civil Engineering Contracts.** |
| 9. | PW344 | - | Appropriate Development of Infrastructure on Dolomite.** |
| 10. | PW147 | - | Manual for Private Architects.** |
| 11. | PW2006/1 | - | Identification of Problematic Soils in Southern Africa: Technical Notes for Civil and Structural Engineers.** |
| 12. | PW2011/1 | - | Small Waste Water Treatment Works |
| 13. | PW343 | - | Building Specifications in Regional Offices.** |

*	Not issued with this document, but available at the Contractor’s expense from the S A Bureau of Standards, Private Bag x 191, PRETORIA, 0001.

**	Not issued with this document, but available on the web-site of the Director General, Department of Public Works,  http://www.publicworks.gov.za/

- ANNEXURE D3:  PROJECT SPECIFICATION CLAUSES

PROJECT SPECIFICATION CLAUSES

INTRODUCTION

The Project Specification, consisting of two (2) parts, forms an integral part of the contract and supplements the Standard Specifications.

Part A contains a general description of the works, the site and the requirements to be met.

Part B contains variations, amendments and additions to the Standardized Specifications and, if applicable, the Particular Specifications.

In the event of any discrepancy between a part or parts of the Standardised or Particular Specifications and the Project Specification, the Project Specification shall take precedence.  In the event of a discrepancy between the specifications, (including the Project Specifications) and the drawings and/or the Bill of Quantities, the discrepancy shall be resolved by the Consultant before the execution of the work under the relevant item.

PROJECT SPECIFICATION CLAUSES

The following clauses must be considered and used where applicable depending on the circumstances pertaining to the particular site:

GENERAL DESCRIPTION

Each installation requires work that may include any one or more of the activities as set out below.

DESCRIPTIONS OF SITE AND ACCESS

An A4 size locality plan as Annexure A to the Project Specification must be included.

NATURE AND CONDITION OF EXISTING MATERIALS AND EQUIPMENT

DETAILS OF CONTRACT

CONSTRUCTION PROGRAMME

When compiling his construction programme, the Contractor shall take into account the time for completion of all work of each installation as amended in Part 1 of the Contract Data.

SITE FACILITIES AVAILABLE

CAMP SITE AND STOREROOM

WATER, ELECTRICITY AND SEWERAGE

Source of Water Supply

Water that the Contractor may use at his own discretion is available on site.  The Contractor must make the temporary connection and install a meter at his own expense at a point approved by the Engineer.  The connection shall be watertight.  Water will not be charged for, but consumption will be monitored in order to prevent wastage.

Where the site is located on dolomite, the Contractor shall take the necessary precautions to safeguard the use/abuse of water.  If the Engineer is of opinion that the Contractor is negligent or abusing the service in such a way that the continual use of the service compromises the integrity of the underlying dolomite, the service may be discontinued.  The Contractor will make his own arrangement for water in such cases.

The Department does not guarantee the sufficiency or continuity of the supply and no claims will be considered in this regard.

The Contractor will be held responsible for any wastage of water due to negligence.

Source of Power Supply

If Single/3 Phase electric power is available on site, the Contractor may use it at his own discretion.  The Contractor must make the temporary connection and install a meter at his own expense at a point approved by the Engineer.  Power will be charged for at a tariff to be determined by the Regional Manager of the Department.

The Department does not guarantee the sufficiency or continuity of the electrical supply and if the supply should fail or be insufficient, the Contractor shall make his own arrangements.  The Department will not be liable for any claims in this respect.

Sewerage connection

The contractor shall ensure that hygienic safe and easily accessible toilet facilities are available.

If a sewerage connection is not available on site, chemical toilets shall be used.

NOTE:	  The Employer shall not be held responsible for any losses or inconvenience due to a disruption in the supply of water and/or electricity.

PARKING FACILITIES

Parking facilities are available on the Site.

SITE FACILITIES REQUIRED FOR THE ENGINEER

GENERAL

CONTRACT NAME BOARDS

MOBILE PHONES

ACCOMMODATION FOR ENGINEER'S REPRESENTATIVE

CALL CENTRE

FEATURES REQUIRING SPECIAL ATTENTION

INSTALLATIONS AT FACILITIES

The installations at all facilities shall be carefully checked for damage and all damages shall be listed and discussed with the Engineer before commencement of repair and maintenance work.  The Contractor shall present copies of all correspondence in this regard for discussion at the following site meeting.

SECURITY

| (a) | Restrictions on movement and limited access |
| --- | --- |
|  | The Contractor's personnel, vehicles and equipment will be restricted to areas of construction only. The Contractor shall comply with any requirements that the Engineer and User Department may have in this regard and shall take note that access to some areas may be limited for security reasons. |
| (b) | Prohibition on taking of photographs |
|  | The Contractor's attention is drawn to the Defence Act, 1957 (Act No 44 of 1957) and the Correctional Services Act, 1998 (Act No. 111 of 1998) which clearly state that the taking of photographs is prohibited and that even the possession of a camera on Site is an offence. Permission to take photographs of damaged equipment may be arranged by the Engineer. |
| (c) | Security check on personnel |
|  | The Employer may ask the Contractor to have his personnel or a certain number of them security-classified, if required by any competent authority. In the event of the Employer or any competent authority requiring the removal of a person/persons from the site for security reasons, the Contractor shall do so forthwith and the Contractor shall thereafter ensure that such person/persons are denied access to the site and/or to any documents or information relating to the work. In such circumstances, the Contractor shall indemnify the Employer and the Engineer and will discharge the Employer and the Engineer from any claims whatsoever. |
| (d) | Access cards to security areas |
|  | All personnel are subject to access control measures. The Contractor shall supply access cards (laminated cards containing colour photograph, name, surname, ID number, etc) for his security-cleared personnel and employees who work within such an area. The Contractor must comply with any regulations or instructions issued by the Department of Correctional Services or SA Police services from time to time, concerning the safety of persons and property. |

SITE TO BE KEPT CLEAN

During the progress of the work and upon completion thereof, the site of the Works shall be kept and left in a clean and orderly condition.  The Contractor shall store materials and equipment for which he is responsible in an orderly manner, and shall keep the site free from debris and obstructions.

All redundant materials, rubbish and waste arising from the work must be removed from the site at the Contractor’s cost and the site and buildings left clean and tidy.

FACILITIES TO OTHER CONTRACTORS

In addition to the requirements of Clause 18 of the General Conditions of Contract, the Contractor must make allowances for other Contractors on the site.  This may involve adapting his programme to accommodate the work of other contractors and ensuring access to their sites along prescribed routes over the site of this Contract.

SUBCONTRACTORS

In addition to the requirements of Clause 6 of the General Conditions of Contract as amended in Part 1 of the Contract Data, the Contractor shall be responsible for work carried out by subcontractors on his behalf.  The Engineer will not liaise directly with such subcontractors.  Problems related to payments, programming, workmanship, etc, shall be the responsibility of the Contractor and the subcontractor.  The Contractor will report payment to subcontractors to the Engineer.  Payment must be declared on a monthly basis.

SANS SPECIFICATIONS AND CODES OF PRACTICE

In this document all reference to South African National Standards specifications and codes of practice, or any other standard specifications or codes of practice, including National Building Regulations, shall will deemed to be references to the latest issues of such specifications and codes.

MATERIALS

The monthly payment for materials brought onto the site will only be applicable for repair work and not for maintenance work.

Unless otherwise instructed in writing by the Engineer, all proprietary materials are to be used, mixed, applied, fixed, etc, strictly in accordance with the manufacturer's recommendations.

BORROW PITS

There will be no designated borrow pits.  The Contractor shall utilise the material on Site or import material from commercial sources.

PROTECTION OF FURNITURE AND EQUIPMENT

In the event where work is to be done inside buildings where there is furniture and other equipment involved, the Contractor will be responsible for moving the furniture and equipment in order to provide working space for his personnel.  The programme shall be drawn up in such a way as to keep the movement of furniture and equipment to the very minimum and the Contractor shall be solely responsible for any damage to furniture or equipment.

TESTING AND QUALITY CONTROL

The Contractor shall engage the services of an approved independent laboratory or other institution as applicable for quality testing, in order to ensure that his work complies with the specifications.

No separate payment will be made for such testing, the cost will be deemed to be included in the Contractor's rates for the items of work that require testing in accordance with the Specifications.

The onus to produce work that conforms to the requirements of the Specifications and Drawings regarding quality and accuracy of detail, rests upon the Contractor and he will, at his own expense, institute a quality-control system and provide experienced engineers, foremen, surveyors, materials technicians, other technicians and technical staff, together with all transport, instruments and equipment to ensure adequate supervision and positive control of the Works at all times.

The cost of supervision and process control, including testing carried out by the Contractor, will be deemed to be included in the rates bid for the related items of work.

The Contractor's attention is drawn to the provisions of the various Specifications regarding the minimum frequency of testing required.  The Contractor shall increase this frequency at his own discretion, to ensure adequate control where necessary.

On completion and submission of every part of the work to the Engineer for examination, the Contractor shall furnish the Engineer with the results of the relevant tests to indicate compliance with the Specifications.

CERTIFICATES OF PAYMENT

The statement to be submitted by the Contractor in terms of Clause 49 of the General Conditions of Contract shall be prepared in accordance with the standard payment certificate prescribed by the Engineer and shall comprise at least two (2) sets of A4-size paper copies.

All costs for the preparation and submission of the statements shall be borne by the Contractor.

CONSTRUCTION IN RESTRICTED AREAS

Working space in certain areas may be restricted.  The construction method used in these restricted areas largely depends on the Contractor's Plant.  However, the Contractor must note that measurement and payment will be according to the specified cross-sections and dimensions irrespective of the method used, and that the rates and prices submitted will be deemed to include full compensation for difficulties encountered while working in restricted areas.  Neither extra payment nor any claim for payment due to these difficulties will be considered.

DRAWINGS

The Contractor will, in terms of Clause 13 of the General Conditions of Contract, be provided free of charge with three (3) paper prints of each drawing issued to him.

All information in the possession of the Contractor that is required by the engineer to complete the “as-built” drawings must be submitted to the engineer before a Certificate of Completion will be issued.

Only figured dimensions shall be used and drawings shall not be scaled unless required by the engineer.  The engineer will provide the dimensions that may have been omitted from the drawings.

OPEN

LEGISLATION

| (a) | Changes in legislation |
| --- | --- |
|  | In the General Conditions of Contract and in any other standard document forming part of this Contract to legislation, which has been amended or superseded by other legislation since the most recent publication of such standard document, any reference will be deemed to be a reference to the amended or replacement legislation. |
|  | Such amended or replaced legislation shall be applicable during the contract period provided the amendment or replacement occurred more than twenty eight (28) days before the closing date for bids in terms of Clause 46.4 of the General Conditions of Contract as amended in Part 1 of the contract Data. |

| (b) | The Occupational Health and Safety Act |
| --- | --- |
|  | The Contractor shall be required to comply with the Occupational Health and Safety Act, 1993: Construction Regulations, 2003 as promulgated in Government Gazette No. 25207 and Regulation Gazette No. 7721 of 18 July 2003. Non-compliance with these regulations, in any way whatsoever, will be adequate reason for suspending the Works. The proposed type of work, materials to be used and hazards likely to be encountered on this Contract are detailed in the Scope of Work, Pricing Data and Drawings. The Employers' health and safety specifications (sub clause 4(1)) of the regulations will be issued separately. In terms of sub clause 5(1) the Contractor will provide a comprehensive health and safety plan detailing his proposed compliance with the regulations, for approval by the Employer. The Contractor shall at all times be responsible for full compliance with the approved plan as well as the Construction Regulations and no extension of time will be considered for delays due to non-compliance with the abovementioned plan or regulations. A payment item is included in the Bill of Quantities to cover the Contractor's cost for compliance with the OHS Act and the abovementioned Construction Regulations 2003. |

OPEN

INSURANCE AMOUNTS

The amounts for which the Contractor must insure the Works in terms of Clause 35 of 
Part 1 of the Contract Data are stated in the Agreement.

TIMES FOR COMPLETION

Times for completion of repair work to installations as well as the maintenance down-time for different types of breakdowns are given under Clause 42.1 of Part 1 of the Contract Data.  The time for completion will start on the date of access to an installation.

PRACTICAL COMPLETION

| (a) | The Contractor will, in terms of Clause 51.1 of the General Conditions of Contract, be entitled to receive a Certificate of Practical Completion when the Works to be executed under the Contract have been completed to the stage where: |  |
| --- | --- | --- |
|  | (i) | All materials which are required to be replaced have been replaced and installed to the satisfaction of the Engineer; and |
|  | (ii) | All repair and modification works have been completed |
| (b) | The Engineer will issue a Certificate of Completion in terms of Clause 51.4 of the General Conditions of Contract to the Contractor and the Employer, except where a thirty (30) day commissioning period is applicable as stated in paragraph (c) below. |  |
| (c) | Where indicated at the end of this paragraph, the issuing of a Certificate of Practical Completion for a certain installation will be followed by a thirty (30) day commissioning period. The tasks of the Contractor during the thirty (30) day commissioning period are described in Additional Specification SC: General Decommissioning, Testing and Commissioning Procedures. After the completion of the thirty (30) day commissioning period to the satisfaction of the Engineer, a certificate of completion will be issued to the Contractor as described in Clause 51.4 of the General Conditions of Contract. |  |

PENALTIES

In terms of Clause 43.1 of the General Conditions of Contract for late completion of repair work to different installations penalties are given under Clause 43.1 of Part 1 of the Contract Data.  Payment reductions for exceeding the maintenance down-time for different types of breakdowns are given under the applicable pay items in the Bill of Quantities for Additional specifications SA:  General Maintenance.  Penalties will run concurrently where applicable.

| (a) | Penalty for failing to meet undertakings and/or conditions pertaining to Targeted Procurement for the award of points |
| --- | --- |
|  | If the bid adjudication points awarded to the Contractor are found to be based on incorrect or false information or the conditions pertaining to the award of points are not met and the Contractor fails to substantiate that such failure is due to a reason acceptable to the Employer (as being) beyond the Contractor’s control, the Contractor shall be liable for and pay to the Employer, and amount determined in accordance with Clause 2 and subject to Clause 1 both of the Works Information, Part 2 of the Conditions of Bid. |
| (b) | Payment reduction for non-performance |
|  | If the Contractor shall fail to rectify a fatal breakdown, an emergency maintenance breakdown, an ordinary maintenance breakdown and damage breakdown within the time as stipulated in Additional Specifications SA: General Maintenance, the Contractor shall be liable to the Employer for the sum/sums stated in the Bill of Quantities for Additional Specification SA as a payment reduction for every hour/day down-time counting from the hour/day the breakdown was reported to the Contractor until the day it was repaired. These payment reductions will be cumulative and will run concurrently. Where indicated above that the money will be recovered from the Contractor by means of payment reductions, the fixed negative amounts in the rate column of the Bill of Quantities will be used to reduce payments due to the Contractor. The imposition of such payment reductions shall not relieve the Contractor from his obligation to complete the Works or from any of his obligations and liabilities under the Contract. |
| (c) | Application of penalties to be accumulative |
|  | The imposition of all penalties in terms of this clause shall be accumulative and shall not relieve the Contractor from his obligation to complete the Works or from any of his obligations and liabilities under the Contract. |

NON-WORKING DAYS AND HOURS

Whenever any special non-working days stated in Clause 1.6 and Clause 38 of Part 1 of the Contract Data fall within the days allowed or stipulated in the Contract in terms of Clause 1.6 of Part 1 of the Contract Data, such special non-working days shall also be excluded from the calculation of the number of working days concerned.

The Contractor shall not work on any statutory public holidays or on any public holidays declared by the Government to be statutory non-working days, except for work related to repair fatal and emergency breakdowns, which influences the functionality of any of the installations.

Working hours might be limited and the Contractor shall work in close cooperation with the User Client and Engineer in this regard.  Working hours for the different installations are indicated at the end of this clause where applicable.

The Engineer shall be entitled at any time during the Contract, to vary the normal working hours specified in the Bid documents, including increasing or decreasing the total number of hours per day during which the Contractor may execute the Works or specific portions thereof.

If any variation by the Engineer of the normal working hours specified in the Bid Documents should result in an increase or a decrease in the total number of hours per week during which the Contractor is permitted to execute the Works or any particular portions of Works, then the time allowed in the Contract for the completion of the respective part of the Works to which the varied normal working hours apply shall be adjusted proportionately in relation to:

| (a) | the remaining time allowed for completion of the specific part or parts of the Works; and |
| --- | --- |
| (b) | the extent of the variation in the total normal working hours per week. |

SAMPLES

Materials or work will be rejected if it does not conform to the approved samples submitted in terms of sub clause 26(4) of the General Conditions of Contract.  The Engineer reserves the right to submit test-samples to ensure that the material represented by the sample meets the specification requirements.

WORKMANSHIP AND QUALITY CONTROL

The onus to produce work that conforms to the requirements of the Specifications and Drawings regarding quality and accuracy of detail, rests upon the Contractor and he will, at his own expense, institute a quality-control system and provide experienced engineers, foremen, surveyors, materials technicians, other technicians and technical staff, together with all transport, instruments and equipment to ensure adequate supervision and positive control of the Works at all times.

The cost of supervision and process control, including testing carried out by the Contractor, will be deemed to be included in the rates tendered for the related items of work.

The Contractor's attention is drawn to the provisions of the various Specifications regarding the minimum frequency of testing required.  The Contractor shall, at his own discretion, increase this frequency to ensure adequate control where necessary.

On completion and submission of every part of the work to the Engineer for examination, the Contractor shall furnish the Engineer with the results of the relevant tests to indicate compliance with the Specifications.

OPEN

DECOMMISSIONED/DISCARDED MATERIALS

| (a) | Storeroom |
| --- | --- |
|  | Ownership of the material shall, however, lie with the Department of Public Works. Material to be decommissioned by the Contractor shall be removed to this maintenance storeroom and added to the inventory. This material shall then become available to the Contractor for use in the execution of his maintenance duties. The Contractor will apply from the Engineer for approval to dispose of any material at an approved landfill. |

EXPLOSIVE CLASSIFICATIONS OF THE FUEL INSTALLATIONS

APPLICABLE STANDARDISED SPECIFICATIONS

PS8.n	RESTRICTED WORKING HOURS

In terms of Clause 38 of GCC 2004, normal working hours will be those hours laid down by the Commanding Officer in conjunction with the Engineer.

PS9.n	ABNORMAL RAINFALL

The values of Nn and Rn for use in Clause 47.5 of Contract Data shall be as follows: -

Source of information:  Weather Bureau, Department of Transport.

| Rainfall Station: | ......................................... |  |  |
| --- | --- | --- | --- |
| Period: From: | ......................................... | to | ......................................... |

| MONTH | Nn | Rn | MONTH | Nn | Rn |
| --- | --- | --- | --- | --- | --- |
| January |  |  | July |  |  |
| February |  |  | August |  |  |
| March |  |  | September |  |  |
| April |  |  | October |  |  |
| May |  |  | November |  |  |
| June |  |  | December |  |  |
| Average Annual Rainfall: |  |  |  |  |  |

PSAn	TIME RELATED ITEMS (Sub-clause 8.2.2)

An approved extension of time (other than an extension of time granted in terms of Clause 47.5 of Contract Data will entitle the Contractor to submit a claim for additional payment.  Any such approved additional payment will be made for proven additional costs for each relevant time related item but will be limited to a maximum amount determined from the sum tendered for such item and from the designated operation, the period stated for the completion of the item or the tendered contract period, as applicable.

PSABn	NAME BOARD (Sub-clause 3.2.1)

You must make provision for only one name board as per Annexure B5, which must be bound in as Annexure A to the Project Specification.

PSACn	SAMPLE/TRIAL SECTION

Depending on the nature of the contract, a clause must be added requiring a sample/trial section to be provided, constructed and approved by the engineer before the actual work is executed.

PSADn	PREAMBLE CLAUSES

The standard preamble to the Schedule of Quantities as laid down in SABS 0120 
(SANS 10120) Section 4: Part A:  General must be used with the following change(s).

1.1.6  A price, rate or the word “NIL” is to be entered against each item of the Schedule of quantities, whether the quantities are stated or not.  If a rate is not entered against an item or a word other than “NIL” is entered the item will be considered to be covered by other prices in the schedule but the rate will nevertheless be taken as NIL and no claim will be considered if the quantity of such item increase or decrease.

PSA	GENERAL

PSA 1	SCOPE

Replace sub clause 1.1 with the following:

"1.1	  This specification covers requirements, principles and responsibilities of a general nature that are normally applicable to all Civil Engineering Contracts, as well as the requirements for the Contractor's establishment on the Site."

PSA 2	INTERPRETATIONS

PSA 2.3	DEFINITIONS

| (a) | General |
| --- | --- |
|  | ADD THE FOLLOWING DEFINITIONS: |
|  | "General conditions: The General Conditions of Contract specified for use with this Contract, and the Contract Data. |
|  | Specified: As specified in the standardised and standard specifications, the Drawings or the Scope of Work. |
|  | Permanent Works: as defined in Clause 1.1.17 of the General Conditions of Contract shall for the purpose of this Contract, be regarded as the repair work and maintenance work as defined in Sub clause SA 02.06 of Additional Specification SA: General Maintenance.” |
| (b) | Measurement and payment |
|  | Replace the definitions for "fixed charge", "time-related charge" and "value-related charge" with the following: |
|  | "Fixed charge: A charge that is not subject to adjustment on account of variation in the value of the Contract price or the Contract Time of Completion. |
|  | Time-related charge: A charge, the amount of which varies in accordance with the Time for Completion of the repair work, adjusted in accordance with the provisions of the Contract. |
|  | Value-related charge: A charge, the amount of which varies pro rata with the final value of the measured repair work executed and valued in accordance with the provisions of the Contract." |

PSA 2.4	ABBREVIATIONS

| (a) | Abbreviations relating to standard documents |
| --- | --- |
|  | ADD THE FOLLOWING ABBREVIATION:: |
|  | "CKS: SABS Co-ordinating Specification." |

PSA 3	MATERIALS

PSA 3.1	QUALITY

ADD THE FOLLOWING:

"All manufactured materials supplied shall be new materials unless the contrary is specified.  All materials specified in accordance with SABS Specifications shall bear the SABS mark, whether so specified or not."

ADD THE FOLLOWING SUB-CLAUSE:

"PSA 3.3	ORDERING OF MATERIALS

The quantities set out in the Bill of Quantities have been carefully determined from calculations based on data available at the time and should therefore be considered to be approximate quantities only.  Before ordering materials of any kind, the Contractor shall check with the Engineer whether or not the scope of the work for which the materials are required is likely to change substantially.  No liability or responsibility whatsoever shall be attached to the Employer for materials ordered by the Contractor except when ordered in accordance with written confirmation issued by the Engineer."

PSA 4	PLANT

PSA 4.2	CONTRACTOR'S OFFICES, STORES AND SERVICES

ADD THE FOLLOWING PARAGRAPH BEFORE THE FIRST PARAGRAPH:

“One (1) office (with toilet seat and wash-hand basin), one (1) storeroom and one (1) workshop (unequipped) will be made available for the exclusive use of the Contractor.

No personnel may reside on the Site.  Only one (1) night-watchman may be on the Site after hours.”

PSA 5 	CONSTRUCTION

PSA 5.4	PROTECTION OF OVERHEAD AND UNDERGROUND SERVICES

Replace the heading and the contents of this sub clause with the following:

“PSA 5.4	LOCATION AND PROTECTION OF EXISTING SERVICES

PSA 5.4.1	Location of existing services

Before underground or excavation work is carried out, the Contractor shall ascertain the presence and position of all services likely to be damaged or interfered with by his activities.  He shall obtain up-to-date plans from the Engineer for this purpose, showing the position of services in the area where he intends to work.  As services can often not be reliably located from such plans, the Contractor shall determine the exact position of such services by means of suitable detecting equipment and afterwards by careful hand excavation where necessary in order to expose the services at the positions of possible interference by his activities.  This procedure shall also be followed in respect of services not shown on the plans but believed to be present.

All such services, the positions of which have been located at the critical points, shall be designated as 'known' services and their positions shall be indicated on a separate set of Drawings, a copy of which shall be furnished to the Engineer.

While he is occupying the Site, the Contractor shall be liable for all damage caused by him to known services as well as for consequential damage, whether caused directly by his operations or by the lack of proper protection.

PSA 5.4.2	Protection during repair modification and maintenance work

The Contractor will exercise all the necessary care to prevent damage to known services.  Major excavating equipment and other plants will not be operated dangerously close to these services.  Where necessary, excavation in close proximity to these services shall be carefully carried out with suitable hand tools, excluding picks wherever their use could damage the services.  No additional payment will apply to such more difficult work.

Services left exposed shall be suitably protected from damage.

PSA 5.4.3	Alterations and repairs to existing services

Unless the contrary is clearly specified or ordered, the Contractor shall not carry out alterations to existing services.  When this is necessary, the Contractor shall inform the Engineer, who will either make arrangements for such work to be executed by the owner of the service, or instruct the Contractor to make such arrangements himself.

When existing services are damaged by the Contractor, he shall immediately inform the Engineer, or when this is not possible, the relevant authority, and obtain instructions as to who should carry out repairs.  In urgent cases, the Contractor shall take the necessary steps to minimise damage to and interruption of the service.  No repairs of telecommunication cables or electric power lines and cables shall be attempted.

The Employer will accept no liability for damages due to a delay in having such alterations or repairs affected.  The Contractor shall provide all reasonable opportunity, access and assistance to persons carrying out alterations or repairs of existing services."

Add the following sub clause:

"PSA 5.9	SITE MEETINGS

The Contractor will be required to attend regular site meetings, normally held once a month to discuss general progress, quality of work, problems, claims, payments, etc, but not matters concerning the day-to-day running of the Contract."

PSA 6	TOLERANCES

Add the following sub clause:

"PSA 6.4	GENERAL

No guarantee is given that the full specified tolerances will be available independently of each other, and the Contractor is cautioned that the liberal or full use of any one or more of the tolerances may deprive him of the full or any use of tolerances relating to other aspects of the work.

Except where the contrary is specified or when clearly not applicable, all quantities for measurement and payment shall be determined from the 'authorised' dimensions.  These are specified dimensions or those shown on the Drawings or, if changed, as finally prescribed by the Engineer, without any allowance for the specified tolerances.  Except if otherwise specified, all measurements for determining quantities for payment will be based on the 'authorised' dimensions.

If the work is therefore constructed in accordance with the 'authorised' dimensions plus or minus the tolerances allowed, quantities will be based on the 'authorised' dimensions regardless of the actual dimensions to which the work has been constructed.

When the work is not constructed in accordance with the 'authorised' dimensions plus or minus the tolerances allowed, the Engineer may nevertheless, at his sole discretion, accept the work for payment.  In such cases no payment shall be made for quantities of work or material in excess of those calculated for the 'authorised' dimensions, and where the actual dimensions are less than the 'authorised' dimensions minus the tolerance allowed, quantities for payment shall be based on the actual dimensions as constructed."

PSA 7	TESTING

PSA 7.1	PRINCIPLES

PSA 7.1.1	Checking

Replace the last sentence with the following:

“The Contractor shall obtain the services of an independent testing laboratory at his own expense (refer to Clause 8 in Portion 1 of the Project Specifications) to carry out the checks prescribed in the various Standardised Specifications.”

PSA 7.1.2	Standard of finished work not to specification

Replace the words:  “Where the Engineer’s checks reveal …” with “Where the checks by the approved laboratory reveal ……..”

PSA 8	MEASUREMENT AND PAYMENT

PSA 8.1	MEASUREMENT

PSA 8.1.2	Preliminary and general items or section (for repair phase only)

PSA 8.1.2.2	Bid sums

Replace the contents of this sub clause with the following:

"The Contractor's bid sums under items PSA 8.3 and PSA 8.4 shall collectively cover all charges for:

risks, costs and obligations in terms of the General Conditions of Contract, the Contract Data and of this Standardised Specification, except where provision is made in these Project Specifications to cover compensation for any of these items;

head-office and site overheads and supervision;

profit and financing costs;

expenses of a general nature not specifically related to any item or items of permanent or temporary work;

providing facilities on Site for the Contractor's personnel, including offices, storage facilities, workshops, ablutions, for providing services such as water, electricity, sewerage, sewage and rubbish disposal, for access roads and all other facilities required, as well as for the maintenance and removal on completion of the Works of these facilities and the cleaning-up of the camp site on completion of the Works;

providing facilities for the Engineer and his staff as specified in  SANS 1200 AB and in these Project Specifications"

PSA 8.2	PAYMENT

PSA 8.2.1	Fixed-charge and value-related items

Replace the contents of this sub clause with the following:

"Payment of fixed charges in respect of item 8.3.1 fixed preliminary and general will be made as follows:

Eighty (80%) percent of the sum bid will be paid when the facilities have been provided and approved.  The remaining twenty (20%) percent will be paid when the works have been completed, the facilities have been removed and the camp site has been cleared and cleaned.

Payment for the sum bid under item 8.3.2 value related preliminary and general will be made in three (3) separate instalments as follows:

| (a) | The first instalment, which is fourty (40%) percent of the sum, will be paid when the Contractor has fulfilled all his obligations to date under this Standardised Specification, the General Conditions of Contract and the Contract Data, and when the value of work certified for payment, excluding materials on Site and payments for preliminary and general items, is equal to no less than five (5%) percent of the total value of the repair and modification work listed in the Bills of Quantities. |
| --- | --- |
| (b) | The second instalment, which is fourty (40%) percent of the sum, will be made when the amount certified for payment, including retention moneys but excluding this second instalment, exceeds fifty (50%) percent of the repair and modification work. |
| (c) | The final payment, which is twenty (20%) percent of the sum, will be made when the works have been certified as completed and the Contractor has fulfilled all his obligations to date under this Standardised Specification, the General Conditions of Contract and the Contract Data |

Should the value of the measured work finally completed be more or less than the Bid Sum, the sum bid under item 8.3.2 will be adjusted up or down in accordance with the provisions of Clause 50 of the General Conditions of Contract as amended in Part 1 of the Contract Data, and this adjustment will be applied to the third instalment.  No adjustment will apply to item 8.3.1 in respect of variations in the value of work done or after the time for completion has finally been authorised."

PSA 8.2.2	Time-related items

Replace the contents of this sub clause with the following:

"Subject to the provisions of sub clauses 8.2.3 and 8.2.4, payment under item 8.4.1 (time-related item) will be made monthly in equal amounts for each installation, calculated by dividing the sum bid for the item by the repair phase period for the installation in months, , always provided that the total of the monthly amounts paid for the item is not out of proportion with the progress of the work on the installation as a whole.

Should the Engineer grant an extension of Time for Completion of the repair works on the installation, the Contractor will be entitled to an increase in the sum bid for the time-related item, which increase shall be in the same proportion to the original sum bid as the extension of time is to the original Time for Completion of the repair works.

Payment of such increased amounts will be deemed full compensation for all additional time-related preliminary and general costs due to the circumstances pertaining to the extension of time granted for an installation.  The length of the repair phase for each installation is indicated in Part 1 of the Contract Data.

Regarding time-related items, separate provision is made in the Bills of Quantities for each installation individually.  Time-related payment for an installation shall only be made when the repair work on the installation is in progress and shall end when the time for completion or an extension of time granted by the Engineer expires.  When repair work on more than one installation is in progress, time-related payment will be made for each installation and the conditions as stated above shall apply to each installation individually."

PSA 8.3	BILLED FIXED-CHARGE AND VALUE-RELATED ITEMS

Replace the items with the following:

| "PSA 8.3.1 | Fixed preliminary and general charges .............................................. | Unit : Sum |
| --- | --- | --- |

| "PSA 8.3.2 | Value related preliminary and general charges ................................. | Unit : Sum |
| --- | --- | --- |

PSA 8.4	BILLED TIME-RELATED ITEMS

Replace this item with the following:

"PSA 8.4.1	Time-related preliminary and general charges:

The sums bid shall include full compensation for all time-related preliminary and general charges as described in sub clause PSA 8.1.2.2.  Payment will be made as described in sub clause PSA 8.2.2.

NOTE:	  The total amount bid for items PSA 8.3.1, PSA 8.3.2 and PSA 8.4.1 shall not exceed fifteen (15%) percent of the total amount bid for repair work, excluding value-added tax.

PSA 8.5	OPEN

PSA 8.6	PRIME COST ITEMS

Replace this item with the following:

"PSA 8.6	PRIME COST SUMS:

| (a) | Accommodation for Engineer's representative ...................... | Unit : PC Sum |
| --- | --- | --- |
| (b) | Charge required by Contractor on sub item (a) above ........... | Unit : Sum |

The Prime Cost Sum provided under sub item (a) in the Bill of Quantities will be expended in accordance with Clause 45.2 of the General Conditions of Contract.

The bid percentage under sub item (b) will be paid to the Contractor on the value of each payment made to the Engineer.

PSA 8.8	TEMPORARY WORKS

Replace item 8.8.4 with the following:

"PSA 8.8.4	Location and protection of existing services:

PSA 8.8.4.1	Provision of detecting devices for:

| (a) | Water and sewer pipes ............................................................... | Unit : Sum |
| --- | --- | --- |
| (b) | Electrical and other cables .......................................................... | Unit : Sum |

The bid sums shall cover the cost of providing and operating suitable equipment for as long as it is needed to locate all the existing services likely to be affected by the construction activities.  Alternatively, an approved specialist firm may be employed to carry out the work.

PSA 8.8.4.2	Hand excavation necessary for locating and exposing existing services in all material:

| (a) | In roadways ................................................................................ | Unit : m3 |
| --- | --- | --- |
| (b) | In all other areas ......................................................................... | Unit : m3 |

The rates shall cover the cost of excavating by means of hand tools within authorised dimensions, for all precautionary measures to protect the services from damage during excavation and backfilling, and for subsequent backfilling and compacting.  Compaction of material in all areas except in roadways shall be to ninety (90%) percent of the modified AASHTO density.

The rate for hand excavation in roadways shall include compensation for compacting excavated or selected backfill material to ninety three (93%) percent of modified AASHTO density.

The bid rates will also include for keeping excavations safe, for dealing with surface and subsurface water, for removing surplus excavated material from the Site, for transporting all material, and for supplying adequate supervision during both excavation and backfilling operations."

Add the following items:

"PSA 8.9	ADDITIONAL TESTS

| (a) | Additional tests required by the Engineer ............................ | Unit : Rand (R) |
| --- | --- | --- |
| (b) | Attendance and profit ........................................................... | Unit : % |

An amount has been allowed in the Bill of Quantities under sub item (a) to cover the cost of additional tests required by the Engineer.  The Engineer will have the sole authority to spend the amount or part thereof.

The bid percentage under sub item (b) will be paid to the Contractor on the value of each payment made to the testing authority.

In connection with sub-item please note that (a):

The Contractor is responsible for both the cost of normal testing as described in Sub clause PS 8.10 in portion 1 of the Project Specifications as well as for the cost of any additional test indicating that the Specifications have not been complied with.

PSA 8.12	CALL CENTRE

| (a) | Call centre for breakdown calls logged ................................ | Unit : Rand (R) |
| --- | --- | --- |
| (b) | Charge required by contractor on sub-item (a) above ......... | Unit : % |

An amount has been allowed in the Bill of Quantities under sub item (a) to cover the cost of administrating breakdown calls logged through the call centre. The call centre will submit to the contractor a monthly invoice for breakdown calls logged and monthly subscription. The Contractor will be responsible for prompt payment of the invoice received from the call centre.

The bid percentage under sub item (b) will be paid to the Contractor on the value of each payment pertaining to the call centre to cover his expenses in this regard.

Payment to the Contractor will only become due upon submission of proof of payment to the call centre.

PSA 8.13	COMPLIANCE WITH OHS ACT AND CONSTRUCTION REGULATIONS 2003

| ................................................................................................................... | Unit : Sum |
| --- | --- |

The bid sum shall include full compensation to the Contractor for compliance with all the requirements of the OHS Act and the Construction Regulations 2003 at all times during the contract, as described in PS 13 of Portion 1 of the Project Specifications.  The successful bidder shall provide the Engineer with a complete breakdown of this bid sum.

This sum will be paid to the Contractor in equal monthly amounts for the entire duration of the contract period.

- ANNEXURE D4:  DRAWINGS

INSTRUCTINS FOR THE PREPARATION, NUMBERING AND ISSUE OF DRAWINGS FOR CIVIL ENGINEERING SERVICES

# INTRODUCTION

The following are the requirements in respect of drawings.  These requirements have to be strictly adhered to.

# DRAWING TITLES

## Drawing titles are to be in accordance with the layout and detail on the Departmental web-site item 11.1 to 11.4.  The Departmental Project Manager shall approve the wording of the title.

## The column above the title is to be used for general notes from the top down and to indicate revisions to the previously issued drawings from the bottom upwards.

## All titles and details of the drawings are to be in English.

# SIZE AND LAYOUT OF DRAWINGS

## Only metric drawing sizes may be used.

## Preference is given to the A1 size of drawing.

## Only one (1) size of drawing is to be used throughout the service unless otherwise approved by the Departmental Project Manager.

## Where any drawing is too large for a single sheet and separate sheets are prepared for survey, report, draft or working drawing purposes, e.g. site plans, a key to the various plans must be prepared to a reduced size showing how the various sheets should be jointed together in order to obtain a composite plan of the entire site (or such other detail as is being depicted).  The key should be included on all drawings forming part of such composite plan.

## The following scales shall be used in the preparation of drawings.  The scales used shall be chosen to ensure clarity of the drawing details. (See Section H for Site Plan Directive for Consultants.)

| Locality / Key Plans: | 1:5,000; 1:10,000; 1:50,000 |
| --- | --- |
| Site layout plans: | 1:200; 1:500; 1:1,000 |
| Longitudinal sections (road): | 1:1,000 horizontal and 1:100 vertical |
| Longitudinal sections (sewerage): | 1:1,000 horizontal and 1:100 vertical |
| Detail drawings: | 1:1; 1:2; 1:5 |
|  | 1:10; 1:20; 1:50 |
|  | 1:100; 1:200 |

# SERVICE NUMBER

A “C” number (see Annexure A of the Consultant's Letter of Appointment) is allocated by the Department to each service and no other number should be used when referring to drawings or documents connected to this service.  An example of a service number would be, say C3365.  This number should be used to number the drawings, specification and/or the Schedule of Quantities.  A specific drawing number would be say C3365/25.

# NUMBERING OF DRAWINGS

## A list of drawings should be provided on the first plan, which should be numbered with the suffix /0.

## The general site plan must be numbered using the suffix /1.

## Drawings must be grouped according to activities with gaps between activities to allow for supplementary drawings.  Consecutive numbering must be employed for each activity, e.g.:

C3365/20 - /24 sewerage

C3365/50 - /57 water supply

C3365/70 - /85 roads

## Where a comprehensive site survey is undertaken the survey drawings must be numbered consecutively using an alphabetical suffix starting with /A, e.g. C3365/A, C3365/B, etc.

## The use of letters of the alphabet, or of sub-numbers, for the numbering of drawings must be avoided, except in the case of a comprehensive survey as stated in 5.4 above.

## Preliminary, Draft and Working Drawings

In order to distinguish between preliminary report drawings, draft working drawings and approved working drawings the following numbering system must be adopted.

### Preliminary report drawings are to be indicated by the addition of the suffix (PREL 1), e.g. C3365/12 (PREL 1).  Should it be necessary to submit revised preliminary report drawings an appropriate note must be made in the NOTES column and the suffix altered to the following sequential number, e.g. C3365/12 (PREL 2).

### Draft working drawings, which are submitted for approval, are to be indicated by the addition of the suffix (DRAFT 1), e.g. C3365/12 (DRAFT 1).  Revisions to these drawings must be indicated in the NOTES column and the suffix altered to the next sequential number, e.g. C3365/12 (DRAFT 2).

### After approval of the draft, working drawings the suffix must be removed from the drawing number and the revision notes removed from the NOTES column.

# LEGEND FOR SERVICES

The symbols, colour codes and line weights depicted in the legend below shall be used for indicating the location of services on the drawings.

# ELECTRONIC FORMAT

## All plans and report books that are submitted must be accompanied by the electronic versions of the information preferably on CD.

## A sub directory must be created for the project based on the plan series number Example: d:\WCS3365\ with sub directories named \plans, \report, \other, underneath.

## A word file named Readme.doc/txt (stored under \other) to be created, containing explanatory notes on the layering, grey scale, naming and other conventions used, to enable a third party to easily amend or print/plot drawings/report book(s).

## Drawing data is to be submitted in CAD vector format only – not to be scanned and be submitted as images.  See also sub paragraph 8.7 for “as-built” drawings.

## The following CAD formats are preferred:

AutoCad (.dwg)

Caddie for Windows (.drw)

Allycad (.drg)

Microstation

Ultimate CAD

Data exchange (.dxf) format will be accepted only if the designer does not have the means to submit the plans in the above formats.

## Drawing data must be stored in the \plans sub directory.

## Electronic Drawings should have meaningful file names related to the drawing number.

## The use of grey scale CAD entities (e.g. lines, etc.) should be avoided – distinction between lines, etc. should be done using different pen widths.  Images used as survey plan background should be printed in grey scale (only slightly lighter than the new CAD data).

## If .tif or other images were used as background (i.e. survey plans, photo mosaics, etc.), the images must be given meaningful names, relating them to the drawing in which they are used.

## All drawings shall be compiled in layers.  Each layer shall consist of one (1) category of drawing information.  The colour code of each layer shall be as the default for each cad system.

# PRINTING AND ISSUE OF DRAWINGS

## Generally, preliminary drawings are to be paper prints, which are bound into the preliminary report.  A full set of paper prints of the draft working drawings must be submitted to the Departmental Project Manager for approval.

## All drawings are to be signed in the appropriate place in the title block, as drawn, designed and checked by each member of your staff responsible for these activities.

## For separate civil contracts reduced drawings will generally be required for tender purposes.  No drawing (or document) may be printed for tender purposes until so instructed by the Departmental Project Manager.  In such cases, construction drawings and documents must be issued in accordance with Clause 13 of GCC 2004 and Clause 13.1 of Contract Data (see Section D of this Manual).

## In the case where other consultants are involved plans must be supplied to the Principal Agent/Lead Consultant as required for co-ordinating purposes.  The printing and issue of drawings is to be kept to the absolute minimum required for the proper and effective co-ordinating with the various members of the design team and administration of the Contract.

## All drawings must be submitted to local authorities or other bodies after the approval of the Departmental Project Manager is obtained.

## On completion of the Contract, a full set of transparencies of appropriation drawings is to be signed and stamped “as-built” and submitted to the Departmental Project Manager.

## “As-built” drawings must also be submitted electronically using the same principles as described in Section 6 above.  The drawing must be submitted in CAD vector format (for use with further extensions of project) as well as a scanned/PDF format (for “as-built” record purposes).  A film copy of the drawing is also to be submitted at the cost of the consultant.

A legible name of the compiler and the date of compilation have to appear on the “as-built” drawings.

# AMENDED DRAWINGS

The procedure to be followed when amending working drawings during the contract period is as follows:

## Revised working drawings shall be numbered using the suffix Rev, e.g. C3365/20 Rev 1, C3365/20 Rev 2 etc.

## All amendments must be clearly dated and numbered so that the nature and time of alteration to previous versions of a drawing may be easily identified.  A brief description of the amendment should be given. Alterations to drawings must be kept to a minimum and variations made by way of site instructions where possible.

## No amendment or supplementary working drawing may be issued for construction without the prior approval of the Departmental Project Manager if:

### alterations to approved layouts or details are involved or if

### additional work is being indicated.

## Such approval of the Departmental Project Manager should, unless prior approval has been granted, be sought telephonically and confirmed in writing if required by the Departmental Project Manager.

## Copies of amended working drawings need not be forwarded to the Departmental Project Manager unless approval of the revision is required in terms of 8.3 above.

# “AS-BUILD” DRAWINGS

See Section C 19 of the Consultant's Letter of Appointment in this regard.

- ANNEXURE D5:  SITE CLEARANCE CERTIFICATE

SITE CLEARANCE CERTIFICATE

Although a site clearance certificate is issued by the Town Planning Section of the Department which confirms that the specific site are suitable for the facilities to be provided on that site based on the initial information available to the Department, it still remains the responsibility of the Consultant to check whether all aspects have been covered.  He must also check whether the findings are correct and complete.

The following items need his specific attention:

- Access to the site

- Has the community been involved?

- The availability of bulk services required including underground water for boreholes if needed.

- Has a site development plan been provided?  Is a surveyor general plan available?

- Is the size and location of the site suitable for the required facilities?

- Geology of the site (dolomite, soil information).

- Environmental impact of facilities.

- Historic value of existing buildings and structures.

- Impact of additional traffic which will be created.

- Hydrological matters, e.g. flood line determinations.

- Water pressure recordings at municipal service connection points, etc

- Relocation of existing services.

- Affected/required way leaves/servitudes/right of ways.

- Adjacent properties affected.

- Topography (contours, structures, trees, etc.)

- Climate.

- ANNEXURE D6:  FORM OF GUARANTEE

- ANNEXURE D7:  PRO FORMA RISK ASSESSMENT REPORT