SECTION E:	CONTRACT ADMINISTRATION, INSPECTION, 					VARIATIONS AND CLOSE-OUT

CONTENTS

Item 			Page

E.1	STAGE 5: CIVIL ENGINEERING PROJECTS:  CONTRACT   ADMINISTRATION AND INSPECTION	4

E.1.1	PROCESS CHART	4

E.1.2	INTRODUCTION	5

E.1.2.1	Contractual claims	5

E.1.3	REFERENCES	6

E.1.4	SITE HANDOVER	6

E.1.5	CONSTRUCTION PROGRAMME	6

E.1.5.1	Schedules of cash flow forecast	6

E.1.6	SITE MEETINGS	7

E.1.7	CONSTRUCTION DOCUMENTATION	8

E.1.7.1	Drawings issued and amended	8

E.1.7.2	Estimates for proposed variations	8

E.1.7.3	Contract instructions	9

E.1.8	FINANCIAL CONTROL REPORTS	9

E.1.9	VALUATIONS FOR PAYMENT CERTIFICATES	10

E.1.10	PRACTICAL COMPLETION AND DEFECTS LIST	10

E.1.10.1	Electrical certificate of compliance	11

E.1.11	BUILDING PROJECTS:  CONTRACT ADMINISTRATION AND CONSTRUCTION MONITORING	11

E.1.11.1	General			11

E.1.11.2	Payment Certificates	11

E.1.12	PROVISION OF SITE STAFF	11

E.1.12.1	General			11

E.1.12.2	Site staff		12

E.1.12.3	Reimbursement of technical support services	12

E.2	VARIATIONS	15

E.2.1	PROCESS CHART	15

E.2.2	INTRODUCTION	15

E.2.3	REFERENCES	16

E.2.4	PROCESS FOR VARIATIONS	16

E.2.4.1	Initiation			16

E.2.4.2	Consultant is made aware of the variation	16

E.2.4.3	Inform the Project Manager	16

E.2.4.4	Site Instruction to the Contractor	17

E.2.4.5	Prepare the Variation Order	17

E.2.4.6	Submit the Variation Order	17

E.2.4.7	Site Instruction	17

E.2.5	RULES			17

E.2.5.1	Site Instructions	17

E.2.5.2	Variation Orders	17

E.2.5.3	Day Works	17

E.2.5.4	Contract Price Adjustment	18

E.2.5.5	Principal Agent/Lead Consultant	18

E.2.6	ISSUING SITE INSTRUCTIONS/VARIATION ORDERS	18

E.2.6.1	Comprehensive Civil Contracts	18

E.2.6.2	Nominated Sub-contract to Building Contract	18

E.2.6.3	Civil Work Included in a Building Contract	18

E.2.7	FINANCIAL CONTROL	18

E.2.8	FORMAT OF VARIATION ORDER	19

E.2.8.1	Standard form	19

E.2.8.2	Motivation	19

E.2.8.3	Essential information	19

E.2.9	VARIATION ORDERS FOR EXTENSION OF TIME	19

E.2.10	FLOW DIAGRAM FOR VARIATIONS	20

E.3	STAGE 6:  CLOSE OUT	21

E.3.1	PROCESS CHART	21

E.3.2	INTRODUCTION	21

E.3.3	REFERENCES	22

E.3.4	COMPLETION CERTIFICATE	22

E.3.5	FINAL APPROVAL CERTIFICATE	22

E.3.6	VALUATIONS FOR FINAL PAYMENT CERTIFICATE	23

E.3.7	RELEASE OF RETENTION MONIES	23

E.3.8	CLOSE-OUT AND CIDB REPORTS	23

E.3.9	“AS-BUILT” DRAWINGS AND DOCUMENTATION	23

E.3.10	FINAL ACCOUNT	24

E.3.11	FINAL PROFESSIONAL FEE ACCOUNT	24

ANNEXURES:  SECTION E	28

1.	ANNEXURE E1:  PRO FORMA SITE MEETINGS MEETING MINUTES	29

2.	ANNEXURE E2:  PAYMENT CERTIFICATES	36

3.	ANNEXURE E3:  EXAMPLE FROM SITE INSTRUCTION BOOK	40

4.	ANNEXURE E4: REPORT ON CHANGES IN EXPENDITURE AND/COMPLETION PERIOD			41

5.	ANNEXURE E5:  GUIDELINES FOR REQUESTING APPOINTMENT OF SITE 
STAFF			43

6.	ANNEXURE E6: DIRECTIVE PERTAINING TO THE HANDLING OF THE CONTRACT COMPLETION REPORT (PRM043civ)	45

7.	ANNEXURE E7: MONTHLY REPORT ON PERFORMANCE OF NDPW APPOINTED CONTRACTOR BY THE CONSULTING ENGINEER (CIDB)	47

- STAGE 5:	CIVIL ENGINEERING PROJECTS:  CONTRACT
		ADMINISTRATION AND INSPECTION

PROCESS CHART

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
| 1. | STAGE 5: CONTRACT ADMINISTRATION AND INSPECTION |  |  |  |  |
| 1.1 | Tender award: |  |  | Department |  |
|  | Site to be handed over to Contractor at a formal site handover meeting | 3.2.5 (1) | E.1.4 | Project Manager |  |
| 1.2 | Site handover: |  |  |  |  |
| 1.2.1 | Hand over of the site to the Contractor | 3.2.5 (2) | E.1.4 | Departmental Project Manager | Contractor, Consultant, User Department |
| 1.2.2 | Issue construction documentation and register drawings issued | 3.2.5 (2), (16), (17) | E.1.4 | Consultant | Project Manager & Contractor |
| 1.3 | Contract administration: |  |  |  |  |
| 1.3.1 | Construction Programme: | 3.2.5 (3) | E.1.5 | Consultant & Contractor | Project Manager |
|  | Schedule of Cash Flow forecast | 3.2.5 (4), (5) | E.1.5.1 | Consultant & Contractor | Project Manager |
|  | Schedule of milestones | 3.2.5 (4), (12) | E.1.5 | Consultant & Contractor | Project Manager |
| 1.3.2 | Appointment of Site Staff | 3.3.3 (2) | E.1.12.2 | Consultant | Project Manager |
| 1.3.3 | Site Diaries for Consultant and Contractor | 3.2.5 (2) | E.1.7.3 | Consultant & Contractor | Project Manager |
| 1.3.4 | Site Instructions | 3.2.5 (3), (8), (13) | E1.7.1 | Consultant | Contractor & Project Manager |
|  |  | (15), (18) | E1.7.2 |  |  |
|  |  | (23) | E1.7.3 |  |  |
| 1.3.5 | Statement for payment claims | 3.2.5 (9), (19) | E.1.9 | Contractor | Project Manager |
| 1.3.6 | Interim monthly Payment Certificates | 3.2.5 (14), (10) | E.1.9 | Consultant | Contractor & Project Manager |
| 1.3.7 | Monthly Progress and Financial reports | 3.2.5 (12) | E.1.8 | Consultant | Project Manager |
| 1.3.8 | Variation Orders | 3.2.5 (6), (11), (23) | E.1.2.1 | Consultant & Contractor | User Department |
|  |  |  | E1.7.2 | Departmental Project Manager |  |
|  |  |  | E.1.9 |  |  |
| 1.3.9 | Monthly progress meetings | 3.2.5 (3), (7), (8) | E.1.6 | Consultant & Contractor | Project Manager |
| 1.3.10 | Inspection of works regularly | 3.2.5 (7), (8), (13), | E.1.10 | Consultant & Contractor | Project Manager & User Department |
|  |  | (15), (21) | E.1.12.1 |  |  |
|  |  |  | E.3.4 |  |  |
|  |  |  | E.3.5 |  |  |
| 1.3.11 | Resolve claims, disputes and dissatisfaction | 3.2.5 (11) | E.1.2.1 | Consultant & Contractor | Project Manager |
| 1.3.12 | Certification of all electrical work | 3.2.5 (22) | E.1.2.1 | Consultant | Competent Electrical Contractor |
|  |  |  | E.1.10.1 |  |  |
| 1.3.13 | Certificate of Practical Completion and Defects List | 3.2.5 (20), (21) | E.1.10 | Consultant, Departmental Project Manager & Contractor |  |
| 1.3.14 | Operating and Maintenance manuals | 3.2.5 (20) | E.3.9 | Consultant & Contractor | User Department |

INTRODUCTION

The Contract Administration and Inspection stage follows the completion of the Documentation and Procurement stage.  On appointment of the successful Tenderer (Contractor) the Departmental Project Manager will advise the Consultant of the date of the Site Handover meeting.  Complete form PRM031civ.

The Consultant will be required to supervise the construction of the works as approved by the Departmental Project Manager.

The Consultant will ensure that the Contractor(s) comply with all the relevant acts and statutory regulations, e.g. National Water Act (Act 36/1998), Occupational Health and Safety Act (Act 85/1993), etc.

The functions of the Consultant in respect of the administration of the Contract and construction monitoring of the works are laid down in principle in the Consultant's Letter of Appointment Section X1.

Contractual claims

Attention is drawn to the fact that certain functions are reserved for the Director General.  Such functions comprise:

Approval of Variation Orders

Extension of the contract period

Release of the guarantee

Application of the penalty (delay report), and

Termination of the contract

Signing of the final account.

It is however the duty of the Consultant to submit reports and recommendations in regarding these matters to the Departmental Project Manager for comment and forwarding to the Office of the Director General.

The Consultant will deal with all minor matters arising on site.  If any major points arise on site, which have significant financial and/or time implications or require decisions in principle, the Consultant must apply for a ruling in writing to the Departmental Project Manager. If it seems likely that the Contractor is not going to complete the Contract on time, he must be warned in terms of the relevant clauses of the Contract Document, and it must be recorded that penalties will be applied should the completion not be in time.

In terms of the Occupational Health and Safety Act (Act 85/1993), an accredited person must certify all electrical work.

REFERENCES

The contract (Consultant's Letter of Appointment)

National Department of Public Works Scope of Civil Engineering Services and Tariff Fees for persons registered in terms of the Civil Engineering profession Act, 2000, (Act No. 46 of 2000)

General Conditions of Contract 2004 (GCC 2004) as amended (DPW-04 JBCC and DPW-05 GCC 2004)

Manual for Project Managers

Conditions of Contract (GCC 2004 or JBCC 2000) DPW-04/05

The Department’s “Preliminaries for Inclusion in Bills of Quantities and Lump Sum Documents Based on the JBCC Series 2000 Documentation

The Department’s “Specification of Materials and Methods to be Used” (PW 371) and/or SABS 1200 (SANS 1200).

SITE HANDOVER

The Departmental Project Manager, on behalf of the Director General, shall conduct the handing over of the site meeting. The Consultant will be responsible for the taking and issuing of the minutes of this meeting only.  See PRM031civ.  The Departmental Project Manager will advise the Consultant on the time and date of the meeting.

The banking details of the contactor must be confirmed at this meeting.

Thereafter the Consultant will be responsible for conducting site meetings and issuing minutes.  At the handing over of the construction site, the Departmental Project Manager will issue three (3) sets of the contract documents and drawings to the Contractor.

CONSTRUCTION PROGRAMME

Immediately upon the site being handed over to the Contractor or as described in the contract documents, the Consultant shall take delivery of a detailed Construction programme from the Contractor taking into account all trades and aspects of the works and allowing for any procedural/contractual requirements.

When the Consultant is satisfied that the programme complies with the standards a copy must be submitted to the Departmental Project Manager for his record.

Schedules of cash flow forecast

Since the Department is required to plan and execute its construction programme within fixed yearly allocation of funds, strict control over expenditure in general and specifically on variations has to be exercised to ensure that:

The annual agreed cash flows allocated are not exceeded.

The Department is under no circumstances placed in the position of having to authorise ex post facto applications regarding additional funds for the completion of a contract.

Consequent changes in the approved requirements, no matter how minor, which may be requested at any stage by officials of the Client/User Department or other members of the design team, at any stage, may only be implemented if they are approved by the Departmental Project Manager.

If the Consultant makes unauthorised alterations on the instructions of other Civil Engineers or a Client/User Department or cause other Civil Engineers to make changes resulting in claims for additional or fruitless expenses, he will be held responsible for the payment of such claims.

The Departmental Project Manager is the authorised local representative of the Director General and as such holds the funds for all contracts and is therefore responsible for overall administration and financial control.  In order to execute financial control over the Contract and preclude unauthorised over-expenditure, it is imperative that a revised completion estimate be submitted to the Departmental Project Manager monthly together with the minutes of site meetings.

The Consultant may be held liable for any unauthorized over-expenditure that may occur.

A graph of actual and cash flow forecast must be attached to the site minutes (see Annexure H).  Also show the Comparison and implications of the projected cash flows on the works reflecting the actual value of the work, i.e. excluding contract price adjustment (CPA) and contingency costs.

SITE MEETINGS

The Consultant, who will act as chairperson, will also convene site meetings and due notice must be given to all who will attend.  Besides the Consultant, those represented at site meetings will be other professional engineers if applicable, the Contractor, the Departmental Project Manager as he may decide, the User Department’s representative or any others concerned with the work. This will be according to the discretion of the chairperson or the Department.

At each site meeting, the Consultant must ascertain from the Contractor whether he requires any drawings, information or decisions to ensure the maintenance of progress of the Contract and to obviate delays.  The Contractor’s reply and, where appropriate, the names of persons who are to take the required action must be recorded in the minutes.

The Departmental Project Manager must be invited to attend all formal site meetings on behalf of the Department.

The site meeting minutes must cover all the relevant items listed in the pro forma agenda for site meetings: Annexure E1.

Every clause in Annexure E1, with its relevant sub-heading, must be included in all minutes.  Where matters have not been fully dealt with, the relevant clauses must contain sufficient information to obviate the necessity of referring back to previous minutes.

Where any item in the minutes calls for further action to be taken, e.g. queries to be dealt with, information to be furnished or work to be executed, the name of the responsible person must be recorded alongside the relevant item in an action column in the right hand margin of the minutes, together with the date of completing such action.

A signed copy of the minutes must be forwarded to the Departmental Project Manager under cover of Annexure E3.  The requirements of the Departmental Project Manager and the User Department must be determined at the first site meeting.

Formal site meetings must be held at least once (1) a month.  Site meeting minutes should be distributed not later than one week after the meeting.

CONSTRUCTION DOCUMENTATION

The Consultant is responsible for the interpretation to the Contractor of the intent of the design and documentation and for the monitoring of quality control of workmanship and materials.  The Consultant’s attention is drawn to his obligations in terms of the most recent Regulations of the Occupational Health and Safety Act (Act 85 of 1993).

The Departmental Project Manager of the Department is responsible for the overall administration and financial control on behalf of the Department. The Consultant will assist him in this regard. All correspondence relating to contract administration must be addressed to the Departmental Project Manager.

Documentation shall be based on the General Conditions of Contract 2004 issued by the SAICE, SABS 1200 (SANS 1200), the Departmental Contract Data (Annexure D2 – latest version) and the documents contained in Annexures - Section B.  Except for the “List of Specifications” in Annexure D2.4, the documents contained in Annexure D2 and the Contract Data may in no circumstances be amended.

Ensure that the CIDB is advised regarding the Contract and the Contractor appointed. Complete the standard form for performance evaluation of the Contractor on a monthly basis and submit it to the Departmental Project Manager.  Submit a copy to CIDB, see Close-out:  Stage 6.

Drawings issued and amended

Apart from the tender drawings issued to the Contractor by the Departmental Project Manager at site handover, the Consultant will be responsible for the issue of all working drawings to the Contractor in terms of General Conditions of Contract.  All drawings must be issued under cover of a Site Instruction and the Consultant must maintain an updated drawing schedule on site at all times indicating date of issue and revision number of drawings issued.  Refer to GCC 2004 Clause 13.

Please refer to Annexure E1 (E1.1.9.1) of this manual in this regard.

All amendments on drawings must be clearly dated and numbered so that the nature and time of alteration to previous versions of a drawing may be easily identified.  A brief description of the amendment should be given.  Alterations to drawings must be kept to a minimum and variations made by way of site instructions where possible.

The procedure to be followed when amending working drawings during the contract period is as follows:

Revised working drawings shall be numbered using the suffix Rev, e.g. C3365/20 
Rev 1, C3365/20 Rev 2, etc

The Consultant retains three (3) contract documents and one (1) set of drawings for contract administration purposes.

Estimates for proposed variations

Requests from representatives of a Client/User Department for changes to the design must be made officially in writing by the Head Office of that Department to the Director General.  The Consultant may not implement any such changes without the written approval of the Departmental Project Manager.

A breakdown of the elements involved with estimates for each element and the total estimated cost must be given.  Refer to PRM039civ.

Confirm that the additional work will be done at existing rates in the Bill of Quantities if this is the case. If not, explain how the estimate has been established, e.g. rates to be negotiated but based on existing rates, calling for quotations via the Contractor. If the estimate is based on quotation submitted by the Contractor, confirmation is required that the price is considered fair and reasonable.

All variations to the Contract must be made in writing on the Site Instructions form 
(PW320, Annexure E3), and confirmed by Variation Orders in the cases described below.

The Consultant must give due consideration to any suggestions in respect of the execution of the Contract, which may be made by the Departmental Project Manager.  In the event that the Consultant does not agree with such suggestion, the Consultant must request that the matter be referred to the Departmental Project Manager’s superior for a decision.

Furnish the Departmental Project Manager with draft Variation Orders on the Department’s prescribed Variation Order (VO) form for approval by the Department.

Contract instructions

All site instructions must be written in the Site Instruction Book provided by the Departmental Project Manager.  Furnish the Departmental Project Manager with copies of all Site Instructions.  The Consultant and the Contractor must sign all Site Instructions.  The Consultant may only issue Site Instructions.  Facts and circumstances shall also be recorded in the official Site Instruction Book. Refer to GCC 2004 Clause 48.3.1 to 48.3.6.

The Consultant must ensure that a Site Diary is available on site and is kept up to date. The Site Diary shall have records of rain, which shall include the date, time, duration, and amount, as well as all other details that may be required when lodging a claim. It is encouraged that dated photographs of the site be kept.  The Consultant and the Contractor may have separate site diaries.

The Contractor will, if ordered by the Consultant in writing, search for the cause of any defect. If such defect shall be one for which the Contractor is not liable under the Contract, the cost of the work carried out by the Contractor in defect-searching will be paid to him, but if the Contractor is liable for the defect, the cost of such work will be borne by the Contractor.

FINANCIAL CONTROL REPORTS

To control the strict adherence to the time schedule required for compliance with the documentation programme laid down in terms of the Consultant's Letter of Appointment or as provided at the briefing, the Consultant is required to render progress reports to the Department throughout and up to the last working day of each month on the form PRM014/6civ.

Monthly reports must accurately reflect the financial status of the Contract and must include detailed reports on payments and anything else that may influence the contract value.

Financial reports will be prepared by the Consultant/other Engineers and submitted to the Departmental Project Manager on a monthly basis.

In order to execute financial control over the Contract and preclude unauthorised over-expenditure, it is imperative that a revised completion estimate be submitted to the Departmental Project Manager monthly.

In completing the form, special attention must be drawn to any delays or changes in the estimated cost of the service and the cause thereof.

The Contractor is to be warned of the implication of delays in time and in writing.

See Financial Report Pro-forma on PRM036civ.

When the various stages of the Contract are approved, an estimate of cost will concurrently be approved and the Consultant is required to adhere strictly to this cost limit, subject to escalation in costs or such deviation as approved by the Departmental Project Manager.  Such estimates shall include Preliminary and General costs and an estimate of Contract Price Adjustment, but exclude any amounts for professional fees, travelling, supervision, etc. for which the Department will make its own allowance.

Financial control is done on a dual basis, i.e. construction (execution) costs and professional fees, which include travelling cost, supervision, etc.

VALUATIONS FOR PAYMENT CERTIFICATES

Payment Certificates must be submitted to the Departmental Project Manager on a date as agreed to by the Departmental Project Manager.

In the event where the civil work is executed as a nominated sub-contract to a Building Contract the Consultant will certify the certificates of the sub-contractor, but these will be further processed by the Quantity Surveyor appointed for the main Contract.

In the case of comprehensive Building Contract, the Quantity Surveyor will do all measurements.  The Consultant will only be responsible for certifying the quality of the work, as and when appropriate/required.

Monthly payment certificates for Civil Engineering Services must be based on an accurate assessment of the work completed up to the time of measurement.

The quantities of work completed must be filled in on a blank schedule of quantities and valued at contract rates and prices.

The Schedule of Quantities must indicate the quantity of work scheduled in the contract documents and the quantity of work measured to date as well as the percentage completion of each item.  A separate schedule must be made for measurement of work executed against Variation Orders.  The total for each section of the Schedule of Quantities must be carried to a summary sheet.

The Departmental Project Manager will arrange for payment to be made within twenty one (21) days of submission of the certificate to his office. The Consultant shall ascertain and determine the value of the works.  The Contractor shall measure the work executed during each month and the materials on site and will deliver a supporting statement with his monthly statement to the Consultant, showing the said measurements and the relevant amounts already paid for or payable by him for such materials and all other particulars required by the Consultant.  Refer to GCC 2004, Clauses 44.2 and 49.1.

In the event where work has been done as day work where work has been done as day work, an audited statement regarding the wages paid to the relevant employees as well as time sheets and invoices for all materials used must be included in the valuation of payment.

All the work shall be measured in accordance with the provisions of the pricing data.  Refer to GCC 2004 Clause 44.5.

PRACTICAL COMPLETION AND DEFECTS LIST

Although the defects liability period (maintenance period) on a building contract is normally three (3) months, the civil portion will be subject to a defects liability period of twelve (12) months.

As soon as the works have reached a stage that allows their use for their intended purpose without danger or undue inconvenience, the Consultant must arrange for a joint inspection of the works with the Contractor and the Departmental Project Manager for a joint inspection of the Works.  The Consultant must issue a list to the Contractor, stating the work to be completed in order to justify the issue of a Certificate of Practical Completion.  As soon as the work on this list is completed, a Certificate of Practical Completion must be issued.

Refer to form PRM041/1civ.

After the Contractor has received the Certificate of Practical Completion a further list of work to be completed within a specified time frame, to justify the issue of a Certificate of Completion must be handed to the Contractor.  The Consultant must arrange with the Contractor and the Departmental Project Manager for a joint inspection of the works. If it is concluded at the inspection that the works are essentially completed, the Consultant will advise the Departmental Project Manager in writing, including a list of defects and of work still to be completed in the defects liability period.  The Certificate of Completion must then be issued. Refer to form PRM041/2civ.

The Departmental Project Manager will advise the Contractor and the Department’s Head Office accordingly and arrange for the release of Guarantees.  The Consultant shall immediately proceed with the preparation of the draft Final account on PRM044civ and submit written recommendations on delays as set out on Annexure E3.

Electrical certificate of compliance

In terms of the Electrical Installation Regulations of the Occupational Health and Safety Act (Act 85 of 1993), an Electrical Certificate of Compliance shall be issued.

The Contractor must submit Electrical Certificate of Compliance in order to include it in the Final account.

BUILDING PROJECTS:  CONTRACT ADMINISTRATION AND CONSTRUCTION MONITORING

General

Where the civil work is executed as a direct or nominated sub-contract to a Building Contract the Consultant will assist the other members of the professional team in the above duties.

Payment Certificates

Where the civil work is executed as a nominated sub-contract to a Building Contract the Consultant will certify the certificates of the sub-contractor but the Quantity Surveyor appointed for the main Contract will further process these.

In the case of a comprehensive Building Contract all measurements will be done by the Quantity Surveyor.  The Civil Engineer will only be responsible for certifying the quality of the work, as and when appropriate/required.

PROVISION OF SITE STAFF

General

Should the Department requires the provision of site staff for construction monitoring from the consulting firm, the Consultant will appoint such competent site staff to the satisfaction of the Department as may be necessary for the efficient checking of setting out, verification of the construction to the design, testing of the construction for conformance with specifications, day-to-day inspection of the construction of the works, measuring up of the works on site, and agreeing to the quantities with the Contractor's representatives.

The staff appointed can either be full-time or part-time.  The category of staff needed by the Department must be clarified with the Departmental Project Manager.

The Consultant shall submit a recommendation for the appointment of Site Staff on forms PRM033/1-4.  In completing the application refer to the relevant clauses of the Consultant's Letter of Appointment.

The Consultant will submit applications of the personnel structure and details of the staff on the prescribed forms for approval by the Department together with a detailed breakdown of their remuneration packages, which are to be certified by an external auditor (forms PRM033/1-4).

The Consultant shall re-submit the complete application for the salary increase of Site Staff for approval by the Department, i.e. form PRM033/1-4.

The Consultant’s Representative, and his appointment to undertake the construction monitoring, shall be approved by the Department.  His appointment will not relieve the Consultant of any of the obligations entrusted to him.

Site staff

The actual costs of Site Staff provided by the Consultant will be reimbursable by the Department as per Section X2 of the Consultant's Letter of Appointment.

plus

All other direct costs and expenses as mutually agreed between the Consultant and the Department will be reimbursable by the Department as per Section C of the Consultant's Letter of Appointment.

Reimbursement of technical support services

The Consultant shall, if and when required by the Department to do so, provide the necessary equipment for a suitable Site Laboratory and Survey Office to provide acceptance control as mutually agreed beforehand between the Department and the Consultant.  The costs of providing such services shall be agreed between the Departmental Project Manager and the Consultant.

For the use of Specialist Services, three (3) quotations for these services must be obtained and submitted to the Departmental Project Manager for approval.

The Contractor shall provide the Laboratory buildings, Survey Office and the fixed facilities needed, which are necessary for the construction monitoring of the works, for the use of the Consultant at the cost of the Department.  The type and extent of the buildings and facilities provided shall depend on the nature of the particular Contract and agreed beforehand between the Departmental Project Manager and the Consultant.

Geotechnical and drilling investigation costs are also reimbursable as specified above.  The interpretation shall however be deemed to be inclusive in the Civil Engineering fees, unless specifically approved otherwise by the Department.

VARIATIONS

Refer to GCC 2004 Clauses 36 and 37

PROCESS CHART

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
| 1. | Request variation of works: | 3.2.5.1 | E.2.1 to E.2.4.3 | Consultant | End user / Department |
|  | a) Initiation |  |  |  |  |
|  | b) Consultant is made aware |  |  |  |  |
|  | c) Inform Project Manager in principal |  |  |  |  |
| 2. | Variation of works: | 3.2.5.1 | E.2.5 PRM037civ | Consultant | Department |
|  | a) Site Instruction to Contractor |  |  |  |  |
|  | b) With specification and BoQ |  |  |  |  |
|  | c) Pricing from Contractor on BoQ including base month & substantiation of prices |  |  |  |  |
| 3. | Compile documentation: | 3.2.5.1 | E.2.5 | Consultant |  |
|  | Prepare the Variation Order with contractor's price including the motivation for variation PRM037civ (also for Day Work) |  |  |  |  |
| 4. | Submit documentation: | 3.2.5.1 | E.2.6 PRM039 | Consultant | Department |
|  | a) Submit VO to Project Manager |  |  |  |  |
|  | b) Apply for additional funds even if funds are available and add list of savings if funds are available |  |  |  |  |
| 5. | Variation approved: | 3.2.5.1 | E.2.4.7 E.2.7 | Consultant |  |
|  | Issue Site Instruction |  |  |  |  |

INTRODUCTION

Variations from the original contract bill of quantities stem mainly from changes to Client Department requirements, instructions of the Department, bad design or unexpected site or other environmental situations.  These variations can be of a minor nature, which can be rectified within the project scope or of a major nature, requiring Departmental authorisation.

Every precaution must be taken to minimise variations to the contract.  The Consultant must ensure that all possible work, which is necessary to complete the project according to the required standards, is detailed and scheduled in the bill of quantities and to ensure that the anticipated work is covered by the budget for the project.  No variations due to bad design or work that could have been foreseen are allowed.

REFERENCES

General Conditions of Contract 2004 (GCC 2004) as amended (DPW-04 EC JBCC and DPW-05 EC GCC 2004),

DPW-05: EC (DPW-05_(JBCC),

Manual For Project Managers,

PRM-forms referring to variations:  GCC 2004: Clause 36 and 37

| DPW form No. | PRM-No. | Description |
| --- | --- | --- |
| PW1526 | PRM034civ | Progress Payment |
| PW1525 | (PRM034civ/1) | Progress Payment |
| PW32 |  | Site Instruction |
| PW778(2)E | PRM037civ/3 | Variation Order (VO-form - electronic format) |
| PW778(1)E | PRM037civ/2 | Variation Order: Motivation |
|  | PRM036civ/1 | Contract status report |
|  | PRM036civ | Financial report with PRM039 |
|  | Annexure E2 | Application for additional funds |
|  | Annexure E3 | Application for authorisation of a contract variation exceeding the delegation limits of the adjudicated bid value |
|  | Annexure E4 | Application for additional funds |
|  | PRM039civ/1 | Application for additional funds, contractor |
|  | PRM040civ | Application for extension of time |

PROCESS FOR VARIATIONS

Initiation

Variations are normally initiated by a request from the Client/User Department, the Project Manager, changes to designs by other disciplines or as a result of bad design work or incomplete bills of quantities by the Consultant.

Consultant is made aware of the variation

When the Consultant becomes aware of any variation to the original design or quality or quantity of work he must act immediately.

Inform the Project Manager

The Consultant must inform the Departmental Project Manager immediately of a potential variation and the motivation for the variation unless the instruction was received from the Departmental Project Manager himself.  If the variation was initiated by the User Department or the Client the Consultant must also add the motivation for the variation for record purposes.

Site Instruction to the Contractor

The next step for the Consultant is to make the necessary design change, compile a specification and a bill of quantities for the specific variation.

Issue a Site Instruction requesting the Contractor to price the bill of quantities substantiating his prices and stating the base month for on which his prices are based.

Prepare the Variation Order

Prepare the variation order PRM037civ including the contractor’s price for the work

Submit the application for additional funds, form PRM039civ, even if funds are available.  Add the list of foreseen savings.

Submit the Variation Order

Submit the Variation Order to the Departmental Project Manager for final approval.

Site Instruction

Issue Site Instruction to the Contractor for the execution of the Variation Order.

RULES

Only in cases where totally unforeseen work is encountered or where the Client requires changes to the original design if cleared with the Client previously will variations be allowed according to the following rules:

Site Instructions

All variations to the Contract must be made in writing on the Site Instructions Form (form PW320, Annexure E5), and in the cases described below confirmed by variation orders.

Variation Orders

Additional work that cannot be done at contract rates (non-scheduled items), provisional and prime cost sums and extensions of the contract completion date, must be covered by a variation order.  Whenever possible acceptable rates are to be negotiated with the Contractor and approved by the Department before the work is put in hand.  A separate section shall be provided for measurement of this work.

A variation order is not required for additional work, resulting from a variation in quantities, carried out at contract rates (scheduled items) provided that any increase in the Contract Sum must be approved by the Departmental Project Manager before the work is put in hand.

Variation orders must be obtained from the Department for all work that is outside the scope of Works as defined in the Contract, even if contract rates can be used for this work.

A variation order must be applied for and approved by the Department for all Extension of Time claims related to additional work or variation orders outside the Scope of Work as defined in the Contract.

Day Works

In general work must not be done as day works unless this is unavoidable and can be regarded as an emergency.  Work paid against day works must be accompanied by day work sheets certified by both the Consultant and the Departmental Project Manager.

Work carried out on a day work basis must be covered by a variation order including the estimated cost of the work. (Motivation and Variation Order form PRM037civ/2-3).

Contract Price Adjustment

When new rates are negotiated these must be based on scheduled rates and/or the prices and wages ruling at the time of tender.  If such prices are unobtainable, rates must be based on the time of negotiation and de-escalated to the time of tender.  Such adjusted rates will be accepted as rates that would have ruled at the time of tender.  Negotiated rates must be certified by the Consultant as being fair and reasonable and recommended for acceptance.

Principal Agent/Lead Consultant

In contracts where the Civil Engineering Consultant is not the Principal Agent/Lead Consultant, the procedure laid down by the Principal Agent/Lead Consultant must be followed.

ISSUING SITE INSTRUCTIONS/VARIATION ORDERS

Comprehensive Civil Contracts

Ensure that all site instructions are entered in the site instruction book provided by the Departmental Project Manager and furnish the Departmental Project Manager with copies of all site instructions.  The Consultant and the Contractor must sign all site instructions.  The Consultant may only issue site instructions.  Facts and circumstances referred to in Sub clause 48.3.1 to 48.3.6 of GCC 2004 shall also be recorded in the official site instruction book.

Furnish the Departmental Project Manager with draft variation orders on the Department’s prescribed form for approval by the Department (PRM037civ).

Nominated Sub-contract to Building Contract

Where civil work is carried out as a nominated sub-contract to the building contract the Civil Engineering Consultant shall submit a draft variation order (where necessary) for any changes to the civil work to the Principal Agent/Lead Consultant for further processing.

Civil Work Included in a Building Contract

In this case, the Principal Agent/Lead Consultant will be responsible for the preparation of all variation orders.  The Civil Engineering Consultant shall however assist him where civil engineering matters are concerned.

FINANCIAL CONTROL

Since the Department is required to plan and execute its construction programme within fixed yearly allocation of funds, strict control over expenditure in general and specifically on variations must be exercised to ensure that:

the annual agreed cash flows allocated are not exceeded;

the Department is on no account placed in the position of having to authorise ex post facto applications for additional funds for the completion of a contract.

Consequently changes in the approved requirements, no matter how minor, which may be requested at any stage by officials of the Client/User Department or other members of the design team may only be implemented if they are approved by the Project Manager.

The consultant shall include all information on approved and proposed variations in the financial reports in the prescribed formats on form PRM036civ.

| Note: | If the Civil Engineering Consultant makes unauthorised alterations on the instructions of other consultants or a Client/User Department or cause other consultants to make changes resulting in claims for additional or fruitless expenses, he will be held responsible for the payment of such claims. |
| --- | --- |

FORMAT OF VARIATION ORDER

Standard form

Draft variation orders must be submitted to the Departmental Project Manager or where civil work is included in the building contract to the Principal Agent/Lead Consultant on the standard Departmental variation order forms available from the Department. See Annexure G:  Variation Forms (PRM037civ).

Motivation

Each variation order must be prepared timeously and be accompanied by a full motivation, specification for the work and priced bill of quantities for approval by the Department.  Wherever practical such motivation must be submitted on a variation order form bearing the same number as the variation order.

Essential information

Where applicable the following information must be contained in each variation order:

Negotiated rates with provisional quantities and the estimated total extra cost or saving. An endorsement to the effect that rates have been de-escalated to the month prior to the closing of tenders.

Variation orders must be itemised if possible.

Except in the case of an extension of time, motivations accompanying variation orders must contain the following:

A statement that rates are fair and reasonable.

A statement as to whether funds are available to meet the cost of the Variation Order or not.

A statement as to whether fruitless expenditure is involved.

VARIATION ORDERS FOR EXTENSION OF TIME

No Contract Price Adjustment may be paid for an extended contract period, other than that provided for in Clause 3 of the Contract Price Adjustment Schedule in the GCC 2004, until the Variation Order covering the extension of time has been approved by the Department.

Variation order for an extension of time as a result of abnormal rainfall in terms of 
Clause 47.5 of Contract Data (where applicable) must only be submitted after practical completion has been certified, at which stage the algebraic extension of time can be calculated.

An extension of time will only be considered where the Contractor has been delayed in terms of the Contract and has submitted a claim in writing in terms of the General Conditions of Contract (e.g. Clause 48 of GCC 2004).  Delays in the supply of materials or non-performance of sub-contractors will not be considered reason for granting an extension of time.  However, such delays may be taken into consideration when the Department considers the imposition of penalties for late completion.

| Note: | The Consultant must process variation orders expeditiously before the work involved is executed. |
| --- | --- |

FLOW DIAGRAM FOR VARIATIONS

STAGE 6:  CLOSE-OUT

PROCESS CHART

| No. | Task / Event / Activity / Milestone | Reference |  | Responsibility | Other Role Players |
| --- | --- | --- | --- | --- | --- |
|  |  | DPW Fees Guideline | Manual |  |  |
| 3. | STAGE 6: CLOSE-OUT |  |  |  |  |
| 3.1 | Inspect and verify rectification of defects | 3.2.6 (1) |  | Consultant | Contractor |
| 3.2 | Contract documentation and drawings: |  | E.3.2 |  |  |
|  | Operating and Maintenance manuals | 3.2.6 (3) | E.3.9 | Consultant & Contractor |  |
|  | "As-built" drawings | 3.2.6 (4) | E.3.9 | Consultant & Contractor |  |
|  | Close-out report | 3.2.6 (5) | E.3.8 | Consultant |  |
|  | CIDB report | 3.2.6 (5) | E.3.8 | Consultant | Department |
| 3.3 | Certificate of Completion |  | E.3.4 | Consultant, Contractor & Project Manager | User Department |
|  | Liability period start | 3.2.6 (1) | E.3.4 E.3.5 E.3.6 | Contractor |  |
|  | Retention reduced | 3.2.6 (2) | E.3.7 | Consultant | Department |
| 3.4 | Liability period expired: |  |  |  |  |
|  | Final Approval Certificate | 3.2.6 (2) | E.3.5 | Consultant & Project Manager | User Department |
|  | Final Statement for payment | 3.2.6 (5) | E.3.6 | Contractor | Consultant / Department |
|  | Submit Final Account | 3.2.6 (5) | E.3.10 | Consultant | Department |
|  | Final Payment | 3.2.6 (5) | E.3.6 | Project Manager | Department / Contractor |
|  | Final Professional Fee Account | 3.2.6 (5) | E.3.11 | Consultant / Project Manager | Department |

INTRODUCTION

This stage is defined as the fulfilment and completion of the contract close-out. It includes the necessary documentation to facilitate effective completion, the handover of the contract, follows the completion of the construction works and includes the guarantee and defects completion period.

This stage includes the following actions to be performed by the Consultant:

Inspect and verify the rectification of defects

Issue a Certificate of Completion when all defects were rectified – works completed.  (defects liability period starts)

Agree with Contractor on final quantities

Issue final Payment Certificates

Release half of the retention money

Submit reports

Submit “as-built” drawings and documentation

Submit Final Account

Issue Final Approval Certificate after defects liability period

Release all retention money

Submit final professional fee account.

REFERENCES

The Contract (Letter of appointment)

National Department of Public Works Scope of Engineering Services and Tariff Fees for persons registered in terms of the Engineering profession Act, 2000, (Act No. 46 of 2000)

General Conditions of Contract 2004 (GCC 2004) (DPW-05_GCC2004)

DPW-04_JBCC Contract Data: Principal Building Agreement

The Department’s “JBCC_PBA_Preliminaries_(QS 003)_Jun_2008” (QS 003)

The Department’s “Specification of Materials and Methods to be Used” (PW371) and/or SABS 1200 (SANS 1200), Manual for Project Managers.

COMPLETION CERTIFICATE

After proper inspection of the works by the Consultant accompanied by the Departmental Project Manager (DPM), the DPM arrange for the handing over of the Contract.

If it is concluded at the inspection that the works are essentially completed, the Consultant will advise the Departmental Project Manager in writing, including a list of defects and of work still to be completed in the defects liability period.  The Certificate of Completion must then be issued.  Refer to form PRM041civ/2.  The Departmental Project Manager will advise the Contractor and the Department’s Head Office accordingly and arrange for the release of Guarantees.  The Contract Guarantee and Warranties will be released to the Guarantor within fourteen (14) days after the issuing of the Completion Certificate.  Refer to GCC 2004 Clause 51.4.

The Contractor will clear the site by the end of the Contract period by removing construction equipment, surplus material, site establishment buildings and temporary structures and leave the site clean and safe.

Possession of the site reverts back to the Department (Employer) after final completion and insurance of the works shall only cease at the end of the Contract.

FINAL APPROVAL CERTIFICATE

The Consultant and the Departmental Project Manager shall take final delivery after a joint inspection at the end of the Defects Liability Period, subject to all defects having been rectified.  Refer to GCC 2004 Clause 52.1.

The Consultant must issue the Final Approval Certificate (refer to form PRM046civ), and confirm this in writing to the Departmental Project Manager, who will inform the Contractor and the  Department’s Head Office accordingly and arrange for the release of the final retention.

VALUATIONS FOR FINAL PAYMENT CERTIFICATE

The Final Payment Certificates must be submitted to the Departmental Project Manager for final payment.

Submit Payment Certificates prepared in accordance with Annexure E2 to the Departmental Project Manager.

Where the civil work is executed as a nominated sub-contract to a Building Contract, the Civil Engineer will certify the certificates of the Contractor, and the Quantity Surveyor appointed for the main Contract will process it.

In the case of comprehensive Building Contract the Quantity Surveyor will do all measurements.  The Civil Engineer will only be responsible for certifying the quality of the work, as and when appropriate/required.

The Final Payment Certificates for Civil Engineering Services must be based on an accurate assessment of the work completed at the end of the defects liability period.

The quantities of work completed must be filled in on a blank schedule of quantities and valued at contract rates and prices.

The Schedule of Quantities must show the quantity of work scheduled in the Contract Documents and the quantity of work measured to date as well as the percentage completion of each item.  A separate schedule must be made for measurement of work executed against Variation Orders.  The total for each section of the Schedule of Quantities must be carried to a summary sheet.

The Departmental Project Manager will arrange for payment to be made within twenty one (21) days of submission of the certificate to his office.

The Consultant shall ascertain and determine the final value of the works. Refer to GCC 2004, Clause 44.2.

At this stage, all payments to the Contractor should have been made accept for the retention moneys and all penalties subtracted from the previous accounts.

RELEASE OF RETENTION MONIES

The Consultant must arrange with the Departmental Project Manager to reduce the retention to half, upon issuing of the certificate of completion.

The second part of the retention will only be released upon issuing of the final approval certificate.

CLOSE-OUT AND CIDB REPORTS

On Completion of the works, the Consultant shall submit a Completion Report/Close-out Report to the Department in the format of PRM046.

The Consultant shall also submit his Contractor Performance Evaluation Report to the CIDB on the prescribed format.

On completion of the Contract, the Departmental Project Manager must be furnished with written recommendations regarding the imposition of penalties on form PRM043/1-5civ Contract Completion Report/Close-out Report.

“AS-BUILT” DRAWINGS AND DOCUMENTATION

On completion of the Contract, the Consultant must submit full set of transparencies (film) of appropriation drawings, which is signed and stamped “as-built” to the Departmental Project Manager within three (3) months after Completion, as per Item 8 of Annexure D4.  A certificate must accompany the drawings, confirming that these drawings are an exact indication of the situation on site of the work completed. “as-built” drawings are submitted at the cost of the Consultant.

A legible name of the compiler, his/her signature and the date has to appear on the “as-built” drawings.

“As-built” drawings must be submitted in electronic format.  The drawing must be submitted in CAD vector format (for use with further extensions of the project) as well as a scanned/PDF format for “as-built” record purposes.  See Annexure D4 for “as-built” drawings.

The Consultant must facilitate the submission of appropriation Operating and Maintenance manuals to the Departmental Project Manager.  Refer to Clause 13.8 of Contract Data, and the relevant National Department of Public Works: Scope of Engineering Services and Tariff of Fees for Registered Professionals applicable to the specific appointment. See the relevant Consultant's Letter of Appointment in this regard.

Three (3) copies of any Operating and Maintenance manual are required.

FINAL ACCOUNT

The Consultant is responsible for the compiling of the Final Account prepared in accordance with form PRM044civ and to submit it to the Departmental Project Manager for approval, certified on form PRM045. The Departmental Project Manager will arrange for signature of the final account by the Contractor.

The Consultant shall immediately proceed with the preparation of the final account (PRM044civ) and submit written recommendations on delays in accordance with paragraph E.1.8.  The final account must be submitted to the Department within three (3) months after Completion.

The final account must be certified and forwarded to the Departmental Project Manager within three (3) weeks after receiving the official decision regarding imposition of penalties.

Where work has been done as day work, an audited statement regarding the wages paid to the relevant employees as well as time sheets and invoices for all materials used must accompany the final account and be certified by the Consultant.

FINAL PROFESSIONAL FEE ACCOUNT

The Consultant shall submit the final professional fee account for payment as soon as the Final Account has been approved by the Department of Public Works.

ANNEXURES:  SECTION E

CONTENTS

Item			Page

ANNEXURES:  SECTION E	28

1.	ANNEXURE E1:  PRO FORMA SITE MEETINGS MEETING MINUTES	29

2.	ANNEXURE E2:  PAYMENT CERTIFICATES	36

3.	ANNEXURE E3:  EXAMPLE FROM SITE INSTRUCTION BOOK	40

4.	ANNEXURE E4: REPORT ON CHANGES IN EXPENDITURE AND/COMPLETION  PERIOD			41

5.	ANNEXURE E5:  GUIDELINES FOR REQUESTING APPOINTMENT OF SITE 
STAFF  			43

6.	ANNEXURE E6: DIRECTIVE PERTAINING TO THE HANDLING OF THE 
CONTRACT COMPLETION REPORT (PRM043civ)	45

7.	ANNEXURE E7: MONTHLY REPORT ON PERFORMANCE OF NDPW APPOINTED CONTRACTOR BY THE CONSULTING ENGINEER (CIDB)	47

ANNEXURE E1:  PRO FORMA SITE MEETINGS MEETING MINUTES

| DEPARTMENT OF PUBLIC WORKS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type PROJECT TYPE here TYPE PROJECT NAME HERE I.E. "BLOEMFONTEIN PRISON" Type in relevant STAGE of project WCS No. ______ |  |  |  |  |  |
| MINUTES: PROGRESS MEETING No. TYPE IN NUMBER OF MEETING XX=" " |  |  |  |  |  |
| MEETING DETAILS VENUE: ___________________________ DATE : ___________________________ TIME : __________________________ |  | CONTRACT DETAILS TENDER No. : ___________________ DPW REF NO : ___________________ CONTRACTOR : ___________________ CONSULTANT : ___________________ PRINCIPAL AGENT : ____________________ |  |  |  |
| CONTRACT FINANCIAL INFORMATION (Payment Certificate No: ) |  | CONTRACT TIME INFORMATION |  |  |  |
| CONTRACT AMOUNT (Incl. VAT) : ______________ VALUE OF WORK (Excl VAT) : ______________ ESTIMATE VARIATION : ______________ ESTIMATE CPA : ______________ ESTIMATED FINAL COST (Incl. VAT): ______________ PAYMENT TO DATE (Subtotal A) : ______________ ESTIMATED PENALTIES : ______________ % COST : ______________ |  | COMMENCEMENT DATE : _______________ GUARANTEE RECEIVED : _______________ COMPLETION DATE : _______________ CONTRACT PERIOD : _______________ TIME EXTENSION APPLICATION : _______________ ESTIMATED COMPLETION DATE : ________________ % TIME EXPIRED : _______________ |  |  |  |
| # XX.1 ATTENDANCE REGISTER |  |  |  |  |  |
| # XX.1.1 Present |  |  |  |  |  |
| ###### Name | ###### Representing |  | ###### Tel/Cell No. |  | ###### Fax No. |
| # XX.1.2 Apologies |  |  |  |  |  |
| ###### Name | ###### Representing |  | ###### Tel/Cell No. |  | ###### Fax No. |

SEE ITEM XX.20 THE NEXT PROGRESS MEETING WILL BE HELD AT: .................... VENUE: ...................... ON: ....................., 20.. AT ..h.. ATTACHED : SCHEDULE OF MEETINGS AND DISTRIBUTION LIST

| No | ITEM AND DESCRIPTION |  |  |  |  |  |  |  |  | ACTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| XX.2 | WELCOME AND PURPOSE |  |  |  |  |  |  |  |  |  |
|  | - The purpose of the Progress Meeting No. XX (Regular Site Meeting PSA 5.9), would further be to focus on the contract specific aspects such as: Performance and quality of work - Problems Payments - Scorecards Communication procedures Operational restrictions Claims Potential variation orders Client concerns and follow-on contract scope Site visit after the meeting |  |  |  |  |  |  |  |  |  |
| XX.3 | AGENDA |  |  |  |  |  |  |  |  |  |
|  | The example agenda can be used for the first meeting and thereafter the Minutes of the previous meeting, is to be used as the agenda. |  |  |  |  |  |  |  |  |  |
| XX.4 | MATTERS ARISING FROM PREVIOUS MINUTES |  |  |  |  |  |  |  |  |  |
|  | Matters arising from the previous Minutes will be addressed under the appropriate items. |  |  |  |  |  |  |  |  |  |
| XX.5 | APPROVAL OF THE MINUTES OF MEETING No. 22 |  |  |  |  |  |  |  |  |  |
|  | The original signed Minutes are kept on site. |  |  |  |  |  |  |  |  |  |
|  | The Minutes of Progress Meeting No. XX(-1) was approved and signed at the end of the meeting. |  |  |  |  |  |  |  |  |  |
| XX.6 | SUB-CONTRACTORS |  |  |  |  |  |  |  |  |  |
| XX.6.1 | Approved sub-contractors must be listed here. |  |  |  |  |  |  |  |  |  |
| XX.6.2 | Sub-contractors including ABE’s are to be dealt with under this heading. |  |  |  |  |  |  |  |  |  |
| XX.7 | COMMUNICATION |  |  |  |  |  |  |  |  |  |
|  | Discuss general communication issues |  |  |  |  |  |  |  |  |  |
| XX.7.1 | CO-OPERATION BETWEEN PARTIES |  |  |  |  |  |  |  |  |  |
|  | The Employer expects the engineer’s representative and the site agent to work in close co-operation with one another in terms of the daily running of the contract and differences are to be lodged timeously with the Engineer in order to prevent the development of claim situations. |  |  |  |  |  |  |  |  |  |
| XX.8 | PROGRAMME AND PROGRESS |  |  |  |  |  |  |  |  |  |
|  | The progress is determined by assessing the reaching of the milestones set as targets at the previous meeting: |  |  |  |  |  |  |  |  |  |
| XX.8.1 | Programme |  |  |  |  |  |  |  |  |  |
|  | Only items which may lead to a change in the project programme must be listed here. |  |  |  |  |  |  |  |  |  |
| XX.8.1.1 | Planning (Work still to be completed ) |  |  |  |  |  |  |  |  |  |
|  | - The list serves as a data base for the defects and future planning. |  |  |  |  |  |  |  |  |  |
|  | No | Description |  |  | Type |  | Report Date |  | Repair Date |  |
| XX.9 | BORROW PITS & SIMILAR (if applicable) |  |  |  |  |  |  |  |  |  |
| XX.9.1 | Strict control regarding excavations and final finishing of the areas is to be exercised at the borrow pits. |  |  |  |  |  |  |  |  |  |
| XX.9.2 | All dealings etc. shall be recorded here. |  |  |  |  |  |  |  |  |  |
| XX.10 | LOCAL AUTHORITIES, COMMUNITY AND LANDOWNERS |  |  |  |  |  |  |  |  |  |
| XX.10.1 | Any dealings or negotiations shall be recorded here. |  |  |  |  |  |  |  |  |  |
| XX.11 | CONTRACT DRAWINGS |  |  |  |  |  |  |  |  |  |
| XX.11.1 | New Drawings and Amended Drawings |  |  |  |  |  |  |  |  |  |
|  | All new drawings issued during the contract period will be listed under this item and will be issued with a Site Instruction. |  |  |  |  |  |  |  |  |  |
|  | Drawing Amendments |  |  |  |  |  |  |  |  |  |
| XX.12 | MATERIAL DESIGNS, SUBMISSIONS AND APPROVALS |  |  |  |  |  |  |  |  |  |
|  | Borrow pits and Gravels |  |  |  |  |  |  |  |  |  |
|  | Surfacing and Similar |  |  |  |  |  |  |  |  |  |
|  | Concrete Mix Designs |  |  |  |  |  |  |  |  |  |
| XX.13 | QUALITY OF WORK. |  |  |  |  |  |  |  |  |  |
| XX13.1 | ACCEPTANCE AND QUALITY CONTROL |  |  |  |  |  |  |  |  |  |
| XX13.2 | Acceptance Control |  |  |  |  |  |  |  |  |  |
|  | The engineer is to, on a monthly basis, define the system to be used and ensure that it is operational and reported on. |  |  |  |  |  |  |  |  |  |
| XX13.3 | STANDARD OF WORK |  |  |  |  |  |  |  |  |  |
|  | All parties to report on standard of work after site inspection. |  |  |  |  |  |  |  |  |  |
| XX.14 | BUDGETING |  |  |  |  |  |  |  |  |  |
| XX.14.1 | Estimation of the contract amount will be continually recorded against the original tender sum in order to assist the employer in the project budgeting. Any items of work not shown on the drawings or in the schedule of quantities must be regarded as omitted from the schedules of quantities and classified as a possible over-expenditure. |  |  |  |  |  |  |  |  |  |
| XX.15 | CLAIMS |  |  |  |  |  |  |  |  |  |
|  | The Contractor must be familiar with the procedure stated in the General Conditions of Contract should he consider submitting a contractual claim. |  |  |  |  |  |  |  |  |  |
| XX.16 | MEASUREMENT AND PAYMENTS |  |  |  |  |  |  |  |  |  |
|  | Measurement of quantities and finalisation thereof must be undertaken on a continuous basis to avoid re-measurement at a later stage. |  |  |  |  |  |  |  |  |  |
| XX.16.1 | PAYMENT |  |  |  |  |  |  |  |  |  |
|  | The Contractor must provide an original VAT certificate with the statement. |  |  |  |  |  |  |  |  |  |
|  | Cert. No. |  | Value | Date submitted |  | Date Evaluated |  | Date paid |  |  |
| XX.17 | SITE INSTRUCTIONS AND VARIATION ORDERS |  |  |  |  |  |  |  |  |  |
|  | All site instructions issued during the contract period will be dealt with under this item. |  |  |  |  |  |  |  |  |  |
|  | Day work Orders |  |  |  |  |  |  |  |  |  |
|  | Day work shall only be undertaken upon the instruction of the engineer. |  |  |  |  |  |  |  |  |  |

| XX.18 | EXTENSION OF TIME: DELAYS AND DISRUPTIONS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| XX.18.1 | Rainfall: (Clause 50 of the “Special conditions of contract” forming the Annexure to the “General Conditions of contract” for the six edition (1990) for use in connection with Works of civil engineering construction) |  |  |  |  |  |
|  | Date | Rainfal (mm) | Min. Temp. (C) | Max. Temp. (C) | Standing time (days) | Extension of time (V) Recorded (days) |
|  | Total Rw = |  |  |  |  |  |
|  | V = | (Nw - Nn) | + | (Rw – Rn) X | = |  |

| No | ITEM AND DESCRIPTION |  |  |  | ACTION |
| --- | --- | --- | --- | --- | --- |
| XX.18.2 | Delays: |  |  |  |  |
| XX.18.3 | Disruptions: |  |  |  |  |
|  | Applications for and Approved Extension of Time |  |  |  |  |
|  | Reason for Extension of time |  | Date Applied For | Date Approved |  |
| XX.19 | SAFETY ON SITE AND ACCOMMODATION OF TRAFFIC |  |  |  |  |
| XX.19.1 | Accidents |  |  |  |  |
|  | Report on any accidents |  |  |  |  |
| XX.19.2 | OHS Act |  |  |  |  |
|  | - The OHS Act Plan was reviewed by the OHS Act specialist. - The SAAF requested to be present at the next inspection. |  |  |  |  |
| XX.19.3 | Hiv/Aids awareness |  |  |  |  |
|  | - The Contractor’s HIV/AIDS programme report is kept on site. |  |  |  |  |
| XX.20 | EPWP |  |  |  |  |
|  | Information of the beneficiaries must be provided. |  |  |  |  |
|  | Progress with the EPWP on this contract? |  |  |  |  |
| XX.21 | CIDB REPORT |  |  |  |  |
|  | A monthly report on performance of NDPW appointed contractor by the consulting engineer (CIDB) shall be signed by the contractor and handed to the Project Manager. (Example attached) |  |  |  |  |
| XX.22 | INFORMATION OUTSTANDING |  |  |  |  |
| XX.23 | GENERAL |  |  |  |  |
| XX.24 | NEXT MEETING : SCHEDULE OF FUTURE MEETINGS ATTACHED Next Meeting to be held at the …………………. at the .on ……………………. |  |  |  |  |
| XX.25 | APPROVAL OF MINUTES The Engineer and Contractor approved and signed the Minutes of Meeting No. XX |  |  |  |  |
|  | APPROVAL OF MINUTES |  |  |  |  |
|  | CONTRACTOR | DATE |  |  |  |
|  | ENGINEER | DATE |  |  |  |

SCHEDULE OF MEETINGS

Generally the fourth Wednesday of the month

| No. | DATE | MEETING |
| --- | --- | --- |

DISTRIBUTION LIST

| FAX |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |

| E-MAIL |  |
| --- | --- |
| 1 |  |
| 2 |  |

CLAIMS FOR EXTENSION OF TIME FOR EXCESSIVE RAINFALL

V  = (Nw - Nn) + (Rw – Rn)/X

V	=	Extension of time in calendar day is respect of the calendar month under 			consideration.

Nw	=	Actual number of days during the calendar moth on which a rainfall of Y 				mm or more has been recorded

Nn	=	Average number of days as derived from existing rainfall records on 				which a rainfall of Y mm or more has been recorded for the calendar 				month

Rw	=	Actual rainfall in mm recorded for the calendar month under 					consideration

Rn	=	Average rainfall in mm for the calendar month as derived from existing 				rainfall records

For purposes of the contract Nn, Rn, X and Y shall have those values assigned to them in the Appendix and/or the Specification.

If V is negative and its absolute exceeds Nn, then V shall be taken as equal to minus Nn.

The total extension of time shall be the algebraic sum of all monthly totals of the period under consideration, but if the total is negative the time for completion shall not be reduced due the subnormal rainfall.  Extensions of time for part of a month shall be calculated using pro-rata values of Nn and Rn.

This formula does not take account flood damage which could cause further or concurrent delays and will be treated separately as far as extension of time is concerned.

The factor (Nw – Nn) shall be considered to represent a fair allowance for variations from the average in the number of days during which rainfall exceeds Y mm. The factor (Rw – Rn) shall be considered to represent a fair allowance for variations from the average in the number of days during which the rainfall did not exceed Y mm but wet conditions prevented or disrupted work.

ANNEXURE E2:  PAYMENT CERTIFICATES

# MONTHLY PAYMENT CERTIFICATES

## Monthly payment certificates for civil engineering services must be based on an accurate assessment of the work completed up to the time of measurement.

## The quantities of work completed must be completed on a blank schedule of quantities and valued at contract rates and prices.

## The schedule of quantities must indicate the quantity of work scheduled in the contract documents the quantity of work measured to date as well as the percentage completion of each item.  A separate schedule must be composed for measurement of work executed against variation orders.  The total for each section of the schedule of quantities must be carried to a summary sheet.

## Agree with the Departmental Project Manager on the time of submission of the Payment Certificate.  The Departmental Project Manager will arrange for payment to be made within twenty one (21) days of submission of the certificate to his office.

## The payment certificate must be submitted under cover of form PROGRESS PAYMENT PW1526 (PRM034civ) which should be completed as follows:

| ITEM 1. | ESTIMATED FINAL COST |
| --- | --- |
| Item 1.1 | Contract Sum |
|  | With completion of the original contract sum (tender price), any allowances for VAT, contingencies, etc. must be included. This amount must be used for calculating the Limit of Retention (see DPW-05 (EC) Contract Data Clause 49). |
| Item 1.2 | Variations: Nett additions/omissions |
|  | This item should not be completed in the case of engineering contracts. Work done against variation orders must be included in Item 3.1. |
| Item 1.3 | Estimated Contract Price Adjustment |
|  | The estimated total value of Contract Price Adjustment on completion is to be indicated here. |
| Item 1.5 | Estimated Final Value |
|  | Type in the latest estimate of completion value for the Contract (Contract Price – Clause 1.1.9 of GCC 2004). This amount should be the same as that used in completing Annexure E3 but should also include estimated CPA as per 1.3 above. This is only required for departmental financial control purposes and is not mentioned anywhere else on the form. |
| ITEM 2. | DATE OF VALUATION |
|  | Put in the date on which the certificate is measured (the last day of the period to which the relevant monthly statement relates). |

| ITEM 3. | PAYMENT DETAILS |
| --- | --- |
| Item 3.1 | Value of Work Done |
|  | This total must be brought forward from the abovementioned summary sheet in Clause 3. |

| Item 3.2 | Materials on Site |
| --- | --- |
|  | 100% of materials on site, for which the necessary proof of ownership can be produced, must be paid for under this item. (See PRM035civ in this regard). In the event of civil contracts a certain percentage, to conform to the specification is again subtracted under item 3.7. |
| Item 3.3 | Materials off Site |
|  | Does not apply to civil contracts – see item 3.7. |
| Item 3.4 | Contract Price Adjustments |
|  | In terms of GCC 2004, escalation must also be paid on value of materials on site. Contract Price Adjustments regarding nominated sub-contractors should not be taken into consideration here but should be included in the amount reflected under item 3.5. Should the Contractor exceed his contract period, Clause 3.0 of the Contract Price Adjustment Schedule must be applied. |
| Item 3.5 | Nominated Sub-contractors |
|  | The name of and amount due to all nominated sub-contractors (including Contract Price Adjustment and VAT where applicable but excluding materials on site) must be indicated here. |
| Item 3.6 | Retention Money |
|  | Calculate the Limit of Retention from the percentage stated in the Appendix to the Tender and item 1.1 and enter in the space for maximum retention. Calculate normal retention at ten percent (10%) of SUB-TOTAL A, and enter in the space for retention money. Carry the lesser of the two into the right hand (money) column. After the issuing of the Certificate of Completion, fifty percent (50%) of the above values must be used. In the event where the contract is divided into separate phases, the above calculations for each individual phase of the work should be repeated separately on a summary sheet and the total of the minimums carried to the right hand (money) column. |
| Item 3.7 | Materials on Site |
|  | Payment for materials on site may only be made on receipt of proof of the Contractor’s ownership certified by the Supplier. Advances for materials on an extended site may only be authorised after approval by the Departmental Project Manager. The eighty five percent (85%) advance (one hundred percent (100%) payment under item 3.2 minus fifteen percent (15%) under item 3.7) for materials on site is a maximum and due care must be taken in making any advance. |
| Item 3.8 | MISCELLANEOUS |

| ITEM 4. | DEDUCTIONS |
| --- | --- |
| Item 4.1 | Previous Payments |
| Item 4.2 | Penalty for Late Completion |
|  | Should the Contractor exceed his contract period, Clause 43.1 of GCC 2004 (penalties) must be applied progressively. |
| Item 4.3 | Other (Specify) |
| Item 4.4 | Any direct payments made by the Department on behalf of the Contractor must be completed here. Such amounts must also be included in the value of work done (SUB-TOTAL A) or elsewhere in the certificate. |
| ITEM 6. | VALUE ADDED TAX |
|  | Refer to Clause D.7.6 of this manual. |
| ITEM 7. | AMOUNT PAYABLE (TOTAL) |
| ITEM 8. | Stages |
|  | The progress of the least advanced phase of the Contract must be indicated. |
|  | Expected date of practical completion – Complete |

# RECOVERY STATEMENT

This part must be used to show the following items in accordance with JBCC 2000 
Clause 33:

1.1.1	Effecting insurances (33.2.1)

1.1.2	Work executed by other parties (33.2.2)

1.1.3	Cancellation of a nominated subcontract (33.2.3)

1.1.4	Cancellation of the agreement (33.2.6)

1.1.5	Default by the contractor (33.2.7)

1.1.6	Direct payments to nominated subcontractors (33.2.8)

1.2	Default interest (33.2.5)

2.1	Default interest (33.1.5)

2.2	Damages (33.1.6)

# FINAL STATEMENT

## Appropriation of drawings must be done as work proceeds.  Final measurements and quantities for completed sections of the Contract must be agreed with the Contractor as soon as possible after completion of such sections of the work.

## The final statement for the Contract must be in accordance with PRM044civ/2.

## The final account must be certified in accordance with Annexure E6 and forwarded to the Departmental Project Manager within three (3) weeks after receiving the official decision regarding imposition of penalties.  The Department will forward the final account to the Contractor for signature.

## Where work has been done as day work, the final account must be accompanied by an audited statement regarding the wages paid to the relevant employees as well as time sheets and invoices for all materials used, certified by the Consultant.

## Variation order work must be summarised in a separate schedule, to prevent re-measuring in the other schedule.

ANNEXURE E3:  EXAMPLE FROM SITE INSTRUCTION BOOK

ANNEXURE E4:	REPORT ON CHANGES IN EXPENDITURE AND/COMPLETION 	PERIOD

ANNEXURE E5:  GUIDELINES FOR REQUESTING APPOINTMENT OF SITE STAFF

Download the form PRM033 from the Departmental website and follow the following steps to complete the application:

The different forms, making up the complete submission, are spread over 4 forms plus a Route form, each as per tab at the bottom of worksheets.  NO SEPARATE ROUTE FORM REQUIRED.

Start by completing the forms by moving from the first tab to the next until PRM033-4

Type only the required information in shaded cells - cells that are not shaded contain formulas, etc, please do not alter or remove these!

Repeated information need not be typed in more than once as Excel makes provision for this.

This format makes provision for five site staff members.  If less are required, simply enter zeros in the remaining spaces where no names are entered and regard these as "full time", in other words replace the "#" on PRM033-1 with a "1".  If additional site staff personnel are required at a later stage, replace the zeros with actual data and the correct symbol against full or part time.  By doing this the decision makers can always have a complete cost picture.

Start to open tab marked "PRM033-1:

Rows 7 and 9:  delete the post descriptions which are not applicable

Complete all shaded cells

Follow the instructions emphasised by the red blocks and arrows

Be sure to follow the method description exactly - see comments in certain cells

Type the motivation for the site staff in the appropriate block:

Clearly state the reasons why site staff is/are required, indicating what the effect will be if not appointed, under which regulation the appointment is requested and what the duties of the site staff will be

Costs for all disciplines can be entered - the value for "building" will automatically be shown as the difference between the total and the sum of the others (civil, structural, electrical, mechanical and electronic).

Open tab marked "PRM033-2:

Type the appropriate values in the shaded cells.

Open tab marked PRM033-3:

Only one of two possibilities exist:  site staff is either "full time" or "part time", depending on the entry on PRM033-1 - the entry on PRM033-1 will automatically appear on this sheet.

Excel will indicate one as "not applicable" depending on what was entered on PRM033-1.  Complete the shaded cells in the scenario that is not marked "not applicable".

If no indication was entered on PRM033-1, both scenarios will be marked "not applicable".  If both are marked "not applicable", go back to PRM033-1 and indicate the appropriate scenario.

Tab:  PRM033-4:

If all information was correctly entered on the previous tabs, there should be no need to type/enter anything in this sheet.

Tab:  ROUTE FORM:

If all information was correctly entered on the previous tabs, there should be no need to type/enter anything in this sheet.

Go to File/Print; in the box entitled: "Print What".

Tick "Entire Workbook"

Forward for approval cycle.

ANNEXURE E6:	DIRECTIVE PERTAINING TO THE HANDLING OF THE CONTRACT COMPLETION REPORT (PRM043civ)

| 1. | This report must be dealt with immediately after completion of the works. |
| --- | --- |
| 2. | The Principal Agent (or Private Project Manager, if one was appointed) must complete Sections A to D of the report, which should be supported by the Departmental Project Manager (DPM). |
| 3. | Thereafter, at Head Office, the Departmental Project Manager’s Director, or at Regional Office the Departmental Project Manager’s Regional Project Manager (C/RPM) comments on and signs the report. |
| 4. | The report does not necessarily need to be submitted to the Penalty Committee but may be signed off by the Director Major Projects (D/MP) or the Director Maintenance (D/Maint) at Head Office or by the Regional Manager (RM) at the Regional Office (RO), should one of the following apply: |
| 4.1 | When the contract was completed in time (no penalties). |
| 4.2 | When extension was granted for all delays (no penalties). |
| 4.3 | When extension was granted for part of the delays and no application was received for the waiver, reduction or condonation of the balance of the delays (penalties apply for the balance of the delays). |
| 4.4 | When delays occurred and no application was received for the waiver, reduction or condonation of these delays (penalties apply for the full delay). |
| 5. | After the report has been signed off, the procurement section of Head Office (HO) or Regional Office (RO), whatever the case may be, updates the WCS (#WG07PU) regarding the Contractor’s performance and the decisions on penalties, if any. A copy of the report is then submitted to the DPM, who immediately has to inform the consultants of the penalty amount to be included in the final account (if applicable). |
| 6. | Should the contractor apply for the waiver, reduction or condonation of all or any part of the delays, the report must be referred to the Penalty Committee at HO for a decision. The Penalty Committee consists of the Chief Director/DO and the CD/P+FM. |
| 7. | HO services applications for decisions by the Penalty Committee must be send through the HO Procurement Section and RO services through the RO Procurement Section who in turn has to send it to HO Procurement Section. |
| 8. | After the Penalties Committee’s decision, the report is returned along the same route as described in 7 above. The Procurement Section at HO updates the WCS (#WG07PU) regarding the Contractor’s performance and the decision on penalties. A copy of the report is then submitted to the DPM. The original Contract Completion Report must be placed on the central file (HO or RO, which ever the case may be). |
| 9. | The DPM informs the Principal Agent as well as the Consultant, if any, of the decisions in the report are to be implemented. |

HANDLING OF THE CONTRACT COMPLETION REPORT (PRM043civ)

ANNEXURE E7:	MONTHLY REPORT ON PERFORMANCE OF NDPW APPOINTED CONTRACTOR BY THE CONSULTING ENGINEER (CIDB)

| (Note: This form must be completed and submitted for the signature of the Project Manager simultaneously with the monthly progress report. The original reports shall be kept by the Consultant in order to complete the final report for submission to the CIDB) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Prepared by Consulting Engineering Enterprise/Firm: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ....................................................................... |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Office Physical Address: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Office Postal Address: |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Postal Code: |  |  |  |  |  | .................................... |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Postal Code: |  |  |  |  |  |  |  | ............................... |  |  |  |  |
| 1.2 | Date: |  |  | .................................................... |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. | Enterprise evaluated: |  |  |  |  |  |  |  |  |  | ............................................................................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Trading as: |  |  |  | ............................................................................................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | CIDB Registration No: |  |  |  |  |  |  |  |  |  |  |  | ........................................................................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Company / CC Registration No: |  |  |  |  |  |  |  |  |  |  |  |  |  | ............................................................................................................. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 | Head Office Physical Address: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Head Office Postal Address: |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | .............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Postal Code: |  |  |  |  |  | .................................... |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Postal Code: |  |  |  |  |  |  |  | ............................... |  |  |  |  |
| 2.5 | Contact Person: |  |  |  |  |  | Title: |  |  |  |  | ........................ |  |  |  |  |  |  | Initials: |  |  | ........ |  |  |  |  | Surname: |  |  |  |  |  |  | ....................................... |  |  |  |  |  |
| 2.5.1 | Designation: |  |  |  | ............................................................. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | e-mail: |  |  |  |  | ...................................................... |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Telephone: |  |  |  | (.......) .............................. |  |  |  |  |  |  |  |  |  |  |  |  |  | Fax: |  | (.......) ........................... |  |  |  |  |  |  |  |  |  |  |  |  | Cell: |  |  | ............................ |  |  |
| 3. | Project description: |  |  |  |  |  |  |  | ................................................................................................................................ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Location: |  |  |  | ............................................................................................................................................. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Contract No.: |  |  |  |  | ......................................... |  |  |  |  |  |  |  |  |  |  |  |  | 3.3 | Date appointed: |  |  |  |  |  |  |  |  |  | ..................................................... |  |  |  |  |  |  |  |  |  |
| 3.4 | Project Team Leader: |  |  |  |  |  |  |  |  | ...................................... |  |  |  |  |  |  |  |  |  | H&S Officer: |  |  |  |  |  |  |  |  |  | ..................................................... |  |  |  |  |  |  |  |  |  |
| 3.5 | Duration of project: |  |  |  |  |  |  | Start date: |  |  |  |  |  |  |  |  | ............................... |  |  |  |  |  |  |  | 3.6 |  |  | Completion date: |  |  |  |  |  |  |  | .............................. |  |  |  |
| 4. | Evaluation of performance of this enterprise: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Evaluation criteria: |  |  |  |  |  |  | (Excellent = 1, |  |  |  |  |  |  |  |  |  | Good = 2, |  |  |  |  | Fair = 3 |  |  |  |  |  |  |  |  | Unacceptable/poor = 4) |  |  |  |  |  |  |  |
|  | ITEM |  | DESCRIPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | EVALUATION |  |
|  | A |  | Compliance with Contract Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 |  | Compliance with contract documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 |  | Adherence to contractual commitments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  | Compliance with labour standards (contractor and subcontractor) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 |  | Compliance with other laws and regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 |  | Compliance with insurances and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  | Quality of Resources (Specify which resources are not acceptable) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7 |  | Sufficiency of Resources (Specify which resources are not adequate) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | ITEM | DESCRIPTION |  |  |  |  |  |  |  |  |  |  | EVALUATION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | B | Quality of housekeeping, Project Cleanliness |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Standard of camp site |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Quality of the contract name board |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | General housekeeping on site |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Complying with environmental requirements |  |  |  |  |  |  |  |  |  |  |  |
|  | C | Quality of Contractor's Health and Safety Program |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Quality of Health and Safety Plan |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Adherence to OSHA Requirements |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Compliance with Construction Regulations |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | HIV/Aids awareness |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Quality of safety procedures |  |  |  |  |  |  |  |  |  |  |  |
|  | D | Staffing of Project |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Adequate skilled staff to administer the project (supervisory and other personnel) |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Adequate project workforce |  |  |  |  |  |  |  |  |  |  |  |
|  | E | Quality of Contractor's Work |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Quality of Contractor's required documentation |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Quality of supervisory personnel |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Quality of the work executed (Attach list of work not to standard) |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Quality of material used (Attached list of material not to specification) |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Compliance with written contract instructions |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Compliance with specifications and drawings |  |  |  |  |  |  |  |  |  |  |  |
|  | 7 | Quality of supervision of work |  |  |  |  |  |  |  |  |  |  |  |
|  | F | Working Relationship between Contractors and with Project Owner |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Cooperation/Communication with Project Owner |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Cooperation/Communication with Other Contractors |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Cooperation/Communication with Subcontractors |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Attendance at Project Meetings |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Managing of Subcontractors |  |  |  |  |  |  |  |  |  |  |  |
|  | G | Contractor's Ability to Work within Allotted Cost |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Contractor's ability to keep to the contract's allotted cost |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | The level of progress on the project in relation to the financial program |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Quality of financial reporting and adherence to financial programme |  |  |  |  |  |  |  |  |  |  |  |
|  | H | Adherence to Project Schedule Including Project Completion |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Adherence to Project Schedule Including Project Completion |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Submission of Project Schedule and Updates |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Notification of Possible Claims of Delays |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | The degree of progress in line with the project programme, contractual completion period and/or extension thereto |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Timeous submission of time delay claims |  |  |  |  |  |  |  |  |  |  |  |
|  | I | OTHER |  |  |  |  |  |  |  |  |  |  |  |
| 5. | Explanation of non-performance and rectification measures |  |  |  |  |  |  |  |  |  |  |  |  |
|  | In case of evaluation points greater than two (2) please explain the reason for the score and detail of the non acceptable performance below. Also indicate what measures have been taken to ensure that the contractor address the unacceptable performance. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ITEM | DETAILED REPORTING ON BAD PERFORMANCE |  |  |  |  |  |  |  |  |  |  |  |
|  | Report prepared by: |  |  | ........................................................... |  |  |  |  |  | (Consultant signature) |  |  |  |
|  | Date: | ................................................... |  |  |  |  |  |  |  |  |  |  |  |
| 6. | Explanation by the Contractor regarding the reasons for his/her non/bad performance |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ITEM | REASONS FOR BAD/NON PERFORMANCE BY THE CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |
| 7. | Intended actions by the Contractor rectify bad/non-performance |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ITEM | INTENDED ACTIONS BY THE CONTRACTOR TO RECTIFY BAD/NON-PERFORMANCE |  |  |  |  |  |  |  |  |  |  |  |
|  | I concur with the contents of the report and will take the steps as described to ensure compliance with all requirements of the contract with my Client, the National Department of Public Works. I also accept the fact that the final performance report to the CIDB in terms of the CIDB Act will be based on the information gathered on these reports during the contract period. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | The Contractor (Name in print): |  |  |  | ............................................................................................................. |  |  |  |  |  |  |  |  |
|  | Signature: |  | ............................................................ |  |  |  |  | Date: | .................................................................. |  |  |  |  |
| 8. | Endorsed by the NDPW Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |
|  | I have taken notice of the report |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ....................................................................... |  |  |  |  |  |  | Date: | .................................................................. |  |  |  |  |
|  | Project Manager (name in print) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ....................................................................... |  |  |  |  |  |  | Date: | .................................................................. |  |  |  |  |
|  | Project Manager (signature) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ....................................................................... |  |  |  |  |  |  | Date: | .................................................................. |  |  |  |  |
|  | Office (Regional Office name or Head Office) |  |  |  |  |  |  |  |  |  |  |  |  |