SECTION G:  RELEVANT PRM-FORMS

CONTENTS

Item	Page

G.1	PRM-FORMS	2

G.2	INTRODUCTION	2

G.3	LIST OF RELEVANT PRM-FORMS	2

1.	PRM006:  CONSULTANT’S TEAM	6

2.	PRM007:  INCEPTION CHECK LIST	8

3.	PRM008:  DETAIL PROJECT PLANNING PROGRESS REPORT	25

4.	PRM009:  PROGRESS REPORT ON PROJECT APPRAISAL PHASE	27

5.	PRM011A:  DOLOMITE STATUS CERTIFICATE DOLOMITE RISK MANAGEMENT SYSTEM	28

6.	PRM012:  ENVIRONMENTAL AND SOCIAL ASPECTS TO BE CONSIDERED	31

7.	PRM013:  AGENDA FOR COMPREHENSIVE PROJECT BRIEF	33

8.	PRM014/6:  MONTHLY PROGRESS REPORT ON CIVIL ENGINEERING DESIGN	36

9.	PRM015:  PROGRESS/BAR CHART	37

10.	PRM016/7:  SKETCH PLAN COMMITTEE MANUAL	38

11.	PRM017:  SUBMISSION OF DRAWINGS TO LOCAL AUTHORITIES	46

12.	PRM018:  SCHEDULE OF CONSTRUCTION AND FINISHES,  USE FACTOR 
ANALYSIS AND ESTIMATE	48

13.	PRM019:  COST NORM REPORT (EXAMPLE)	49

14.	PRM031/1civ:  AGENDA FOR SITE HANDOVER MEETING	51

15.	PRM031/2:  GUIDELINES FOR SITE HANDOVER MEETING MINUTES  (Example)	56

16.	PRM034:  PROGRESS PAYMENT	64

17.	PRM035:  APPLICATION FOR PAYMENT OF MATERIALS ON SITE	65

18.	PRM036:  CONTRACT STATUS REPORT	66

19.	PRM037:  VARIATION ORDER (Clause 36 & 37 of GCC 2004): STEP BY STEP	76

20.	PRM037:  VARIATION ORDER: MOTIVATION	77

21.	PRM037:  VARIATION ORDER	78

22.	PRM039:  APPLICATION FOR ADDITIONAL FUNDS	79

23.	PRM040:  APPLICATION FOR EXTENSION OF CONTRACT PERIOD	82

24.	PRM041:  CERTIFICATE OF PRACTICAL COMPLETION	85

25.	PRM041:  CERTIFICATE OF COMPLETION	87

26.	PRM042:  TERMINATION OF GUARANTEE	88

27.	PRM043:  CONTRACT COMPLETION REPORT	90

28.	PRM044:  FINALISATION OF FINAL ACCOUNT AND CHECK LIST	95

29.	PRM045:  CERTIFICATE OF COMPLIANCE AND INDEMNITY BY CONSULTANTS	97

30.	PRM046:  FINAL APPROVAL CERTIFICATE	99

PRM-FORMS

Visit the DPW website http://www.publicworks.gov.za at Consultant’s Guidelines and go to Item No. 14, CONTRACT ADMINISTRATION FORMS/PROJECT MANAGEMENT FORMS (PRM-forms) to access the PRM-forms.

Enquiries:

Obed Molotsi (Construction Project Manager)	
Tel: 012 337-3493 	
e-Mail address: obed.molotsi@dpw.gov.za

INTRODUCTION

The PRM-forms have been developed by the Department to document the various programmes, processes and steps to follow throughout the execution of any project.

As the Department is in process to update all project management (PRM) forms please ensure that the latest form published on the DPW website is used on a project. The Civil Engineering Department adapted some of the standard forms to suit the specific needs of the civil engineer.  These forms have the letters “civ” attached to the number and are not available on the website but can be provided by the Project Manager to the Consultant.

LIST OF RELEVANT PRM-FORMS

A list of all the relevant PRM-forms which exists when this manual was updated follows beneath.

NOTE:

In case of Engineering Projects the Consultant must sign the related document wherever referral is made to the Principal Agent or Principal Agent/Engineer or Engineer.

See pages G3 to G5 for the list of relevant PRM-forms.

| RELEVANT PRM-FORMS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No. |  | PRM No. | STAGE | DESCRIPTION | ROLE PLAYERS |  |  |
| 1. |  | PRM001 | STAGE 1: INCEPTION | Accommodation Schedule Guideline | Department |  |  |
| 2. |  | PRM002 |  | Planning Instruction | Department |  |  |
|  |  |  |  | Example of output from WCS-system: Planning Instruction | Department |  |  |
| 3. |  | PRM003 |  | Appointment of Consultants from Roster Plus Annexures | Department |  |  |
| 4. |  | PRM004 |  | Search request for professional services in respect of specialist and routine assignments | Department |  |  |
| 5. |  | PRM004/1 |  | Fields of Competence | Department |  |  |
| 6. |  | PRM004/2 |  | Consultant Roster Town Selection | Department |  |  |
| 7. |  | PRM004/3 |  | Guideline for the Preparation of a Project Execution Plan Required for the Appointment of a Consultant from a Roster | Department |  |  |
| 8. |  | PRM004/4 |  | Guidelines for the preparation of a brief for the appointment of a consultant from a roster | Department |  |  |
| 9. |  | PRM005 |  | Agenda: Appraisal Phase: Consultants briefing meeting | Department/Consultant |  |  |
| 10. |  | PRM006civ |  | Consultant’s Team | Department/Consultant |  |  |
| 11. |  | PRM007civ |  | Inception check list Local Information check list Site and Building Surveys Check list | Department |  |  |
| 12. |  | PRM008civ | STAGE 2: PRELIMINARY DESIGN | Detail Project Planning Progress Report | Client/Depart/Consultant |  |  |
| 13. |  | PRM009civ |  | Progress Report on Project Appraisal Phase | Consultant |  |  |
| 14. |  | PRM010 |  | Policy and Procurement for the Demolition of state buildings: Treasury Instruction F1.5.1 |  |  |  |
|  |  |  |  | Demolition of State Owned Buildings | Consultant & Department |  |  |
| 15. |  | PRM011Aciv |  | Dolomite status | Department |  |  |
| 16. |  | PRM012civ |  | Environmental and social aspects to be considered | Consultant & Department |  |  |
| 17. |  | PRM013civ |  | Agenda for Consultants Comprehensive Project Brief | Consultant & Department |  |  |
| 18. |  | PRM014/6civ |  | Monthly progress report on Civil Engineering Design | Consultants |  |  |
| 19. |  | PRM015civ |  | Progress Bar Chart | Consultants |  |  |
| 20. |  | PRM016/7civ |  | Sketch Plan Committee Manual | Consultant/Department |  |  |
| 21. |  | PRM017civ | DETAIL DESIGN | Submission of Drawings to Local Authorities | Consultant/Department |  |
| 22. |  | PRM018civ |  | Schedule of construction and finishes, use factor analysis and estimate | Consultant/QS/ Department |  |
| 23. |  | PRM019civ/1 |  | Cost Norm Report (example) | Consultant/Quantity Surveyor// Department |  |
| 24. |  | PRM019civ/2 |  | Certification that Projects are within the Approved Space and Cost Norms | Consultant/Quantity Surveyor// Department |  |
| 25. |  | PRM021 | STAGE 4: DOCUMENTATION AND PROCUREMENT | APP Documents to be included in tender document Preference Certificate for requirements less than R2 Million (ST11.1) Declaration Contract Classification | Department |  |
| 26. |  | PRM022 |  | Information form Provisional sums | Department |  |
| 27. |  | PRM023 |  | Procurement Certificate | Department |  |
| 28. |  | PRM024 |  | Request for printing of contract drawings | Department |  |
| 29. |  | PRM025 |  | Request for printing of documents | Department |  |
| 30. |  | PRM026 |  | Tender advert form - Normal tender process Tender advert form - Pre-Qualification of Tenderers Tender advert form - Price request from Pre-Qualified Tendereres Withdrawal of Tender | Department |  |
| 31. |  | PRM027/01 |  | Agenda for Strategy and Bid Specification Meeting | Department |  |
| 32. |  | PRM027/02 |  | Checklist for Approval of Specification by Specification Committee | Department |  |
| 33. |  | PRM027/03 |  | Checklist for JBCC Procurement Document | Department |  |
| 34. |  | PRM027/04 |  | Checklist for GCC Procurement Document | Department |  |
| 35. |  | PRM028/01 |  | Agenda for Evaluation Meeting Technical Risk | Department |  |
| 36. |  | PRM028/02 |  | Agenda for Evaluation Meeting Commercial Risk | Department |  |
| 37. |  | PRM029 |  | Request for Priced Bill of Quantities | Department |  |
| 38. |  | PRM030 |  | APP Tender Report | Department |  |
| 40. | PRM031civ/1 |  | STAGE 5: CONTRACT ADMINISTRATION AND INSPECTION | Hand over of site meeting minutes |  | Department/Consultant |
| 41. | PRM031/1civ/1 |  |  | Agenda for site handover meeting |  | Department/Consultant |
| 42. | PRM031/2civ/1 |  |  | Guideline for site handover meeting minutes |  | Department/Consultant |
| 43. | PRM031/2civ/9 |  |  | Guideline for Agenda for monthly progress meetings |  | Department/Consultant |
| 44. | PRM032 |  |  | Acknowledgement of handing over of site - JBCC and GCC |  | Department & Contractor |
| 45. | PRM033 |  |  | Application for the appointment of Site Staff |  | Consultant/Department |
| 46. | PRM034civ |  |  | Progress Payment JBCC and GCC |  | Consultant |
| 47. | PRM035civ |  |  | Application for an Advance in Respect of Material/Equipment in Terms of Clause 23 of the Conditions of Contract |  | Consultant & Contractor |
| 48. | PRM036civ |  |  | Contract Status Report |  | Department & Consultant |
| 49. | PRM037civ/1 |  |  | Variation Order: Step by step |  | Consultant, Contractor & Department |
| 50. | PRM037civ/2 |  |  | Variation Order: Motivation |  | Consultant & Contractor |
| 51. | PRM037civ/3 |  |  | Contract Adjustment/Variation Order |  | Consultant, Contractor & Department |
| 52. | PRM039civ/1 |  | STAGE 5: (Continued) | Application for Additional Funds Contractor |  | Consultant & Contractor |
| 53. | PRM039civ/2 |  |  | Application to exceed contract amount for non-scheduled and scheduled tariffs |  | Department |
| 54. | PRM040/civ1 |  |  | Application for Revision of Date of Practical Completion/Extension of Time |  | Contractor, Consultant & Department |
| 55. | PRM040civ/2 |  |  | Claim for Revision of Date of Practical Completion/Extension of Time |  | Contractor, Consultant & Department |
| 56. | PRM040civ/3 |  |  | Submission of Application for Revision of Date of Practical Completion/ Extension of Time by Principal Agent |  | Contractor, Consultant & Department |
| 57. | PRM041civ/1 |  |  | Certificate of Practical Completion JBCC |  | Department & Consultant |
| 58. | PRM041civ/2 |  | STAGE 6: CLOSE-OUT | Addendum A: Outstanding work to be completed |  | Department & Consultant |
| 59. | PRM041civ/3 |  |  | Certificate of Completion |  | Department & Consultant |
| 60. | PRM042civ/1 |  |  | Termination of Guarantee/Security |  | Department & Consultant |
| 61. | PRM042civ/2 |  |  | Calling up of Guarantee/Security |  | Department |
| 62. | PRM043civ |  |  | Contract Completion Report |  | Consultant |
| 63. | PRM044civ/1 |  |  | Finalisation of Final Account and check list |  | Consultant |
| 64. | PRM044civ/02 |  |  | Final Statement |  | Consultant |
| 65. | PRM045civ |  |  | Certificate of Compliance and Indemnity by Consultants |  | Consultant |
| 66. | PRM046civ/1 |  |  | Final Approved Certificate GCC |  | Department & Client |
| 67. | PRM047 |  |  | WCS Consultant Payment Advice |  | Department |

PRM006civ/1

# PRM006:  CONSULTANT’S TEAM

| WCS No: |  |  |  |  |  |  |  |  | ………………………………. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REFERENCE No: |  |  |  |  |  |  |  |  | ………………………………. |  |
| PROJECT: | ……………………………………………………………………………………………………..…… |  |  |  |  |  |  |  |  |  |
|  | ………………………………………………………………………………………………………….. |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  | ……………………………… |  |  |  |  |  |  |
| Tel: | ………………………….. |  |  | Fax: |  | ……..…………………… |  |

User/Client Department: Contact person (Head Office):……………………………………………………………………………………….. Tel: …………………... Fax:……………………. Address: ………………………………………………………………………………………………………………. ………………………………………………………………………………………………………………. Contact person (Regional Office): ………………………………………………………………………………….. Tel: …………………… Fax:…………………… Address: ……………………………………………………………………………………………………………….. ……………………………………………………………………………………………………………….

Principal Agent/Consultant (firm): …………………………………………………………………. Name of person: ………………………………………………………………………………………………………. Address:………………………………………………………………………………………………………………… ………………………………………………………………………………………………………………… Tel: …………………… Fax:…………………… Departmental registration No:………………………………………………………………………………………... VAT registration number:………………………………….

* If applicable

DEPARTMENT OF PUBLIC WORKS: DOLOMITE RISK MANAGER Name of person: ……………………………………………………………………………………………………… Address: Private Bag X65 PRETORIA 0001 Tel: (012) 337-2334 Fax: (012) 325-8094 Cell: 082 889 0283

Consultant (Firm): …………………………………………………………………………………………………. Name of person: ……………………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration No:……………………………………………………………………………………. VAT registration No: …………………………………………….

PRM006civ/2

Consultant (Firm): …………………………………………………………………………………………………. Name of person: ……………………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration number ………………………………………………………………………………. VAT registration No. ……………………………………………

Consultant (Firm): …………………………………………………………………………………………………. Name of person: ……………………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration No: ……………………………………………………………………………………. VAT registration No: …………………………………………….

CONSULTANT SPECIALIST/LANDSCAPE ARCHITECT/PROCESS ENGINEER/ ACOUSTICS/TOWN PLANNER Firm (1): ……………………………………………………………………………………………………………. Name of person: ……………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration No: …………………………………………………………………………………… VAT registration No: …………………………………………… Firm (2): ……………………………………………………………………………………………………………. Name of person: ……………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration No: …………………………………………………………………………………… VAT registration No: …………………………………………… Firm (3): ……………………………………………………………………………………………………………. Name of person: ……………………………………… Address: …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… …………………………………………………………………………………………………………… Tel:……………………………… Fax:……………………………… Departmental registration No: …………………………………………………………………………………… VAT registration No: ……………………………………………

PRM007civ/1

# PRM007:  INCEPTION CHECK LIST

The inception check list is a tool enabling the Project Manager to check whether all information needed for the planning of the facility has been made available including an accommodation schedule, with room usage, required equipment, furniture and services with dimensioned positions.

The inception check list must be adapted/adjusted and/or amplified to satisfy the needs of a specific project being either a new or an existing building/facility.

| - Nature of Project: | ………………………………………………………… | WCS: | …………………. |
| --- | --- | --- | --- |
| Outline of objective: | …………………………………………………………………………………………... |  |  |
| ………………………………………………………………………………………………………………………………… |  |  |  |
| Project Manager: | ……………………………………… Region:…………………………………….… |  |  |

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 1.01 | Function |  |  |
| 1.02 | Services |  |  |
| 1.03 | Finishes |  |  |
| 1.04 | Furniture and fittings |  |  |
| 1.05 | Landscape and site. |  |  |

2.	Schedule of accommodation

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 2.01 | Population figures |  |  |
| 2.02 | Functional diagrams, etc. |  |  |

3.	Expenditure intended

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 3.01 | Statements of costs limits if any, see Part 3.514 Cost Limits |  |  |

REMARKS:

PRM007civ/2

4.	Dates and tentative programme

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 4.01 | Survey and detailed analysis of site; |  |  |
| 4.02 | Submission of outline proposals, scheme design and approximate estimates; |  |  |
| 4.03 | Statutory applications/compliance; |  |  |
| 4.04 | Start of production information; |  |  |
| 4.05 | Start of bills of quantities |  |  |
| 4.06 | Out to tender |  |  |
| 4.07 | Contract let |  |  |
| 4.08 | Possession of site and start of works |  |  |
| 4.09 | Completion and handover |  |  |
| 4.10 | Defects liability period and final account |  |  |

5.	Procedure

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 5.01 | Client’s authorised representative |  |  |
| 5.02 | Client’s special requirements regarding selection of main contractor, sub-contractors and suppliers |  |  |
| 5.03 | Client’s special requirements regarding cost control; formal approval of overall cost only; or detailed breakdown of elements, finishes, services, etc., item by item, see Part 3.260 Cost Control |  |  |

REMARKS:

PRM007civ/3

6.	DPW Conditions of Engagement

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 6.01 | Scope of services |  |  |
| 6.02 | Scale of charges |  |  |
| 6.03 | Incidental expenses and travelling |  |  |

7.	Clerk of Works

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 7.01 | If constant supervision is required, refer to DPW Conditions of Contract |  |  |
| 7.02 | Mechanical services Clerk of Works |  |  |
| 7.03 | Electrical services Clerk of Works |  |  |
| 7.04 | Site supervision generally |  |  |

8.	Other members of the design team already appointed or to be recommended; method of appointment and scale of fees.

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 8.01 | Quantity surveyor |  |  |
| 8.02 | Structural engineer / Civil engineer |  |  |
| 8.03 | Mechanical services engineer |  |  |
| 8.04 | Sanitary engineer |  |  |
| 8.05 | Electrical engineer |  |  |
| 8.06 | Acoustical expert |  |  |
| 8.07 | Landscape architect |  |  |
| 8.08 | Painters and sculptors |  |  |
| 8.09 | Model makers etc. |  |  |
| 8.10 | Dolomite Risk Manager |  | Departmental (HQ) |

REMARKS:

PRM007civ/4

9.	Site

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 9.01 | Survey available or required to be done by the Department or outside surveyor |  |  |
| 9.02 | Legal position: freehold, leasehold, etc. restrictive covenants |  |  |
| 9.03 | Name, address and telephone numbers: solicitor, ground landlord, adjoining owners, etc. |  |  |
| 9.04 | Geotechnical Survey and classification |  | Departmental Dolomite Risk Manager |
| 9.05 | Is site located on dolomite |  | Departmental Dolomite Risk Manager |

10.	Statutory and other approvals

The client should be told of the statutory and other consents to be gained, notices to be served, awards to be made and related expenses such as adjoining owners/surveyor fees, own architect’s fees for special negotiations, etc.

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 10.01 | Town and Country Planning Acts |  |  |
| 10.02 | Provincial Fine Arts Commission / Heritage |  |  |
| 10.03 | Building Acts and Byelaws |  |  |
| 10.04 | Public Health Acts |  |  |
| 10.05 | Fire Regulations |  |  |
| 10.06 | Occupational Health and Safety Act, etc. |  |  |
|  | Others |  |  |
| 10.07 | Landlord, lessor, etc. and their architects and surveyors |  |  |
| 10.08 | Adjoining owners |  |  |
| 10.09 | Insurance companies, etc. |  |  |

11.	Other architects

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 11.01 | The names and addresses of other architects who have worked or been instructed to work on the scheme and who must be notified of Professional Conduct. |  |  |

12.	Other information

NAME: ..................................... DATE: ....................................

PRM007civ/5

LOCAL INFORMATION CHECK LIST

1.	Neighbouring owners	WCS:  ....................

Check and consult documents, drawings, and people regarding:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 1.01 | Access to site |  |  |
| 1.02 | Right of light and air |  |  |
| 1.03 | Noise |  |  |
| 1.04 | Smells |  |  |
| 1.05 | Fire risks |  |  |
| 1.06 | Drainage |  |  |
| 1.07 | Services |  |  |
| 1.08 | Right of support |  |  |
| 1.09 | Possibility of flooding |  |  |
| 1.10 | Conflicting interests |  |  |
| 1.11 | Condition of adjacent property (include photographs) |  |  |
| 1.12 | Dolomite |  |  |

2.	Civil engineering contractors and building contractors obtain:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 2.01 | Information relating to adjacent sites |  |  |
| 2.02 | Information relating to earlier use of site |  |  |
| 2.03 | Details of local materials |  |  |
| 2.04 | Details of sub-soil conditions to be anticipated (Initiate engineering geological investigation in terms of current practice if site is located on dolomite. Please note this investigation is not a standard foundation investigation) |  |  |
| 2.05 | Names and addresses of local suppliers of aggregates, hardcore, premix concrete etc. and approved laboratories. |  |  |
| 2.06 | Flood line information. See Section F |  |  |

REMARKS:

PRM007civ/6

3.	Suppliers

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 3.01 | Check on quality, availability and cost of local material |  |  |
| 3.02 | Inspect quarries, brickworks, etc., for samples and prices |  |  |

4.	Local facilities

Check with appropriate authorities, present and future availability of:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 4.01 | Transport |  |  |
| 4.02 | Schools |  |  |
| 4.03 | Shops/shopping centres |  |  |
| 4.05 | Other local facilities |  |  |
| 4.06 | Parking |  |  |

5.	Underground hazards

Check with local authority engineer, Spoornet, local Transport or other operator:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 5.01 | Details of railway or tunnels |  |  |
| 5.02 | Details of mineral workings/rights |  |  |
| 5.03 | Springs, water table, ground movement, soil conditions |  |  |
| 5.04 | Dolomitic land |  | Contact Risk Manager |

6.	Climate

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 6.01 | Find out prevailing climatic conditions (wind, rain, etc.) |  |  |
| 6.02 | Check if there are any unusual conditions |  |  |
| 6.03 | Check on sea air, smoke, fumes, acid rain, corrosion, etc. |  |  |

REMARKS:

NAME:...................................... DATE:..........................................

PRM007civ/7

SITE AND BUILDING SURVEYS CHECK LIST

1.	Preliminaries	WCS: .............................

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 1.01 | Consider purposes of survey, type of information required including type of drawings, reports, etc., and time allowed |  |  |
| 1.02 | Consider employment of qualified land surveyor, air surveyor, photographer, etc., if site is large, obtain client’s approval and consider brief and programme |  |  |
| 1.03 | Consider requesting reports from local specialist sub-contractors or local supply companies on existing heating, hot water, electrical, gas or other services installation; obtain client’s approval if necessary and consider brief and programme |  |  |
| 1.04 | Check what special fees, expenses, etc., have been agreed with the client |  |  |
| 1.05 | Check that client has right of access to site |  |  |
| 1.06 | Check accuracy and availability of survey equipment, e.g.: Compass, level, staff sighting rods and makers ladder, chain manhole lifting irons tape, 2m rod survey board scales, camera (Much of this equipment may be hired from surveying and drawing equipment suppliers) |  |  |
| 1.07 | Consider appointment with local authority officers including Town Planning, Building Inspector, Public Health, Fire Brigade, etc. |  |  |
| 1.08 | Obtain Surveyor sheet or General map and/or Registered Land Plan and establish boundaries, servitudes. |  |  |
| 1.09 | Discuss site development with Departmental Dolomite Risk Manager |  |  |

REMARKS:

PRM007civ/8

2.	General:  Legal

Obtain from the user Department or his agent:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 2.01 | Names and address of solicitors/agents |  |  |
| 2.02 | Existing drawings |  |  |
| 2.03 | Property: leasehold, freehold, if ground rent, tithes or restrictive covenants as to usage, tenure or sale |  |  |
| 2.04 | Ownership of fences |  |  |
| 2.05 | Rateable values |  |  |
| 2.06 | Insurances and insurance companies |  |  |
| 2.07 | Approvals already received |  |  |
| 2.08 | Highway rights and road access. |  |  |

3.	Building work:  Legal

Obtain from local or other statutory authority:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 3.01 | Names and addresses of officials concerned |  |  |
| 3.02 | Town planning: requirements, restrictions and intentions |  |  |
| 3.03 | Future developments including new roads and widening |  |  |
| 3.04 | Building surveyor: obtain copy of local special byelaws if any |  |  |
| 3.05 | Copy of ordnance block plan |  |  |
| 3.06 | Submission requirements and forms and last date each month for submitting applications |  |  |
| 3.07 | Record plans for foundations, etc. |  |  |
| 3.08 | Building lines, servitudes or restrictions |  |  |
| 3.09 | Possible road charges and liabilities |  |  |
| 3.10 | Small Holdings Act, etc. |  |  |
| 3.11 | Restrictions under Clean Air Act |  |  |
| 3.12 | Ancient monuments or scheduled historic buildings >60 years |  |  |
| 3.13 | Housing unit limitations |  |  |
| 3.14 | See Departmental Standards for development on Dolomitic Land. Obtain similar applicable standards from the Local Authority |  |  |

REMARKS:

PRM007civ/9

4.	Services:

Obtain from local authority or public utilities:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 4.01 | Names and addresses of officials concerned |  |  |
| 4.02 | Foul sewer: line and invert levels |  |  |
| 4.03 | Surface water sewer: line and invert levels (stormwater). |  |  |
| 4.04 | Existing septic tanks and if emptied by the local authority |  |  |
| 4.05 | Future drainage schemes by the local authority: possible future connections and charges |  |  |
| 4.06 | Water supply |  |  |
| 4.07 | Electricity supply: voltage, capacity, |  |  |
| 4.08 | Gas supply |  |  |
| 4.09 | Telephone service |  |  |
| 4.10 | Postal services |  |  |

5.	Local enquiries:

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 5.01 | Present or future existence of undesirable features in proximity of site, e.g. sewage works, tanneries, aerodromes, dairies, railway sidings, rivers, ponds etc., liable to overflow or flooding on or near site |  |  |
| 5.02 | Age of property |  |  |
| 5.03 | Adequacy of local facilities, e.g. transport, schools, shops, post |  |  |
| 5.04 | Names of reliable local builders |  |  |
| 5.05 | Special materials available locally |  |  |

REMARKS:

PRM007civ/10

6.	Underground hazards

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 6.01 | Mineral workings |  |  |
| 6.02 | Railway or tube/tunnels |  |  |
| 6.03 | Springs |  |  |
| 6.04 | Level of water table |  |  |
| 6.05 | Ground movement or erosion |  |  |
| 6.06 | Dolomite |  |  |

7.	Adjoining properties

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 7.01 | General character, condition and usage |  |  |
| 7.02 | Rights of air and light |  |  |
| 7.03 | Conflicting interests |  |  |
| 7.04 | Subsidence evidence |  |  |

8.	Actual site

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 8.01 | Orientation |  |  |
| 8.02 | Prevailing wind |  |  |
| 8.03 | Local climatic or other hazards, e.g. sea air, smoke, fumes |  |  |
| 8.04 | Views from and on to site |  |  |
| 8.05 | Trees: species, height, girth and condition |  |  |
| 8.06 | Rock outcrops, gardens, pons |  |  |
| 8.07 | Soil, sub-soil, trail holes |  |  |
| 8.08 | Evidence of flooding or ground movement |  |  |
| 8.09 | Fences, gates, boundary/and retaining walls, ownership, condition |  |  |
| 8.10 | Building lines |  |  |
| 8.11 | Paths, roads, pavings |  |  |
| 8.12 | Existing buildings: position and floor levels, obvious failures of materials or construction |  |  |

PRM007civ/11

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 8.13 | Levels and sections reduced to ordnance datum by relation to bench mark |  |  |
| 8.14 | Position and description of bench marks or other datum points |  |  |
| 8.15 | Septic tanks |  |  |
| 8.16 | Manholes: invert and cover levels |  |  |
| 8.17 | Gullies |  |  |
| 8.18 | Stopcocks |  |  |
| 8.19 | Hydrants |  |  |
| 8.20 | Overhead wires |  |  |
| 8.21 | External lighting |  |  |
| 8.22 | Consecrated ground (Graves, etc.) |  |  |

REMARKS:

NAME:........................................ DATE:....................................

9.	Buildings:  Construction general

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 9.01 | Roof: - construction, covering, pitch - construction, covering, pitch - roof lights, hatches - chimneys: flues, evidence of smoke or leaks in roof space, headroom - rainwater disposal, pipes, gutters, heads - flashing - aerials, wires - access on to roof and into roof space |  |  |
| 9.02 | Walls: - construction: e.g. bond, gauge, type of brick - finishes, rendering, pointing - DPCs - flashing, coping - air bricks - windows, sills, lintels - doors, sills, lentils - pre-fabricated - other |  |  |

PRM007civ/12

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 9.03 | Basements: - level of floor below ground - ventilation - damp proofing - drainage etc. - fire protection |  |  |
| 9.04 | Floors: - construction: for timber floors; direction of joints, beams. Trimmers, details of other types of floor construction - sleeper walls - DPCs - air bricks |  |  |
| 9.05 | Stairs: - construction - floor to floor height - number of risers - hand rails |  |  |

REMARKS:

10.	Buildings:  Room by room

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 10.01 | Floor including skirting |  |  |
| 10.02 | Walls including dado rail, cornice, air bricks |  |  |
| 10.03 | Ceiling |  |  |
| 10.04 | Doors including frame, architrave and ironmongery |  |  |
| 10.05 | Electrical including fittings, sockets, switches |  |  |
| 10.06 | Heating and ventilation including radiators, valves, grilles, cookers, stoves, fireplaces |  |  |
| 10.07 | Sanitary fittings including baths, Lbs, WCS and cisterns, bidets, sinks, pipes, taps, internal manholes |  |  |

PRM007civ/13

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 10.08 | Joinery fittings including cupboards, shelving, benches |  |  |
| 10.09 | Miscellaneous |  |  |

REMARKS:

11.	Buildings:  Water supply

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 11.01 | Stopcocks: main supply and point of entry (Brass, chrome plated, PVC, etc.) |  | DZB |
| 11.02 | Drain cocks |  |  |
| 11.03 | Piping |  |  |
| 11.04 | Circuits and external water points |  |  |
| 11.05 | Insulation |  |  |
| 11.06 | Cisterns, size supports, insulation access |  |  |
| 11.07 | All sanitary fittings and services, including taps, traps, puff pipes, wastes |  |  |
| 11.08 | Shower floor and fittings/walls |  |  |
| 11.09 | Adequacy and type of supply, pressure hardness, need for analysis, e.g. well water, lead pipes carrying soft water, wells, springs, underground or under-floor storage tanks, pumps or rams |  |  |

12.	Buildings:  Drainage

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 12.01 | Surface water: record plan, levels, disposal means |  |  |
| 12.02 | Sewage: record plan, levels, disposal means, if combined system or otherwise |  |  |
| 12.03 | Manholes: invert and cover levels |  |  |
| 12.04 | Gullies, vent pipes, fresh air inlets, interceptors, grease traps, pumps (test pipes and manholes by water test) |  |  |
| 12.05 | Flood line information. See Section F |  |  |

REMARKS:

PRM007civ/14

13.	Buildings:  Hot water

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 13.01 | Systems |  |  |
| 13.02 | Piping |  |  |
| 13.03 | Circuit |  |  |
| 13.04 | Drain cocks |  |  |
| 13.05 | Cylinder |  |  |
| 13.06 | Insulation |  |  |
| 13.07 | Boiler and flue |  |  |
| 13.08 | Safety valve, thermometer, thermostat |  |  |
| 13.09 | Fuel and storage |  |  |
| 13.10 | Efficiency test and/or report from local specialist if necessary |  |  |
| 13.11 | Running costs |  |  |

14. 	Building:  Heating and ventilation

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 14.01 | System |  |  |
| 14.02 | Fittings, radiators, convectors, grilles, fans, filters, diffusers etc. |  |  |
| 14.03 | Piping |  |  |
| 14.04 | Circuits |  |  |
| 14.05 | Drain cocks |  |  |
| 14.06 | Expansion tank |  |  |
| 14.07 | Insulation |  |  |
| 14.08 | Boiler and flue |  |  |
| 14.09 | Safety valve, thermometer, thermostat, altitude gauges, fusible links, controls, pumps |  |  |
| 14.10 | Fuel and storage |  |  |
| 14.11 | Efficiency test and/or report from local specialist if necessary |  |  |
| 14.12 | Running costs |  |  |
| 14.13 | Refrigeration |  |  |

REMARKS:

PRM007civ/15

15.	Building:  Electrical

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 15.01 | Overhead or underground supply |  |  |
| 15.02 | Plot poles, wires or cable on survey |  |  |
| 15.03 | Meters and main switchgear, phasing, voltage, current, AC capacity in kVA |  |  |
| 15.04 | Wiring external and internal |  |  |
| 15.05 | System, conduits and earthing |  |  |
| 15.06 | Distribution boards |  |  |
| 15.07 | Light points and voltage including external lighting |  |  |
| 15.08 | Special fittings: fans, cooker panels, low voltage transformers, bell system |  |  |
| 15.09 | Test and report by local supply authority if necessary with advice on size and adequacy of main cable for future loading |  |  |

16.	Buildings:  Gas

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 16.01 | Cable size, depth and position |  |  |
| 16.02 | Meters: adequacy for future requirements |  |  |
| 16.03 | Points and fittings, flue, hoods, etc. |  |  |
| 16.04 | Test and report by local supply authority if necessary with advice on size and adequacy of main supply for future loading |  |  |
| 16.05 | Gas banks and types |  |  |

REMARKS:

PRM007civ/16

17.	Building:  Other services

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 17.01 | Telephone: overhead wires (plot poles on survey) |  |  |
| 17.02 | Lightning precautions and conductors |  |  |
| 17.03 | Steam |  |  |
| 17.04 | Compressed air |  |  |
| 17.05 | Standby electricity generators or UPS and batteries |  |  |
| 17.06 | Public address system |  |  |
| 17.07 | Lifts: hydraulic, electric or hand |  |  |
| 17.08 | Refrigeration |  |  |
| 17.09 | Escalators |  |  |
| 17.10 | Pneumatic tubes |  |  |
| 17.11 | Central vacuum |  |  |
| 17.12 | Closed circuit television, security systems etc. |  |  |

18.	Buildings:  Structural defects

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 18.01 | Dry tor and causes |  |  |
| 18.02 | Damp patches and causes |  |  |
| 18.03 | Evidence of rodents, woodworm, beetle (death-watch, Lyctus, etc.), insects |  |  |
| 18.04 | Recent repairs and decorations |  |  |
| 18.05 | Settlement cracks or misshapen openings, skirting or window gaps |  |  |
| 18.06 | Bulges in walls, walls out of plumb |  |  |
| 18.07 | Sagging roofs |  |  |
| 18.08 | Floors |  |  |
| 18.09 | Deflection on beams, lintels, etc. |  |  |
| 18.10 | Cracks at beam bearings |  |  |
| 18.11 | Smells |  |  |
| 18.12 | Condition of basements |  |  |

REMARKS:

PRM007civ/17

19.	Buildings:  Specialist fittings

| No. | Description | Yes/No | Comments |
| --- | --- | --- | --- |
| 19.01 | Altars, vestment presses, tabernacles |  |  |
| 19.02 | Engine pits, beds, ducts |  |  |
| 19.03 | Fire equipment: sprinklers, foam hydrants, etc., illuminated and other fire signs, hoses, extinguishers, locks, door closes, fire doors |  |  |
| 19.04 | Emergency lighting |  |  |
| 19.05 | Fire escapes |  |  |
| 19.06 | Fire routes |  |  |
| 19.07 | Stair cases |  |  |

20.	Buildings:  Reports

The architect or surveyor should carefully define in his report whether or not he was able to see inside the structure of a building. If able to do so, describe exactly how much he was able to see and where. The condition of the rest of the building should not be inferred from the sight of one piece of it. Back up with photographs, and/or drawings/diagrams.

A statement in terms stipulated the indemnity insurance policy, or similar to the following wording should be included at the end of the relevant section of the report, if required:

“It was not possible to make a detailed examination of either the floor or roof construction except at the positions described above, as to do so would have required material damage being done to obtain access. It is, therefore, impossible to make any statement on the condition of the un-examined structure”.

Where applicable, it should be advised to call in a specialist in rot, woodworm, etc., to make a more detailed examination.

OTHER REMARKS:

NAME: ................................ DESIGNATION: ……………………………. SIGNATURE: ................................ DATE: .............................

PRM008civ/1

# PRM008:  DETAIL PROJECT PLANNING PROGRESS REPORT

|  |  |  |  |  | WCS No: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | REFERENCE No: |  |  |
| PROJECT: |  |  |  |  |  |  |  |
| PRINCIPAL AGENT/CONSULTANT: |  |  |  |  |  |  |  |
| TEL: |  |  | FAX: |  |  |  |  |

NB:	Complete the planning progress report form and forward to the Project Manager.

| PREPARED BY: |  |  |  |  |
| --- | --- | --- | --- | --- |
| DATE |  |  |  | PRINCIPAL AGENT/CONSULTANT |

| DETAIL PROJECT PLANNING PROGRESS REPORT |  |  |  |  | DATE: 20__/__/__ TIME LAPSED: ___% |  |
| --- | --- | --- | --- | --- | --- | --- |
| USER DEPARTMENT |  |  |  |  |  |  |
| 1. PROJECT DESCRIPTION |  |  |  |  |  |  |
| TOWN |  |  |  | REGION |  |  |
| WCS No. |  |  |  | FILE No. |  |  |
| TENDER No. |  |  |  | CONTRACT SUM |  |  |
| CONTRACTOR |  |  |  | CONTRACT DURATION |  |  |
| 2. PROJECT TEAM |  |  | CONTACT PERSON |  |  | TEL No. |
| DPW PROJECT MANAGER |  |  |  |  |  |  |
| PRINCIPAL AGENT/CONSULTANT/ PROJECT MANAGER |  |  |  |  |  |  |
| CLIENT REPRESENTATIVE |  |  |  |  |  |  |

PRM008civ/2

| 3. PROJECT MILESTONES |  | PLANNED DATE | REVISED DATE | VARIANCE DAYS |
| --- | --- | --- | --- | --- |
| 3.1 | ISSUE FINAL PLANNING INSTRUCTION |  |  |  |
| 3.2 | ACCEPT FINAL PLANNING INSTRUCTION |  |  |  |
| 3.3 | BRIEFING OF CONSULTANTS |  |  |  |
| 3.4 | SUBMIT PLANNING SCHEDULE |  |  |  |
| 3.5 | SKETCH PLAN COMPLETION |  |  |  |
| 3.6 | SKETCH PLAN APPROVAL |  |  |  |
| 3.7 | PRELIMANARY DESIGN |  |  |  |
| 3.8 | PLANNING COMPLETION DATE |  |  |  |
| 3.9 | CONFIRMATION BY CLIENT |  |  |  |
| 3.10 | FUNDS FINAL APPROVAL |  |  |  |
| 3.11 | ADVERTISE TENDERS |  |  |  |
| 3.12 | AWARD TENDER |  |  |  |
| 3.13 | HAND OVER SITE |  |  |  |
| 3.14 | PRACTICAL COMPLETION CERTIFICATE |  |  |  |
| 3.15 | COMPLETION CERTIFICATE |  |  |  |
| 3.16 | FINAL APPROVAL CERTIFICATE |  |  |  |

| 4. PROJECT CASH FLOW |  | CONSTRUCTION | PROF FEES | TOTAL |
| --- | --- | --- | --- | --- |
| 4.1 | PROBABLE TOTAL COST |  |  |  |
| 4.2 | PREVIOUS YEARS EXPENDITURE |  |  |  |
| 4.3 | CURRENT FINANCIAL YEAR: |  |  |  |
| 4.3.1 | ORIGINAL CASH FLOW |  |  |  |
| 4.3.2 | LATEST REVISED CASH FLOW |  |  |  |
| 4.3.3 | ACTUAL EXPENDITURE THIS YEAR |  |  |  |
| 4.3.4 | % ACTUAL EXPENDITURE (4.5)/(4.4) |  |  |  |
| 4.3.5 | ESTIMATED UNDER/(OVER) EXPENDITURE (4.3) – (4.4) |  |  |  |
| 4.4 | FUTURE FINANCIAL YEARS: |  |  |  |
| 4.4.1 | ESTIMATED EXPENDITURE NEXT YEAR |  |  |  |
| 4.4.2 | ESTIMATED FUTURE EXPENDITURE |  |  |  |
| 5. CONSTRUCTION PROGRESS |  |  |  |  |
| 6. COMMENTS |  |  |  |  |

PRM009civ/1

# PRM009:  PROGRESS REPORT ON PROJECT APPRAISAL PHASE

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | WCS No: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | REFERENCE No: |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROGRESS REPORT FOR THE MONTH OF: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |
| 1. | Total progress to date is as shown on the attached bar chart. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. | Original completion date:- |  |  |  |  |  |  |  |  |  |  |  | Revised completion date:- |  |  |  |  |  |  |  |
| 3. | *The work is being delayed by |  |  |  |  |  |  |  |  |  |  | days/ahead of programme, due to the following:- |  |  |  |  |  |  |  |  |
| 4. | Brief summary of work done during the month:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | establishing Client/User needs:- |  |  |  |  |  |  |  |  | ( a ) Accommodation schedule: |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | ( b ) Inception checklist: |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | ( c ) General |  |  |  |  |  |  |  |  |  |  |
|  | Site investigation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Services requirements: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Space and Cost norms: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Original estimate: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Latest estimate of cost by PQS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. | Discussion held with:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. | Information required:- |  |  |  |  |  | 1. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 2. |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. | Remarks:- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * Delete which is not applicable |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DATE |  |  |  |  |  |  |  |  |  |  |  |  | PRINCIPAL AGENT/CONSULTANT |  |  |  |  |  |  |

PRM011Aciv/1

# PRM011A:  DOLOMITE STATUS CERTIFICATE DOLOMITE RISK MANAGEMENT SYSTEM

| PROVINCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDPW REGIONAL OFFICE |  | HO REF |  |  |  |  |  |  |  |  |  |  |  |  | RR REF |  |  |  |  |  |  |  |  |
| MAGISTERIAL DISTRICT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (1996 description) |  |  |  |  |
| DISTRICT COUNCIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCAL MUNICIPALITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Old/new name) |  |  |  |
| SUBURB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOWN/SUBURB EXTENSION NO. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SITE DESCRIPTION/NAME AND SUB-PORTION/SUB-UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BUILDING DESCRIPTION |  | FRN No. |  |  |  |  |  |  |  | No. |  |  |  |  |  | Name |  |  |  |  |  |  |  |
| MUNICIPAL ERF No.. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROPERTY CODE (NDPW) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SG CODE (21 DIGIT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FARM NAME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FARM No. (SG) |  | No. |  |  |  |  |  |  |  | Subdivision (portion) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT NAME (NDPW WCS SYSTEM NAME) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WCS No. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CLIENT DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NDPW PROPERTY |  |  |  | Yes |  |  |  |  | No |  |  |  |  | Lease |  |  |  |  |  |  |  |  |  |  |
| MAP REFERENCE |  | 1:50 000 |  |  |  |  |  |  |  |  |  |  | 1:10 000 |  |  |  |  |  |  |  |  |  |  |
| COORDINATES (dd: mm : ss) |  | Geographic reference |  |  |  |  |  |  | X (longitude) |  |  |  |  |  |  |  |  | Y (latitude) |  |  |  |  |  |
|  |  | Datum: |  |  |  |  |  |  | WGS84 |  |  |  |  |  |  |  |  | CAPE |  |  |  |  |  |
|  |  | Lo block: |  |  |  |  |  |  | Lo X : |  |  |  |  |  |  |  |  | LoY: |  |  |  |  |  |
| REPORT NO AND DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date submitted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RISK ZONE CLASS. | DESCRIPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | % OF SITE * |
| Class 1 Low risk | Residential, light industrial and commercial development provided that appropriate water precautionary measure is applied. Other factors affecting economic viability such as excavatability, problem soils, etc. must be evaluated. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Class 2 Medium risk | Residential development with remedial water precautionary measures. No site and service schemes. May consider for commercial or light industrial development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Class 3 Medium risk | Selected residential development with exceptionally stringent precautionary measures and design criteria. No site and service schemes. May consider for commercial or light (dry) industrial development with appropriate precautionary measures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM0011Aciv/2

| RISK ZONE CLASS. |  | DESCRIPTION |  | % OF SITE * |  |
| --- | --- | --- | --- | --- | --- |
| Class 4 Medium risk |  | Selected residential development with exceptionally stringent precautionary measures and design criteria. No site and service schemes. May utilise for commercial or light (dry) industrial development with appropriate stringent precautionary measures. |  |  |  |
| Class 5 High risk |  | These areas are usually not recommended for residential development but under certain circumstances selected residential development (including lower-density residential development, multi-storied complexes, etc.), may be considered, commercial and light industrial development. The risk of sinkhole and doline formation is adjudged to be such that precautionary measures, in addition to those pertaining to the prevention of concentrated ingress of water into the ground are required to permit the construction of housing units. |  |  |  |
| Class 6 High risk |  | These areas are usually not recommended for residential development but under certain circumstances high-rise structures or gentleman’s estates (stands 4 000m2 with 500m2 proven suitable for placing a house) may be considered, commercial or light industrial development. Expensive foundation designs may be necessary. Sealing of surfaces, earth mattresses, water in sleeves or in ducts, etc. |  |  |  |
| Class 7 High risk |  | No residential development. Special types of commercial or light industrial (dry) development only (eg. bus or trucking depots, coal yards, parking areas). All surfaces sealed. Suitable for parkland. |  |  |  |
| Class 8 High risk |  | No development, nature reserves or parkland. |  |  |  |
| NO RISK |  | Non Dolomitic site (No risk of sinkhole and doline formation) |  |  |  |
| * The proportional percentages of the site in general or the proportional percentages of the selected area of the site. Attach sketch to clarify. |  |  |  |  |  |

All infrastructure development, additions, reparations, maintenance and upgrading must comply with “PW 344 APPROPRIATE DEVELOPMENT OF INFRASTRUCTURE ON DOLOMITE: GUIDELINES FOR CONSULTANTS”

Manual - http://ads.asaqs.co.za/cpd.php?File_Name=DolomiteManual.pdf

Drawings - http://ads.asaqs.co.za/cpd.php?File_Name=DolomiteManual.html

OTHER SPECIFIC COMMENTS

Development potential

Foundation design

PRM0011Aciv/3

Site works

Monitoring

| Please ensure that PRM 006, 007, 011, 012 and 016 that relates to Dolomite conditions have been completed, together with any other relevant documents, as part of the Contract Documentation list of documents. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Departmental confirmation |  |  |  |  |  |
| The Directorate Civil and Structural Engineering (DRMS Unit) hereby confirms that the above-mentioned site / buildings fall on the Risk Zone Class as specified above. |  |  |  |  |  |
| Signature |  | Signature |  |  |  |
| DRMS Unit |  | D / Civil and Structural Engineering |  |  |  |
| Date |  |  |  | Date |  |

| Sketch attached: | Yes |  | No |  |
| --- | --- | --- | --- | --- |

PRM012civ/1

# PRM012:  ENVIRONMENTAL AND SOCIAL ASPECTS TO BE CONSIDERED

Issues to consider with regards to the future Environmental policy for DPW:

1.	SITE SELECTION:

Could the proposed development have a significant impact on, or be constrained by any of the following:

1.1	Degradation of atmosphere i.e.

Levels of air pollution

Production of offensive odours

1.2	Structures and sites of architectural, cultural or historic heritage, i.e.

Site or areas of historical value, religious or spiritual significance. The integrity of cultural resources.

1.3	Prominent landscape/geological features, i.e.

Conservation or recreational value of rivers, streams, lakes, wetland dams or islands.

1.4	Survival of rare or endangered animals/plant species, i.e.

Diversity of animal communities

Natural immigration of species

1.5	Compatibility with surrounds, i.e.

Aesthetic quality of the area

Need for additional recreational facilities

1.6	Land characteristics, i.e.

Natural drainage patterns

Water table

Ability to absorb run-off

Availability of or access to construction materials such as rock and gravel

Availability of topsoil or fill material

1.7	Water, i.e.

Level of water pollution/effect on irrigation schemes

  - Dolomite land

PRM012civ/2

2.	CONCEPT DESIGN:

2.1	Indoor air quality, i.e.

Natural ventilation/air movement

Maximum use of north/east orientation

Proper operation, maintenance, housekeeping

Building materials and methods

2.2	Acoustic, i.e.

Speech-privacy

Orientation of building with regards to roads etc.

2.3	Water efficient design and appliances, i.e.

Luminous environment

2.4	Maintaining physical contact with nature, i.e.

Protection of indigenous trees and other natural features

Minimise visual impact

Promote open green spaces for recreation

Promote safe and appropriate routes and facilities for pedestrians and cyclists

2.5	Minimise interference with natural systems, i.e.

Earth removals or excavations

Storm water run off

Ground water

2.6	Social acceptability, i.e.

Interface with community structures

Use of local skills

Incorporate training schemes

Labour intensive process (appropriate technology and design)

Task based payment (Civil work)

2.7	Compatibility with surrounds, i.e.

Promote public transport

Effect on views, overlooking and privacy

Lifestyle, neighbourhood character

Access for elderly, wheelchairs

PRM013civ/1

# PRM013:  AGENDA FOR COMPREHENSIVE PROJECT BRIEF

|  |  |  |  | WCS No: |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | REFERENCE No: |  |
| PROJECT: |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |
| VENUE: |  |  |  |  |  |
| DATE: |  |  |
| TIME: |  |  |

1.	Welcome/attendance register (All Consultants, DPW Specialist advisors where applicable and Client / User Department representative)

2.	Project description

3.	Interaction between Project manager, User/Client department and consultants

4.	Issuing and/or verification of information and/or forms/manuals/guidelines where applicable:

4.1	Planning instruction including comprehensive completed planning pro-forma

4.2	Space and cost limits

4.3	Preliminary estimate

4.4	Verification of existing accommodation - as-built drawings to be prepared by Consultants if no drawings available

4.5	Site clearance certificate (PTOB – Permission to Occupy and Build)

4.6	Availability of services

4.7	Relevant manual/information as well as Operational Guidelines for incorporating APP principles, etc. to be handed to each Consultant/discipline

4.8	Environmental impact study report

4.9	Landmark building recommendation (heritage buildings, etc.)

4.10	Correctness of site and site information (confirm soil tests)

4.11	Accommodation and planning requirements, confirmed by Client (further detail discussion / meeting to be arrange if required)

5.	The current Departmental polices regarding APP requirements must be strictly adhered to.

6.	Specific requirements by various disciplines and/or Client/User, e.g. air-conditioning, fire, smoke detection, fire prevention, lift installation, uninterrupted power supply (UPS) standby generator, communication systems, access and egress control, computer network, TV circuits, water and sewerage treatment installations, etc.

7.	Planning programme by Consultants.

8.	Principal Agent, in conjunction with Consultant team, to compile and submit planning programme according to pro-forma within one week of briefing meeting.  This information to be input on the WCS-system.

9.	Consultant team to recommend to Project Manager the composition of contracts in accordance with standard DPW practice.

10.	User department’s brief

11.	Comments by specialist advisor(s)

12.	Programme:	-	Target dates (within one week)

-	Progress report

13.	Questions

14.	Closing

PRM013civ/2

PRM013:  ATTENDANCE REGISTER:  COMPREHENSIVE PROJECT BRIEF

| PROJECT: |  |  |  |  | VENUE: |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT MANAGER: |  |  |  |  | TIME: |  |  |  |  |  |
|  |  |  |  |  | DATE: |  |  |
| PURPOSE: |  |  |  |  |  |  |  |  |  |  |
| Present: |  |  |  |  |  |  |  |  |  |  |

| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | FAX No. | TELEPHONE No. | CELL PHONE No. | E-MAIL ADDRESS | SIGNATURE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |
| Apologies: |  |  |  |  |  |  |  |  |
| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | FAX No. | TELEPHONE No. | CELL PHONE No. | E-MAIL ADDRESS | SIGNATURE |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |

PRM013civ/3

PRM013:	MANUALS AND/OR GUIDELINES AVAILABLE ON THE DPW WEBSITE FOR CONSULTANTS WHEN APPLICABLE

PRIVATE CIVIL ENGINEERS

| No. | MANUALS AND/OR GUIDELINES | WEBSITE |
| --- | --- | --- |
| 1. | Civil Engineering Manual April 2011 | PW 347/2011 |
| 2. | Specification of materials and Methods to be Used | PW 371 |
| Direct Contracts the following additional Specifications/Manuals should be used: |  |  |
| 3. | Example – Comprehensive services incorporating electrical installations (**) |  |  |

Direct Contracts (*) and Comprehensive Contracts (**) the following additional Specifications/Manuals should be used:

| 4. | Conditions of Contract (*) | DPW-05 |
| --- | --- | --- |
| 5. | Standard forms during the course of the contract should be obtained from the Project Manager (*) |  |
| 6. | Addendum to Notes to Consultant Quantity Surveyors (*) | QS 37E |
| 7. | APP Guidelines and Specifications for Contracts above or below R2 million (Labour and Material contracts) - Refer to QS37E above for guidance (*) |  |
| 8. | Training – Addendum B for Contracts of 6 months and more – refer to f. above – Requested by client (*) | PW 772 (2 docs) |
| 9. | Standard Conditions in respect of the supply, delivery and installation of Electrical and Mechanical equipment, plant and materials (*) | PW 379 |
| 10. | Particulars of Electrical Contractor (*) | PW 205E |
| 11. | Section C: Quality Specification for Material and Equipment of Electrical Installations (*) and (**) | Part 3 |

Notes:

1	Escalation for Direct or Nominated Sub-Contracts: For Contracts of more than 6 months contract period

2	Nominated/Selected Contracts is not preferred anymore. All Contracts should be either direct or comprehensive Contracts.

PRM014/6civ

# PRM014/6:  MONTHLY PROGRESS REPORT ON CIVIL ENGINEERING DESIGN

For attention:

WCS No:	_________________

REFERENCE No:	_________________

1.	Mr/Ms                                             	Departmental Project Manager

2.	Mr/Ms                                             	Principal Agent/Lead Consultant

Report on progress for the month and year of:  _______________________________________

PROJECT:	_________________________________________________________________

_________________________________________________________________

Consulting Engineer:	___________________________________________________________

| 1. PROGRESS |  |  | PRELIMINARY REPORT |  | DOCUMENTATION |
| --- | --- | --- | --- | --- | --- |
|  | Authorised starting date | Programmed completion date |  |  |  |
| Roads ____________________ |  |  |  |  |  |
| Stormwater ________________ |  |  |  |  |  |
| Water Reticulation __________ |  |  |  |  |  |
| Sewerage _________________ |  |  |  |  |  |
| Other ____________________ Service as whole ___________ |  |  |  |  |  |
| TARGET DATES Can target dates be met YES/NO? ______________ If no, give a date that can be met ___________________________________________ |  |  |  |  |  |
| ESTIMATE THIS MONTH ____________________________________ ESTIMATE LAST MONTH ___________________________________ |  |  |  |  |  |

REMARKS: (give reasons for revised estimate or target dates)

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

SIGNATURE:	__________________		DATE:	_____________________

(Consulting Civil Engineer)

|  |  |  |  |  |  |  |  |  |  | PRM015civ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # PRM015: PROGRESS/BAR CHART |  |  |  |  |  |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  | WCS No: |  |  |
| PRINCIPAL AGENT/CONSULTANT: |  |  | TEL: |  | FAX: |  |  | REFERENCE No: |  |  |

| MILESTONES/ ACTIVITIES | MONTHS | PLANNED: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MONITORED: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | WEEKS | APRIL 2011 |  |  |  |  |  |  | MAY 2011 |  |  |  |  |  |  |  |  | JUNE 2011 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | JULY 2011 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DATES | 1 |  |  | 2 |  | 3 |  | 4 |  | 5 |  |  | 6 |  |  | 7 | 8 |  |  |  |  |  | 9 |  |  | 10 |  |  |  |  |  | 11 |  | 12 |  |  |  | 13 |  |  |  | 14 |  | 15 |  | 16 |  |
|  |  | 7-11 |  |  | 14-18 |  | 21-25 |  | 5-9 |  | 12-16 |  |  | 19-23 |  |  | 26-30 | 2-6 |  |  |  |  |  | 9-13 |  |  | 16-20 |  |  |  |  |  | 23-27 |  | 30-4 |  |  |  | 7-11 |  |  |  | 14-18 |  | 21-25 |  | 28-1 |  |
| - Pre-design Phase | Duration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 appointment of consultants | 4 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 briefing of consultants | 9 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 verification of accommodation | 12 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 site investigation | 16 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 services requirements | 19 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 appraisal report | 19 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 approval by client | 21 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 pre-sign planning completion date | 16 DAYS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| REMARKS: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | PRINCIPAL AGENT/CONSULTANT |  |  |  | DATE |

PRM016/7civ/1

- PRM016/7civ:	SKETCH PLAN COMMITTEE MANUAL

SKETCH PLAN COMMITTEE MANUAL 2008 (Vers 7 Sep 09)

See part 6.4.3 page 33 to 40 for Civil Engineering:

6.4.3.1. Cover Page for Distribution to DPW Civil Engineer PRM 16/07

This form must be completed and signed by the Consultant Civil Engineer.  Attach form to the outside of the set of documentation for distribution purposes.

| WCS No: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REFERENCE No: |  |  |  |  |  |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |
| CONSULTANT |  |  |  |  |  |  |  |  |  |  |
| Tel: |  |  |  |  |  | Fax: |  |  |  |  |
| ITEM DESCRIPTION |  |  |  |  |  |  |  |  |  | YES | NO. |  |
| - The Concept and Viability has been completed in terms of conditions |  |  |  |  |  |  |  |  |  |  |  |  |
| - Concept and Viability report has been attached, see attached guideline and also refer to the engineer’s manual |  |  |  |  |  |  |  |  |  |  |  |  |
| - The design has been coordinated with architect. Note: see engineer’s manual for preliminary design documents |  |  |  |  |  |  |  |  |  |  |  |  |
| - The departmental engineer has been consulted |  |  |  |  |  |  |  |  |  |  |  |  |
| - The departmental engineer’s comments has been incorporated into the design, if not, state reasons below: |  |  |  |  |  |  |  |  |  |  |  |  |
| - Dolomite Status Certificate is attached. |  |  |  |  |  |  |  |  |  |  |  |  |

| Comments: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NAME |  |  |  | SIGNATURE |  |  |  |
| FIRM |  |  |  | DATE |  |  |  |
| For completion by the Principal Agent/Consultant/Architect /Engineer : |  |  |  |  |  | YES | NO |
| One set of architectural/Engineering drawings has been attached |  |  |  |  |  |  |  |
| NAME |  | SIGNATURE |  |  |  |  |  |
| DESIGNATION |  | DATE |  |  |  |  |  |
| For completion by the: DPW Civil Engineer |  |  |  |  |  |  |  |
| For Sketch Plan purposes the recommendation to the SPC Chairperson is : |  |  |  |  | ACCEPT/NOT ACCEPT the Sketch Plan design submitted. |  |  |
| NAME |  |  |  |  | SIGNATURE |  |  |
| DESIGNATION |  |  |  |  | DATE |  |  |
| COPY ON SKETCH PLAN FILE? |  |  |  |  |  |  |  |

PRM016/7civ/2

6.4.3.2. Documentation Required for Civil Engineering

SKETCH PLAN (CONCEPT AND VIABILITY (PRELIMINARY DESIGN)) STAGE - (CIVIL ENGINEERING)

General Comment

The Department of Public Works has a large and diverse property portfolio. Various Departmental Guidelines have been prepared to assist Professional Consultants in the design and documentation of NDPW Projects. They provide direction and guidance on DPW’s requirements and enable Consultants to efficiently translate them into acceptable design solutions.

The Guidelines are not intended to replace the level of initiative, competence and care as expected of consultants in the performance of their duties. Consultants are encouraged to carefully consider the merits of the Design Guidelines in the context of the needs of individual projects. If a Consultant considers a guideline not to be appropriate and that a more suitable solution is available, proposals to this effect should be raised for consideration by the Department.

In the absence of express written approval for a deviation from Departmental guidelines, the Department will assume that the requirements contained in the various Design Guidelines have been fully addressed and incorporated in the proposed Design Solution and Specifications.

Design calculations and investigations should be performed through all stages in an orderly, logical way. They should not only allow the design engineer to arrive at conclusions sufficient to lead to the preparation of detailed drawings, but their final form should reflect neat and systematic thought processes. At any time in the future someone wanting to check back on the original design should be able to find out what the design engineer was trying to achieve and what design standards he used.

The engineer must take particular care in presenting the work connected with his design to ensure that:

- The design processes themselves are orderly, legible and logical so that the engineer charged with the checking should be able to follow them with ease;

- The technical and academic quality is acceptable; and

- Adequate draughting standards are complied with.

The Preliminary Design Report (PDR) gives the designer the opportunity to set out the design considerations and obtain approval for proposed deviations from Departmental standards. Where various options exist to arrive at a suitable design solution, the Department can select the preferred configuration based on information presented in the PDR. To enable the Departmental Civil Engineer to endorse the civil design at Sketch Plan Stage, the designer must have submitted a PDR documenting all facets of the design, to the Department.

The following section proposes a checklist that should be completed by the Project Manager and Professional Consultant to ensure that the Departmental Civil Engineer has sufficient project detail to enable him to check the design proposal:

Proposed Sketch Plan Checklist for the Civil Engineering portion of the design

(Note: 	Although not specifically related to the Civil Engineering, the EIA and Heritage requirements of a project as well as any interface with Service Providers and Municipalities must be addressed in detail at sketch plan stage as they could have a substantial impact on the cost of the works.)

The checklist is generic and some of the listed items/activities may not be applicable to the particular project under review. Provision must be made for a response of Not Applicable and perhaps In Process. Generally most of the aspects should be addressed in the PDR but it can be possible that some of the processes haven’t been taken to conclusion (EIA for example) before submitting the PDR.  An objective decision on allowable exclusions will have to be made by the Project Manager after consultation with the Departmental Civil Engineer so that the Sketch Plan approval is not delayed.

SKETCH PLAN (DESIGN DEVELOPMENT) STAGE - (CIVIL ENGINEERING)

The questions/statements below require a Yes /No /Not Applicable response:

| 1. General |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | The Project Manager briefed Departmental Civil Engineer on client requirements and facility configuration. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The Civil Consultant has discussed design options/details with the Departmental Civil Engineer. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Environmental Impact Assessment: |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  | i) | Application for exemption was made. |  |  |  |  |  |  |  |  |  |  |  |
|  | ii) | Scoping report was compiled and submitted. |  |  |  |  |  |  |  |  |  |  |  |
|  | iii) | Full EIA process is required by DEAT and has been initiated. |  |  |  |  |  |  |  |  |  |  |  |
|  | iv) | ROD was obtained. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Have the requirements of the local municipality been established and taken into consideration in the design proposal? |  |  |  |  |  |  |  |  |  |  |  |
|  |  | If a services report is required by the Municipality or Service Provider has it been compiled and submitted? |  |  |  |  |  |  |  |  |  |  |  |
| 2. Preliminary Design Report (PDR) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | A Preliminary Design Report (PDR) has been drafted in accordance with Clause B 1.4 of PW347 – Civil Engineering Manual, and has been forwarded to Departmental Civil Engineer. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The PDR includes the following: |  | YES |  |  |  | NO |  |  |  | N/A |  |
| a). General |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A Clear description of required facilities as defined by the Client Department. Definition includes function and purpose of facilities; the number and classes of occupants; periods of usage and usage patterns; all farming, abattoir or business activities listed separately. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation by the Architect or Principal Agent that the description of the facility in the Engineer’s PDR is accurate and complete. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Append letter of confirmation to the report. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A summary of the Site Clearance information from the Site Clearance Report-Town Planning; problems identified at site clearance stage. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Locality of project including a large scale - provincial locality map and a small scale map showing locality in town. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Design criteria clearly referenced to Departmental or other guideline documentation. Deviations from standards clearly indicated and motivated. |  |  |  |  |  |  |  |  |  |  |  |
| a). General (Continue) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Recommendations and motivation for further investigations, surveys and servitudes. |  |  |  |  |  |  |  |  |  |  |  |
| b). Water Supply |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | A preliminary assessment of water use as defined by the function or purpose of the facility. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Water demand per category calculated and presented in tabular form. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Tabled calculation of peak factors with reference to Departmental guidelines. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Local Fire Authority regulations and degree of assistance available from the Authority. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The facility classification in terms of fire risk. Tabled fire flow requirements with reference to Departmental or Fire Authority standard. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Layout drawing with position of municipal hydrants adjacent to site. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation in writing from municipality of sufficient capacity in the municipal water supply infrastructure. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of investigations (diurnal flow and pressure readings) confirming the capacity of the municipal infrastructure. (Alternative to the written confirmation from municipality above). |  |  |  |  |  |  |  |  |  |  |  |
|  |  | As-built data of Municipal water supply infrastructure. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of surveys, investigations, methodology and assumptions if as-built data is not available. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Verification of municipal water connection cost and the possibility of bulk water contribution cost. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A copy of the Service Level Agreement with the Service Provider is appended to this report. (Alternative to the verification of connection and bulk costs). |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Special requirements of the municipality and how these requirements have been incorporated in the design proposal. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Where borehole water is to be utilized, test results from yield and quality tests. Recommendations on usage and abstraction rates by Geo-hydrologist. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The conceptual design of river abstraction method. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | A recommendation on licensing requirements to utilize borehole or river water. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposals on water treatment, including disinfection, of borehole and river water. Results of the water quality analysis. |  |  |  |  |  |  |  |  |  |  |  |
| b). Water Supply (Continue) |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Water Storage requirements and proposal. Specific requirements of the user-department or requirements for fire fighting. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Confirmation that elevated storage towers are listed in EIA. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposed layout of water reticulation and placing of services. Pipe networks, ring mains etc. shown on sketch drawings. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Water supply design standards i.t.o materials, hydraulic specification, velocity, pressure limits and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Specifications of materials, valves, air valves, PRV’s, water meters etc. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Placement of water meters to monitor water usage. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | General arrangement and design basis for water supply pump stations, including operational control and standby capacity. |  |  |  |  |  |  |  |  |  |  |  |
| c). Storm Water |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Summary of statistical data of the nearest rainfall station. |  |  |  |  |  |  |  |  |  |  |
|  |  | The sub-catchment areas are shown on the layout plans. |  |  |  |  |  |  |  |  |  |  |
|  |  | Design criteria and calculation assumptions and methodology. |  |  |  |  |  |  |  |  |  |  |
|  |  | Design storm return period and tabulated runoff per sub-catchment. |  |  |  |  |  |  |  |  |  |  |
|  |  | A description of any specific design requirements in terms of storm water reuse or conduit size limitations. |  |  |  |  |  |  |  |  |  |  |
|  |  | Storm water design standards i.t.o materials, hydraulic specification, velocity, pressure limits and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |
|  |  | Flood line for the 1:100 year storm event shown on the layout plan. |  |  |  |  |  |  |  |  |  |  |
|  |  | Routing of storm water affecting cut and fill slopes on embankments or platforms. |  |  |  |  |  |  |  |  |  |  |
|  |  | Concept design of flood attenuating or control devices as well as a description of storm water management plan. |  |  |  |  |  |  |  |  |  |  |
| d). Sewerage |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | A preliminary assessment of sewer flow as defined by the function or purpose of the facility with tabulated results of calculations and design figures. |  |  |  |  |  |  |  |  |  |  |
|  |  | Table showing criteria and results of the peak factor calculations with reference to Departmental guidelines. |  |  |  |  |  |  |  |  |  |  |
| d). Sewerage (Continue) |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | General arrangement and design basis for sewerage pump stations; including sump design, instrumentation and standby capacity. |  |  |  |  |  |  |  |  |  |  |
|  |  | Description of the type and capacity of the sewerage collection system. |  |  |  |  |  |  |  |  |  |  |
|  |  | Capacity assessment of municipal sewer or written confirmation of capacity by municipality. |  |  |  |  |  |  |  |  |  |  |
|  |  | Location and accurate level of municipal sewer indicated on the layout drawing. |  |  |  |  |  |  |  |  |  |  |
|  |  | Assessment of sewerage treatment options. |  |  |  |  |  |  |  |  |  |  |
|  |  | Outcome of Licensing and sewerage treatment discussions with DWAF. |  |  |  |  |  |  |  |  |  |  |
|  |  | Does the EIA scoping report include the establishment of an on-site sewerage treatment works? |  |  |  |  |  |  |  |  |  |  |
|  |  | If on-site treatment has been proposed with irrigation of the final effluent, is there sufficient land available within the site boundary for irrigation. |  |  |  |  |  |  |  |  |  |  |
|  |  | Results of percolation tests if soak-aways are proposed. |  |  |  |  |  |  |  |  |  |  |
|  |  | Sewerage collection system design standards i.t.o materials, min slopes, hydraulic specification, velocity and roughness coefficients. |  |  |  |  |  |  |  |  |  |  |
|  |  | Specifications of special materials, valves, pumps, macerators, water meters etc. |  |  |  |  |  |  |  |  |  |  |
|  |  | Sewerage connection cost and the possibility of bulk sewer contribution cost. |  |  |  |  |  |  |  |  |  |  |
| e). Roads and Parking |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | The information relevant to vehicular traffic to be accommodated on the site eg. Vehicle type loading, frequency and definition of functional areas. |  |  |  |  |  |  |  |  |  |  |
|  |  | Road classification for different functional users. |  |  |  |  |  |  |  |  |  |  |
|  |  | Local Authority or the road owner’s regulations applicable to access. |  |  |  |  |  |  |  |  |  |  |
|  |  | Bulk contribution cost to municipality for access roads. |  |  |  |  |  |  |  |  |  |  |
|  |  | Results or recommendation on traffic study. |  |  |  |  |  |  |  |  |  |  |
|  |  | Applications lodged for way leaves. |  |  |  |  |  |  |  |  |  |  |
|  |  | Road and pavement design criteria. |  |  |  |  |  |  |  |  |  |  |
| f). Earthworks |  |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Final site layout obtained from Architect. |  |  |  |  |  |  |  |  |  |  |
|  |  | Platform elevations obtained from Architect. |  |  |  |  |  |  |  |  |  |  |
|  |  | Retaining wall requirements communicated with Structural Engineer. |  |  |  |  |  |  |  |  |  |  |
|  |  | Slope stability and method of stabilization detailed and motivated. |  |  |  |  |  |  |  |  |  |  |
|  |  | Preliminary cut and fill volumes calculated and balanced. |  |  |  |  |  |  |  |  |  |  |
|  |  | Proposed design standards for earthworks. |  |  |  |  |  |  |  |  |  |  |
|  |  | Borrow pits and Spoil sites have been identified. |  |  |  |  |  |  |  |  |  |  |
|  |  | Borrow pits and Spoil sites were included in EIA scoping report. |  |  |  |  |  |  |  |  |  |  |
| g). Construction Specifications and Form of Contract |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Construction Standard Specifications e.g. SANS 1200; COLTO. |  |  |  |  |  |  |  |  |  |  |
|  |  | Form and Conditions of contract specified e.g. GCC 2004, JBCC. |  |  |  |  |  |  |  |  |  |  |
| h). Cost Estimate |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Cost estimate and comparison of the various design options. |  |  |  |  |  |  |  |  |  |  |
|  |  | Life cycle cost where needed to motivate between options and select final design configuration. |  |  |  |  |  |  |  |  |  |  |
| i). Appendices |  |  | YES |  |  |  | NO |  |  |  | N/A |  |
|  |  | Confirmation by the Architect or Principal agent that the description in the Engineers PDR is accurate and complete. |  |  |  |  |  |  |  |  |  |  |
|  |  | Summary and Recommendations from Site Clearance Report. |  |  |  |  |  |  |  |  |  |  |
|  |  | EIA – Record Of Decision (ROD). |  |  |  |  |  |  |  |  |  |  |
|  |  | Marked up architects drawings showing concept design and layout of roads and parking; bulk water supply and water reticulation; sewerage reticulation, sewer outfall, sewerage treatment, effluent or alternative sewerage disposal; storm water catchments, collection and conveyance systems. |  |  |  |  |  |  |  |  |  |  |

| i). Appendices (Continue) |  |  | YES |  | NO |  | N/A |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | General arrangement of pump stations. |  |  |  |  |  |
|  |  | Recommendations of Geotechnical Investigations. |  |  |  |  |  |
|  |  | Recommendations of Traffic Study. |  |  |  |  |  |
|  |  | Correspondence with Local Municipality including Service Level Agreement (SLA). |  |  |  |  |  |
|  |  | Correspondence/ ROD - Road Owner. |  |  |  |  |  |
|  |  | Way leave applications. |  |  |  |  |  |
|  |  | Photos of typical or specific site characteristics. Results of Water and Sewerage investigation. |  |  |  |  |  |
|  |  | Results of Water and Sewerage investigation. |  |  |  |  |  |
|  |  | Explanatory drawings, typical details or typical road cross sections. |  |  |  |  |  |

j)	Dolomite Issues

During the design or execution (Construction) stage of the project the Project Manager (PM), consultant team and contractor should be alert and pro-active in locating and/or detecting any trace or sign of the presence of dolomite.

Should this be found, it must immediately be brought to the attention of the PM and the designated official responsible for dolomite matters at the Regional office/ Head office.

As and where applicable, appropriate designs/specifications/details for dolomite conditions should conform to the Department’s manual:  “Appropriate development of infrastructure on dolomite”, Document PW 344.

Should there be any uncertainty about the presence of dolomite and/or unscheduled ground movement event, then such enquiries should be referred to the Directorate: Civil & Structural Engineering at Head Office for further investigation and subsequent certification.

PRM017civ/1

# PRM017:  SUBMISSION OF DRAWINGS TO LOCAL AUTHORITIES

(IN TERMS OF THE NATIONAL BUILDING REGULATIONS AND BUILDING STANDARDS ACT 1977, (ACT NO 103 OF 1977).

| To: Local Authority: |  |
| --- | --- |

| Project: |  |
| --- | --- |
| WCS: |  |
| File Reference: |  |

In terms of section 2(4) of Act No 103 of 1977, receive herewith, for your information and comments, the following drawings and particulars in respect of the said project:

| DESCRIPTION: | DRAWING NUMBERS: |
| --- | --- |
| Site Plan(s): |  |
| Layout Drawings: (1:100 Scale Plans, Sections and Elevations plus relevant details) |  |
| Fire Installation Drawing(s): (Including water reticulation system to fire fighting equipment) |  |
| Drainage Installation Drawing(s): (Sewer- and storm water) |  |
| Structural Drawing(s): |  |
| Detail(s) of Artificial Ventilation: |  |
| Other: |  |

PRM017civ/2

It is hereby certified that the building(s) to be erected / upgraded will comply with the National Building Regulations, issued in terms of Act 103 of 1977, and will only deviate, in terms of prior negotiations with your office, in respect of:

| Submitted on Behalf of The Department of Public Works By: | (Name of Firm)* |
| --- | --- |
| Address: | (Address of Firm)* |
| Signed: |  |
| Capacity: |  |
| Date: |  |

The above has been verified, certified herewith and presented to the Local Authority in terms of Regulation A1(2) of the National Building Regulations, issued in terms of Act 103 of 1977.

| Signed: |  |
| --- | --- |
| Capacity: | (Project Manager)* |
| Date: |  |

| Signed: |  |
| --- | --- |
| Capacity: | (Regional Manager / Chief Director: Development Operations)* |
| Date: |  |

__________________

For: DIRECTOR-GENERAL

DATE: __________________

* For info only – to be deleted in actual submissions

PRM018civ/1

# PRM018:  SCHEDULE OF CONSTRUCTION AND FINISHES, 
USE FACTOR ANALYSIS AND ESTIMATE

| PROJECT : |  | WCS No: |  |  |
| --- | --- | --- | --- | --- |
|  |  | REFERENCE No: |  |  |

This form is to be completed by the private Architect in every detail and submitted with the Sketch Plan and Sketch Plan Check List. Indicate applicable items by marking the appropriate line:-

| 1 | FOUNDATIONS |  |  | 4 | INTERNAL WALLING SYSTEM |
| --- | --- | --- | --- | --- | --- |
| 1.1 | FOOTINGS |  |  | 4.1 | Brick, plaster and paint.................................. |
| 1.1.1 | Conventional unreinforced concrete |  |  | 4.2 | Other (describe on separate sheet).............. |
|  | strip................................................................ | ___ |  | 5 | FLOOR FINISH |
| 1.1.2 | Reinforced concrete..................................... | ___ |  |  | TYPE :.............................. POSITION : ....................... |
| 1.1.3 | Foundation beams and piles average |  |  | 5.1 | Vinyl asbestos tiles...................................................... |
|  | length..................................metres................ | ___ |  | 5.2 | Granolithic................................................................... |
| 1.14 | Raft foundations……………………………... |  |  | 5.3 | Ceramic....................................................................... |
| 1.2 | FOUNDATION WALLING |  |  | 5.4 | Wood Mosaic.............................................................. |
| 1.2.1 | Brickwork (not reinforced)........................... | ___ |  | 5.5 | Concrete paving.......................................................... |
| 1.2.2 | Reinforced brick............................................ | ___ |  | 5.1 | Other (specify on separate sheet).............................. |
| 1.2.3 | Reinforced concrete.................................... | ___ |  | 6 | EXTERNAL SUN PROTECTION |
| 1.2.4 | Other (describe on separate sheet)…….… | ___ |  |  | Required? (Described on separate sheet).................. |
| 1.3 | FINISH |  |  | 7 | USE FACTOR ANALYSIS |
|  |  |  |  |  | Total area of building, all floors but excluding |
| 1.3.1 | Face brick..................................................... | ___ |  |  | basement ...................................square metres |
| 1.3.2 | Plaster and paint.......................................... | ___ |  |  | Total net usable area. excluding corridors, foyers |
| 1.3.3 | Precast terrazzo............................................ | ___ |  |  | toilets. engineering service rooms ............square metres |
| 1.3.4 | Other (describe on separate sheet)........... | ___ |  |  | Usable area expressed as a percentage of the total area |
|  |  |  |  |  | ..................................................................................... |
| 2 | SUPER STRUCTURE |  |  | 8 | ESTIMATE |
| 2.1 | Load bearing brickwork............................... | ___ |  |  | All inclusive estimate of cost of service excluding -VAT |
| 2.2 | Reinforced concrete frame.......................... | ___ |  |  | R.................................................................................. |
| 2.3 | Structural steel frame.................................... | ___ |  |  |  |
| 2.4 | Beam and panel slab floors......................... | ___ |  |  |  |
| 2.5 | Other (describe on separate sheet)............ | ___ |  |  |  |
| 3 | EXTERNAL WALLING SYSTEM |  |  |  |  |
|  | TYPE :...................... POSITION : .......................... |  |  |  |  |
| 3.1 | Brick with the following facings: | ___ |  |  |  |
| 3.1.1 | Face brickwork............................................. | ___ |  |  |  |
| 3.1.2 | Plaster and paint.......................................... | ___ |  |  |  |
| 3.1.3 | Precast terrazzo............................................ | ___ |  |  |  |
| 3.1.4 | Other (describe on separate sheet) | ___ |  |  |  |

__________________________________________________________________________________

Note:	Describe on a separate sheet any additional features likely to affect the estimate. If necessary, also elaborate in like manner on any items appearing on this sheet, quoting the relevant reference numbers

| PRIVATE ARCHITECT |  | PRINCIPAL AGENT/ CONSULTANT |
| --- | --- | --- |
| DATE |  | DATE |

| # PRM019: COST NORM REPORT (EXAMPLE) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PRM019civ/1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | ¦ |  | ESTIMATE INDEX 607.7 |  |  |  |  |  |  | 2026.36 SCU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. PROJECT PARTICULARS |  |  |  | PER CONSULTANTS: |  |  | ¦ |  | Comments by Dept: |  |  |  |  |  |  | RECOMMENDATION |  |  |  |  |  |  |  |  | Kop: |  |  |  | Gedruk |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Voet: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 PROJECT NAME: |  |  |  | DURBAN W.VILLE |  |  | ¦ |  | > Prison: Housing |  |  |  |  |  |  | Building cost exceeds cost limit with |  |  |  |  |  |  |  |  |  | Wydte: |  |  | 140 |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 REFERENCE NO: |  |  |  | 6301/1808/5/4A |  |  | ¦ |  | > WCS 005051 |  |  |  |  |  |  | 12.15%, but site devel. cost exceeds |  |  |  |  |  |  |  |  |  |  | Lengte: |  | 69 |  |  |  |  | DRUK |  |  |  |  | L10 |  |
| 1.3 SERVICE STATUS: |  |  |  | SKETCH PLANS (4) |  |  | ¦ |  | > Sketch plan estimate |  |  |  |  |  |  | the cost limit by far. We recommend |  |  |  |  |  |  |  |  |  | :: |  |  |  |  |  |  |  | MENU |  |  |  |  | L18 |  |
| 1.4 DATE OF ANALYSIS: |  |  |  | 96/03 |  |  | ¦ |  | > Date of estimate |  |  |  |  |  |  | that addition. SCU’s for Land |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TABEL1 |  |  |  |  | A2..M59 |  |
| 1.5 BUILDING COST INDEX: |  |  |  | 607.7 |  |  | ¦ |  | > Projected |  |  |  |  |  |  | Development & Abnormal Ground |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | /D |  |  |  |  | A1 |  |
| 1.6 INSPECTION REQUESTED: |  |  |  | DEPARTMENTAL |  |  | ¦ |  | > sketch plan committee |  |  |  |  |  |  | Conditions be allocated |  |  |  |  |  |  |  |  |  | DRUK {WINDOWSOFF} |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 FINAL COST: |  |  |  | 7,141,052.72 |  |  | ¦ |  | > Excluding fees and reserves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | {MENUBRANCH MENU} |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. SPACE NORM |  |  |  |  |  |  | ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 SPACE LIMIT: ASM |  |  |  | 3,397.00 |  |  | ¦ |  | > Approved by Treasury Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DRUK |  |  | G1 |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 PLANNED SPACE: ASM |  |  |  | 3,306.00 |  |  | ¦ |  | > Designed space |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MENU |  |  | G5 |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 RESERVE SPACE: ASM |  |  |  | (91.00) |  |  | ¦ |  | > Complies with space limit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | /D |  |  | A2 |  |  |  |  |  |  |  |  |  |  |  |
| 2.4 GROSS AREA: GSM |  |  |  | 3,306.00 |  |  | ¦ |  | > 2% Over & 10% under provision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. COST ANALYSIS |  |  |  |  |  |  | ¦ |  | > is allowable |  |  |  |  |  |  |  |  |  |  |  | MENU |  | Een Druk |  |  |  |  |  |  |  | Twee Druk |  |  |  |  |  |  | Quit |  |  |
| 3.1 RATE/GROSS M2: R/m2 |  |  |  | 2,160.03 |  |  | ¦ |  | > Norm rate = R 1 843.53/m2 |  |  |  |  |  |  |  |  |  |  |  |  |  | Om tabel1 te druk |  |  |  |  |  |  |  | Om tabel2 te druk |  |  |  |  |  |  | Quite print program |  |  |
| 3.1.1 BUILDINGS: R/m2 |  |  |  | 1,913.64 |  |  | ¦ |  | > Norm rate = R 1 635.23/m2 |  |  |  |  |  |  |  |  |  |  |  |  |  | /PPCAOH |  |  |  |  |  |  |  | /PPCAOH |  |  |  |  |  |  | {GOTO}A1~ |  |  |
| 3.1.2 SITE: R/m2 |  |  |  | 246.39 |  |  | ¦ |  | > 12.88% of building cost (limit = 18.39%) |  |  |  |  |  |  |  |  |  |  |  |  |  | IIGedruk: @ ~ |  |  |  |  |  |  |  | IIGedruk: @ ~ |  |  |  |  |  |  | {QUIT} |  |  |
| 3.1.3 SECURITY: R/m2 |  |  |  | 0.00 |  |  | ¦ |  | > 00.0% of building cost (limit = 00.0%) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | F |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |
| 3.2 DPW INDEX RATE: |  |  |  |  |  |  | ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | IIBladsy # ~ |  |  |  |  |  |  |  | IIBladsy # ~ |  |  |  |  |  |  |  |
| 3.2.1 PROJECTED: Ie |  |  |  | 284.35 |  |  | ¦ |  | > Forecasted by MFA |  |  |  |  |  |  | PROJECT MANAGER |  |  |  |  |  |  |  |  | ML10~ |  |  |  |  |  |  |  | ML10~ |  |  |  |  |  |  |  |
| 3.2.2 FINAL: Ie |  |  |  | 320.39 |  |  | ¦ |  | > Price level of estimate |  |  |  |  |  |  | DATE: |  |  |  |  |  |  |  |  | MR140~ |  |  |  |  |  |  |  | MR140~ |  |  |  |  |  |  |  |
| 3.2.3 DEVIATION: % |  |  |  | 12.67 |  |  | ¦ |  | > Allowable deviation 55 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MT0~ |  |  |  |  |  |  |  | MT0~ |  |  |  |  |  |  |  |
| 3.3 ECONOMICAL DESIGN |  |  |  |  |  |  | ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MB0~ |  |  |  |  |  |  |  | MB4~ |  |  |  |  |  |  |  |
| 3.3.1 ASSIGNABLE M2: % |  |  |  | 100.00 |  |  | ¦ |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | P69~ |  |  |  |  |  |  |  | P69~ |  |  |  |  |  |  |  |
| 3.3.2 NON ASIGN. M2: % |  |  |  | 0.00 |  |  | ¦ |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | QCRR |  |  |  |  |  |  |  | QCRR |  |  |  |  |  |  |  |
| 3.3.3 USE FACTOR: |  |  |  | 1.00 |  |  | ¦ |  | > Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TABEL1~ |  |  |  |  |  |  |  | TABEL2~ |  |  |  |  |  |  |  |
| 4. COST NORM |  |  |  |  |  |  | ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A~GCA |  |  |  |  |  |  |  | A~GCA |  |  |  |  |  |  |  |
| 4.1 APPROVED SCU’S: SCU |  |  |  | (0.36) |  |  | ¦ |  | > Approved by Accommodation Control |  |  |  |  |  |  | DECISION |  |  |  |  |  |  |  |  | Q |  |  |  |  |  |  |  | Q |  |  |  |  |  |  |  |
| 4.2 COST LIMIT: |  |  |  | 0.00 |  |  | ¦ |  | > Cost limit at 96/03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 FINAL COST: |  |  |  | 8,837,052.74 |  |  | ¦ |  | > Estimated cost including 10% reserves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | {MENUBRANCH MENU {MENUBRANCH MENU} |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4 RESERVE FUNDS: |  |  |  | (8,837,052.74) |  |  | ¦ |  | > Does not comply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5 DEVIATION: |  |  |  | ERR |  |  | ¦ |  | > |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reconciliation of the separate cost limits, including professional fees and reserve funds: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PARTICULARS |  |  | ¦ | COST LIMIT |  | ¦ |  | FINAL COST |  |  | ¦ | DIFFERENCE |  |  | ¦ |  | % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Building development cost |  |  | ¦ | 6,675,402.89 |  | ¦ |  | 7,486,566.86 |  |  | ¦ | (811,163.97) |  |  | ¦ |  | -12.15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site development cost |  |  | ¦ | (6,842,265.12) |  | ¦ |  | 1,008,026.22 |  |  | ¦ | (7,850,291.33) |  |  | ¦ |  | -778.78 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Abnormal ground conditions |  |  | ¦ | 166,862.23 |  | ¦ |  | 342,459.56 |  |  | ¦ | (175,597.33) |  |  | ¦ |  | -105.23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Space limit: | Complies with the approved space limit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cost limit: | The building deviates with 12.15%, but the site dev. Cost does not comply with the approved cost limit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recommendation: | Space and cost norms to be adapted for site Development and Building Abnormal Ground Conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER |  |  |  |  | DATE |  |  |  |  | AsD/Ab |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM019civ/2

PRM019:  CERTIFICATION THAT PROJECTS ARE WITHIN THE APPROVED SPACE AND COST NORMS

| PROJECT: |  | WCS No.: |  |
| --- | --- | --- | --- |
|  |  | FILE No.: |  |
| PROJECT MANAGER: |  | DATE: |  |

| ESTIMATED VALUE OF PROJECT: |  |
| --- | --- |

|  |  | STAGES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Sketchplan |  | Tender |  | Completion |  |
|  |  | Signature | Date | Signature | Date | Signature | Date |
| 1 | Principal Agent/Consultant |  |  |  |  |  |  |
| 2 | Project Manager |  |  |  |  |  |  |
| 3 | Chief Regional Project Manager |  |  |  |  |  |  |
| 4 | Regional Manager |  |  |  |  |  |  |
|  | D/MP; D/PAS; D/Risk M |  |  |  |  |  |  |

PRM031/1civ/1

# PRM031/1civ:  AGENDA FOR SITE HANDOVER MEETING

(Possession of Site)

| File Number |  |  |
| --- | --- | --- |
| WCS Number |  |  |
| Project Title |  |  |
| Project Manager | Name |  |
|  | Tel |  |
|  | Fax |  |
|  | Cell |  |

NOTE:		This pro-forma serves only as an example of the site meeting agenda and should be project 	specific (Architects Manual)

The site handover cannot take place without items.5.2 & 5.8 having been complied with in all respects

(Departmental PM to delete when form is customised)

| 1. |  |  | PRINCIPAL AGENT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2. |  |  | CONTRACTOR: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. |  |  | MEETING NUMBER: |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. |  |  | DATE OF MEETING: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. |  |  | CONTRACT INFORMATION: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 |  |  | Contract Sum: |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |
| 5.2 |  |  | Priced Bill of Quantities received (Date): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 |  |  | Form of Security: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 |  |  | Contract Commencement Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 |  |  | Contract period: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.6 |  |  | Contract Completion Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.7 |  |  | Address at which contract is to be executed (Physical address of the site): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.8 |  |  | Health and Safety Plan Approval Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.9 |  |  | Environmental Management Plan: |  |  |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 5.10 |  |  | Heritage Site: |  |  |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 5.11 |  |  | EPWP / NYS |  |  |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 6. |  |  | INTRODUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 |  |  | Role Players. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 |  |  | Communication. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 |  |  | Scope of Work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. |  |  | ATTENDANCE REGISTER (at end of document) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | PRM031/1civ/2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. |  |  | CLERK OF WORKS / RESIDENT ENGINEER / ENVIRONMENTAL CONTROL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. |  |  | CONTRACTOR’S REPRESENTATIVE(S) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. |  |  | PROPERTY OWNER(S), GENERAL PUBLIC, LOCAL COMMUNITY, COMMUNITY LIAISON OFFICER, LOCAL AUTHORITIES, MOVEMENT INTO AND ON SITE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. |  |  |  | SUB-CONTRACTORS: CLAUSE 6 GCC or CLAUSE 23 JBCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. |  |  |  | THE PRINCIPAL AGENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. |  |  |  | OCCUPATIONAL HEALTH AND SAFETY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. |  |  |  | HIV/AIDS AWARENESS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. |  |  |  | PROGRESS / TECHNICAL MEETINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. |  |  |  | CONTRACT DOCUMENTS AND DRAWINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. |  |  |  | DRAWINGS AND DOCUMENTS TO BE HANDED OVER TO THE CONTRACTOR (http://www.publicworks.gov.za) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.1 | 1 x PW371 Standard Specification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.2 | 1 x Site instruction book (GCC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.3 | 1 x Visitors book |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.4 | 2 x sets of drainage details |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.5 | 2 x sets of Hardware sample list PW377 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.6 | 2 x copies of name board drawing, 1 x copy for contractor and 1 x copy for principal agent to prepare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.7 | 3 x sets of architectural drawings, as per drawing list. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.8 | 3 x sets of structural engineering drawings, as per drawing list. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.9 | 3 x sets of civil engineering drawings, as per drawing list. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.10 | 3 x sets of electrical engineering drawings, as per drawing list. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.11 | 3 x sets of mechanical engineering drawings, as per drawing list. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17.12 | Bills of quantities and specifications, 1 x priced copy plus 2 x blank copy, supplied by Quantity Surveyor. (One blank copy to be available on site) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 18. | CONTRADICTIONS IN THE DOCUMENTATION |
| --- | --- |
| 19. | SITE ESTABLISHMENT |
| 19.1 | Contractor’s Site Office |
| 19.2 | Contractor’s Camp site |
| 19.3 | Housing and Accommodation |
| 19.4 | Electricity and Water |
| 19.5 | Effluent and Garbage Disposal |
| 19.6 | Working Hours |
| 19.7 | Telephone and fax services |
| 19.8 | Notice board |
| 20. | MEASURING AND PAYMENTS |
| 21. | CONTRACT INSTRUCTIONS / SITE INSTRUCTIONS AND VARIATION ORDERS |
| 22. | FUNDS |
| 23. | BANKING DETAILS OF Contractor |
| 24. | REVISION OF DATE FOR PRACTICAL COMPLETION / Extension of TIME FOR COMPLETION |
| 25. | FINANCIAL REPORTS |
|  | PRM031/1civ/3 |
| 26. | BEACONS AND REFERENCE POINTS |
| 27. | INFORMATION, DRAWINGs and / or CONTRACT INSTRUCTIONS or VARIATION ORDERS required by the principal agent or the contractor |
| 28. | DAMAGE TO EXISTING SERVICES |
| 29. | CONTRACTOR’S PROGRAMME |
| 30. | PROGRESS |
| 31. | QUALITY |
| 32. | DISRUPTIONS |
| 33. | GENERAL |
| 34. | NEXT MEETING |
| 35. | APPROVAL OF MINUTES |

PRM031/1civ/4

PRM031/1:  ATTENDANCE REGISTER

| PROJECT: |  |
| --- | --- |
| VENUE: |  |
| TIME: |  |
| DATE: |  |
| MEETING DESCRIPTION: |  |

PRESENT:

| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | TELEPHONE NUMBER | FAX NUMBER | CELL PHONE NUMBER | EMAIL ADDRESS | SIGNATURE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  | PRM031/1civ/5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| APOLOGIES: |  |  |  |  |  |  |  |  |
| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | TELEPHONE NUMBER | FAX NUMBER | CELL PHONE NUMBER | EMAIL ADDRESS | SIGNATURE |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |

PRM031/2civ/1

# PRM031/2:  GUIDELINES FOR SITE HANDOVER MEETING MINUTES 	(Example)

(Possession of Site)

| File Number |  |  |
| --- | --- | --- |
| WCS Number |  |  |
| Project Title |  |  |
| Project Manager | Name |  |
|  | Tel |  |
|  | Fax |  |
|  | Cell |  |

NOTE:		This pro-forma serves only as an example of the meeting minutes and should be project specific (Architects Manual)

The site handover cannot take place without items 5.2 & 5.8 having been complied with in all respects

(Departmental Project Manager to delete when form is customised)

| 1. | PRINCIPAL AGENT/CONSULTANT: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2. | CONTRACTOR: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | MEETING NUMBER: |  |  |  | 1 |  |  |  |  |  |  |  |  |  |
| 4. | DATE OF MEETING: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. | CONTRACT INFORMATION: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Contract Sum: |  |  |  |  | R |  |  |  |  |  |  |  |  |
| 5.2 | Priced Bill of Quantities received (Date): |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 | Form of Security: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 | Contract Commencement Date: |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 | Contract period: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.6 | Contract Completion Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.7 | Address at which contract is to be executed (Physical address of the site) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.8 | Health and Safety Plan Approval Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.9 | Environmental Management Plan: |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 5.10 | Heritage Site: |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 5.11 | EPWP / NYS |  |  |  |  | Yes |  |  | No |  |  |  |  |  |
| 6. | INTRODUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Role Players |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | Communication. Communication between all parties must be done in writing through the office of the Principal Agent. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 | Scope of Work (Consultant / PM describes the scope of work and answers any questions specifically about the project and documents available). |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  |  | PRM031/2civ/2 |  |
| --- | --- | --- | --- | --- | --- |
| 7. |  | ATTENDANCE REGISTER (at end of document) |  |  |  |
| 8. |  | CLERK OF WORKS / RESIDENT ENGINEER / ENVIRONMENTAL CONTROL OFFICER |  |  |  |
|  |  | If a Clerk of Works / Resident Engineer / Environmental Control Office is required, a proper motivation must be submitted by the Principal Agent / Engineer to the Project Manager for approval process (Refer Architect’s Manual / Engineers Manual – www.publicworks.gov.za) |  |  |  |
| 9. |  | CONTRACTOR’S REPRESENTATIVE(S) |  |  |  |
|  |  | Contractor must make the name(s) available of his/her representative(s) for all contractual matters relating to the site as well as the name of his/her foreman and a responsible person in accordance with the Occupational Health and Safety Act. HIV/AIDS awareness plans to be formalized |  |  |  |
| 10. |  | PROPERTY OWNER(S), GENERAL PUBLIC, LOCAL COMMUNITY, COMMUNITY LIAISON OFFICER, LOCAL AUTHORITIES, MOVEMENT INTO AND ON SITE |  |  |  |
| 10.1 |  | Role of / and relationship between local community and the contracting parties. |  |  |  |
| 10.2 |  | Nobody will be allowed on site without the necessary approval/permission given by the Contractor and or the Client/Owner (e.g. Security areas, National Defence Force installations or any other required security arrangement). |  |  |  |
| 10.3 |  | At Government Security installations the following must be taken in consideration: |  |  |  |
| 10.3.1 |  | Access permits must be arranged. |  |  |  |
| 10.3.2 |  | All permits for deliveries must be arranged two days in advance of delivery and to reflect at least the vehicle drivers’ particulars and the vehicle registration number and access approval for everyone on and in the vehicle. |  |  |  |
| 10.3.3 |  | All workers must be accompanied by driver/overseer. |  |  |  |
| 10.3.4 |  | Any deviation from formal designated areas and access roads will not be permitted. Any employee of the Contractor roaming about outside the designated area will be prohibited from coming onto the site. |  |  |  |
| 10.3.5 |  | The Contractor must at all times endeavour to prevent complaints from the client and/or public due to his/her own or his/her employee’s action(s) out of context of the contract. |  |  |  |
| 10.4 |  | The Contractor must allow access to the site / works for any direct Contractor of the Department or the Client. |  |  |  |
| 11. |  | SUB-CONTRACTORS: CLAUSE 23 JBCC or CLAUSE 6 GCC |  |  |  |
|  |  | The names of all Sub-contractors to be employed by the Contractor during the contract period must be submitted to the Principal Agent for approval. Suppliers are not recognised as sub-contractors except where applicable. |  |  |  |
| 12. |  | THE PRINCIPAL AGENT |  |  |  |
|  |  | The Principal Agent and / or his delegated representative(s) (consultants) where required will be in charge of the administration of the Contract for supervision, quality control, financial control and this includes all nominated or direct contracts [example of indirect contracts: cell locks, radio equipment, telecommunications etc.] |  |  |  |
| 13. |  | OCCUPATIONAL HEALTH AND SAFETY |  |  |  |
| 13.1 |  | It is a specific requirement of this contract that the contractor provide the Principal Agent with the name of his/her appointed Occupational Health and Safety Officer, who needs to be on site full time, before commencement with any work on site |  |  |  |
| 13.2 |  | The Contractor needs to provide proof to the Principal Agent, prior to commencement of the work on site, of his registration of the project with the Department of Labour as per Regulation 3 of the Construction Regulations |  |  |  |
| 13.3 |  | The Contractor must provide the Principal Agent with proof of his registration with an approved Workmen Compensation Fund or Federated Employers Mutual Assurance Company (FEM) before the commencement of the work. |  |  |  |
| 13.4 |  | The Contractor must provide and maintain a Health and Safety File for his/her contract on site for the duration of the contract. The approved Health and Safety Plan must be filed in this file. The Health and Safety File must be handed over to the Department’s Health and Safety officials at Works Completion / Completion of Works, together with all relevant drawings as per Regulation 5 (8) of the Construction Regulations |  |  |  |
|  |  | PRM031/2civ/3 |  |  |  |
| 13.5 |  | A signed list of all staff on site who has received Health and Safety Induction training must be filed in the Health and Safety File |  |  |  |
| 13.6 |  | Departmental Health and Safety Officials will be at liberty to enter the site at any time. They do have the authority to stop work on site should a dangerous situation or contravention of the OHS Act be detected. They will also be entitled to initiate Safety Instructions and Notices of Contravention of the Act through the Project Manager / Principal Agent. |  |  |  |
| 13.7 |  | Should any temporary electrical supply for construction purposes be required then such a connection should comply with section 7.4 of SANS 10142 and a Certificate of Compliance in respect of such temporary electrical connection should be filed on the Health and Safety File. |  |  |  |
| 13.8 |  | The Contractor must immediately report in writing about any incident, occurrence or accident that may have Contractual implications. |  |  |  |
| 14. |  | HIV/AIDS AWARENESS |  |  |  |
| 14.1 |  | It is required that the contractor provide the Principal Agent with an HIV/AIDS Awareness Programme within 14 days from the date of the Site Hand Over. |  |  |  |
| 14.2 |  | The Contractor is to provide the Principal Agent with the name of the HIV/AIDS Awareness Champion within 14 days from the date of the Site Hand Over. |  |  |  |
| 14.3 |  | The Contractor to provide posters, booklets and a video on compact disc for HIV/AIDS. The posters need to be displayed at the site office and booklets be made available to all staff members requiring further information on the subject. The video is to be shown to all staff employed on site and an attendance register is to be kept on site on the Health and Safety File. (Refer to manual for HIV / AIDS Awareness) |  |  |  |
| 14.4 |  | Contractor to provide the Principal Agent with the necessary reports on a monthly basis. |  |  |  |
| 15. |  | PROGRESS / TECHNICAL MEETINGS |  |  |  |
| 15.1 |  | Progress meetings shall take place at least monthly and should be supported by a technical meeting alternating fortnightly or any other regular arrangement if so requested. |  |  |  |
| 15.2 |  | All representatives at the meeting(s) must be delegated to take binding decisions, although it may be sometimes necessary to refer some decisions to higher authority. |  |  |  |
| 15.3 |  | Any decision with contractual implication taken at the meeting must be formalised in writing by means of a contract instruction / variation order if so required. |  |  |  |
| 15.4 |  | All important matters must be brought to the attention of the meeting timeously and supported by a written notification. |  |  |  |
| 15.5 |  | Any matters of a routine nature must be settled by the principal agent and the contractor’s representative before the meeting and only noted at the meeting if no agreement can be reached. |  |  |  |
| 15.6 |  | Special attention must be given at the meeting to the following: |  |  |  |
| 15.6.1 |  | Progress |  |  |  |
| 15.6.2 |  | Contract Instruction / Variation Orders |  |  |  |
| 15.6.3 |  | Delays and disruptions |  |  |  |
| 15.6.4 |  | Quality |  |  |  |
| 15.6.5 |  | Health and Safety Report. - Certification by relevant Consultants in terms of Construction Regulation 9(f) that the construction is in accordance with the design. - Representative report on Health and Safety. |  |  |  |
| 15.6.6 |  | HIV/AIDS Report |  |  |  |
| 15.6.7 |  | Environmental Management Report |  |  |  |
| 15.6.8 |  | Heritage Report |  |  |  |
| 15.6.9 |  | EPWP / NYS report |  |  |  |
| 15.7 |  | Any item being discussed will be allocated a unique reference number which will be published in the subsequent minutes until the problem has been solved. |  |  |  |
| 16. |  | CONTRACT DOCUMENTS AND DRAWINGS |  |  |  |
| 16.1 |  | Drawings and documents used for the contract must be properly filed for reference purposes and kept in a good condition on site until completion of the project. Drawings replaced must be submitted to the principal agent to be destroyed, which must also be done with all drawings on completion of the project. |  |  |  |
| 16.2 |  | It is important to note that the contractor will only be issued with three copies of each drawing. Additional copies required will be for the account of the contractor. |  |  |  |
|  |  | PRM031/2civ/4 |  |  |  |
| 17. |  | DRAWINGS AND DOCUMENTS HANDED OVER TO THE CONTRACTOR (http://www.publicworks.gov.za) |  |  |  |
| 17.1 | 1 x PW371 Standard Specification |  |  |  |
| 17.2 | 1 x Site instruction book (GCC) |  |  |  |
| 17.3 | 1 x Visitors book |  |  |  |
| 17.4 | 2 x sets of drainage details |  |  |  |
| 17.5 | 2 x sets of Hardware sample list PW377 |  |  |  |
| 17.6 | 2 x copies of name board drawing, 1 x copy for contractor and 1 x copy for principal agent to prepare |  |  |  |
| 17.7 | 3 x sets of architectural drawings, as per drawing list. |  |  |  |
| 17.8 | 3 x sets of structural engineering drawings, as per drawing list. |  |  |  |
| 17.9 | 3 x sets of civil engineering drawings, as per drawing list. |  |  |  |
| 17.10 | 3 x sets of electrical engineering drawings, as per drawing list. |  |  |  |
| 17.11 | 3 x sets of mechanical engineering drawings, as per drawing list. |  |  |  |
| 17.12 | Bills of quantities and specifications, 1 x priced copy plus 2 x blank copy, supplied by Quantity Surveyor. (One blank copy to be available on site) |  |  |  |

| 18. | CONTRADICTIONS IN THE DOCUMENTATION |  |  |
| --- | --- | --- | --- |
|  | Anything unclear or contradictory in the documents must be timeously brought to the attention of those involved and this also includes the non-availability of specified material. |  |  |
| 19. | SITE ESTABLISHMENT |  |  |
| 19.1 | Contractor’s Site Office |  |  |
|  | The site for the establishment of the Contractor’s Site Office must be co-ordinated with the Consultant Team. The site and facilities occupied by the Contractor must be kept neat and tidy at all times. |  |  |
| 19.2 | Contractor’s Camp site |  |  |
|  | Where the building site is within the confines of any other state owned site and also not near an existing town or city, a camp site and the access to the site to be used by the contractor and his staff will be pointed out to the Contractor. The camp site must be kept neat and tidy at all times. Or No space for the establishment of a camp site is available within the boundaries of the Site. |  |  |
| 19.3 | Housing and Accommodation |  |  |
|  | No housing or any accommodation for the Contractor and/or his/her staff on site will be allowed. |  |  |
| 19.4 | Electricity and Water |  |  |
|  | In the event of water and electricity to be supplied free of charge and problems are encountered, the contractor must supply his/her own water and electricity for construction purposes |  |  |
|  | The Department will not accept any responsibility for any breakdown of insufficiency in the supply of electricity or water to the site. Any temporary connections to the water and electricity supply from existing Departmental networks must be arranged with the Departmental Project Manager. Under no circumstances will the Contractor be allowed to draw water from a fire hydrant. |  |  |
|  | Where connections are required to available services, the necessary arrangements must be made with the local authority. |  |  |
| 19.5 | Effluent and Garbage Disposal |  |  |
|  | All sites must be kept hygienic with ablutions connected to existing systems |  |  |
| 19.6 | Working Hours |  |  |
|  | Working hours must be cleared with the principal agent in consultation with the client representative. |  |  |
| 19.7 | Telephone and fax services |  |  |
|  | Telephone and fax services to the site must be arranged by the contractor. |  |  |
|  | PRM031/2civ5 |  |  |
| 19.8 | Notice Board |  |  |
|  | The position of the notice board must be arranged with the Principal agent in consultation with the Clients representative. |  |  |
| 20. | MEASURING AND PAYMENTS |  |  |
| 20.1 | The Contractor shall be entitled to receive a monthly progress payment which shall be based on a progress payment certificate issued by the Principal Agent/Representative (Clause 31 of JBCC / Clause 8 of GCC). |  |  |
| 20.2 | The cost control of the contract is most important and the measuring of quantities at completion of work must be timeously finalized. No work must be covered until measured by the Consultant Quantity Surveyor/Engineer who has been given timeously notice of work completed. |  |  |
| 20.3 | The contractor must submit acceptable proof of ownership of material delivered on site before any payment advance may be given including proof that VAT has been paid. |  |  |
| 21. | CONTRACT INSTRUCTIONS / SITE INSTRUCTIONS AND VARIATION ORDERS |  |  |
| 21.1 | Contract/ Site instructions must be listed in the minutes. |  |  |
| 21.2 | Contract/ Site instructions being formal and binding will only be issued by the Principal Agent or his/her delegated representative (other consultants). Each instruction will be allocated a unique reference number to be quoted in all minutes and related correspondence. |  |  |
| 21.3 | Contract/Site instructions will be issued for the rectification of defective work with copies to the Contractor, Project Manager and all consultants. |  |  |
| 21.4 | Any instruction which may have a cost implication, a contract instruction / variation order, shall be issued only after permission has been obtained from the Project Manager. |  |  |
| 21.5 | The preparation of contract instructions / variation orders is fully described in the manuals and must be strictly adhered to and the following must also be taken in consideration: |  |  |
| 21.5.1 | When issuing instructions the availability of funds required must first be established. If this is not adhered to the principal agent will be held liable for unauthorised expenditure by the Department of Public Works. |  |  |
| 21.5.2 | The client / user cannot instruct consultant / contractor directly and any instruction required by the client must firstly be submitted to the Project Manager to be measured. If it is within the budget and if acceptable, the Project Manager will instruct the Principal Agent to issue the Contract Instructions / Variation Orders. |  |  |
| 22. | FUNDS |  |  |
| 22.1 | Savings on a contract is not owned by the contract but may facilitate requests for additional funds. |  |  |
| 23. | REVISION OF DATE FOR PRACTICAL COMPLETION / Extension of TIME FOR COMPLETION |  |  |
| 23.1 | All submissions of claims for a revision of the Date for Practical Completion / Extension of Time for Completion must be minuted in the meeting minutes progressively with an indication whether pending, approved or not approved. |  |  |
| 23.2 | Claims must be fully and acceptably motivated by the contractor and evaluated by the Principal Agent before submission to the Project Manager. |  |  |
| 23.3 | Claims or the intention to claim for a revision of the Date for Practical Completion must be dealt with strictly in accordance with Clause 29 of the JBCC / Clause 42 of GCC and no late claims will be entertained. |  |  |
| 24. | FINANCIAL REPORTS |  |  |
| 24.1 | Financial reports will be prepared by the Quantity Surveyor / Engineer and must be submitted to the Project Manager on a monthly basis via the Principal Agent all in accordance with the relevant Manuals. |  |  |
| 24.2 | The monthly reports must accurately reflect the financial standing of the project and must include detailed report on payments, cash flow projections and any incident that may influence the budget of the contract. |  |  |
| 25. | BEACONS AND REFERENCE POINTS |  |  |
|  | Pegs and any other formal reference points which indicate the borders of the site must be formally pointed out to the contractor and acknowledged by the contractor by signing the section of the document (PRM032): Acknowledgement of Handing Over of Site. |  |  |
|  | PRM031/2civ/6 |  |  |
| 26. | INFORMATION, DRAWINGs and / or CONTRACT INSTRUCTIONS or VARIATION ORDERS required by the principal agent or the contractor |  |  |
|  | This item must appear in the minutes of every meeting and is to be utilised for general information, enquiries and referring to Contract Instructions / Variation Orders. |  |  |
| 27. | DAMAGE TO EXISTING SERVICES |  |  |
| 27.1 | The Contractor and / or his staff will be held responsible for any damage to existing services. |  |  |
| 27.2 | Any damage to existing services must be reported to the Principal Agent immediately. |  |  |
| 27.3 | The arrangement to have the damage repaired must not be delayed. |  |  |
| 28. | CONTRACTOR’S PROGRAMME |  |  |
| 28.1 | The programme must be submitted to the Principal Agent by the contractor within 14 calendar days of handing over of site (Possession of Site). |  |  |
| 28.2 | The programme must be in the form of a Gantt Chart - indicating all activities and the critical path. |  |  |
| 29. | PROGRESS |  |  |
| 29.1 | The Contractor must report at each site meeting on progress against his/her programme. The Progress Report must indicate progress on all elements of the contract. |  |  |
| 29.2 | Progress report must indicate whether the contract is on time or running late. When running late the contractor must be informed in writing and requested to submit his plan of action to rectify the situation. |  |  |
| 29.3 | All Consultants must report to the Principal Agent about the progress of their disciplines. |  |  |
| 30. | QUALITY |  |  |
| 30.1 | This item will remain on the agenda for the run of the contract allowing the minuting of remarks on workmanship. |  |  |
| 30.1.1 | Satisfactory Work. |  |  |
| 30.1.2 | Unsatisfactory Work. |  |  |
| 30.2 | Contract / Site Instructions will be issued when unacceptable work is produced. |  |  |
| 31. | DISRUPTIONS |  |  |
| 31.1 | This item remains on the agenda for the run of the contract and as soon as any disruption occurs it must be reported to the Principal Agent. |  |  |
| 32. | GENERAL |  |  |
| 33. | FIRST SITE MEETING |  |  |
|  | The address, place, date, time of the regular meetings must be established for the foreseeable future. |  |  |
| 34. | APPROVAL OF MINUTES |  |  |
|  | All progress / technical meeting minutes must be approved by the following parties. |  |  |
| PRINCIPAL AGENT/CONSULTANT |  |  | DATE |
| CONTRACTOR |  |  | DATE |

PRM031/2civ/7

PRM031/2:	ATTENDANCE REGISTER

| PROJECT: |  |
| --- | --- |
| VENUE: |  |
| TIME: |  |
| DATE: |  |
| PURPOSE: |  |

PRESENT:

| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | TELEPHONE NUMBER | FAX NUMBER | CELL PHONE NUMBER | EMAIL ADDRESS | SIGNATURE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  | PRM031/2civ/8 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| APOLOGIES: |  |  |  |  |  |  |  |  |
| No. | NAME (BLOCK LETTERS) | FIRM OR DEPARTMENT | DISCIPLINE | TELEPHONE NUMBER | FAX NUMBER | CELL PHONE NUMBER | EMAIL ADDRESS | SIGNATURE |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |

| # PRM034: PROGRESS PAYMENT | PRM034civ/1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOR DEPARTMENTAL USE ONLY |
| KEY INFORMATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advice number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FMS Distribution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WCS number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payee’s code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor’s code |  |  |  |  |  |  |  |  |  |  |  |  | (if 4.4 is applicable) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payment number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regional Office |  |  |  |  |  |  |  |  |  |  |  | HO Ref. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | RM Ref. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VAT No. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SERVICE |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR : PAYEE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Address |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract amount (VAT incl.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | c |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. |  |  |  | ESTIMATED FINAL COST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.1 Contract sum MINUS VAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.2 Estimated variations Excluding VAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.3 Estimated contract price adjustment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.4 Estimated VAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.5 Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. |  |  |  | DATE OF VALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. |  |  |  | PAYMENT DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Payment no. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Certificate no. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3.1 Value of work done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
|  |  |  |  | 3.2 Material on site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
|  |  |  |  | 3.3 Material off site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
|  |  |  |  | 3.4 Contract price adjustments Principal contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (+ or/ -) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3.5 Nominated sub-contractors include. CPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SUB-TOTAL A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3.6 MINUS Retention money: Maximum reten. Money |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R……….. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  | 3.7 MINUS Mat. On Site (Civil contr.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ….% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | of |  |  |  |  |  |  |  |  | R……………. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  | 3.8 Miscellaneous (Specify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PLUS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | e.g. VAT on Penalties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MINUS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | e.g. Guarantee amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SUB-TOTAL B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. |  |  |  | DEDUCTIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 4.1 Previous payments no. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ………….. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | to |  |  |  |  |  |  | …………….. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  | 4.2 Penalty for late completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ………… |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  | 4.3 Penalty for non-compliance with APP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
|  |  |  |  | 4.4 Direct payments to Nominated sub-Contractors/Suppliers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  |  |  |  |
| 5 |  |  |  | NET AMOUNT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SUB-TOTAL C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. |  |  |  | PLUS VAT |  |  |  |  |  |  |  |  | (Cumulative R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | This payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | + |  |  |  |  |  |
| 7. |  |  |  | AMOUNT PAYABLE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. |  |  |  | STAGE **Code |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | **1 = Progress payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 = Practical completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 = Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 = Final account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Expected date of Practical completion if |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | STAGE = |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | I hereby certify in terms of this contract the payee is entitled to the payment as calculated above. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | CERTIFIED DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SIGNED AGENT/REPRESENTATIVE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOR DEPARTMENTAL USE ONLY |
|  | ALLOCATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Payment indicator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Warrant voucher |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Objective |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Item |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Allocation amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Payment checked |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Official title |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Payment authorised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Posted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Designation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Verified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM035civ/1

# PRM035:  APPLICATION FOR PAYMENT OF MATERIALS ON SITE

IN TERMS OF CLAUSE 49.2 AND VESTING OF OWNERSHIP IN TERMS OF

CLAUSE 29 OF THE GENERAL CONDITIONS OF CONTRACT 2004.

|  |  |  | WCS No: |  |
| --- | --- | --- | --- | --- |
|  |  |  | REFERENCE No: |  |
| PROJECT: |  |  |  |  |
| PROJECT MANAGER |  |  |  |  |
| NAME OF CONTRACTOR: |  |  |  |  |

I/we hereby apply for ……. % payment in respect of the following materials which have been delivered on site and attach the relevant invoices and receipts:-

| MATERIALS: |  | VALUATION: |
| --- | --- | --- |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
|  | R |  |
| TOTAL VALUE: | R |  |

I/we certify that these materials were my/our bona fide property at the time of delivery on site, ownership of which had passed to me/us according to Law.  The ownership is hereby transferred to the Department of Public Works.

| CONTRACTOR / AUTHORISED REPRESENTATIVE |  |  | DATE |
| --- | --- | --- | --- |
| CONSULTANT CIVIL ENGINEER |  |  | DATE |
| PRINCIPAL AGENT/REPRESENTATIVE |  |  | DATE |

PRM036/1civ/1

# PRM036:  CONTRACT STATUS REPORT

| MONTH: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | WCS No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | REFERENCE No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRINCIPAL AGENT/CONSULTANT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | PROGRESS AND COMPLETION: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A1 | Contract Commencement Date: |  |  |  |  |  |  |  |  |  | (Date of letter of acceptance of tender) |  |  |  |  |  |  |  |  |  |
| A2 | Contractual Completion Date: |  |  |  |  |  |  |  |  |  | (= |  |  |  | month of contract) |  |  |  |  |  |
| A3 | Extended Completion Date: |  |  |  |  |  |  |  |  |  | (as approved by client) |  |  |  |  |  |  |  |  |  |
| A4 | Extended Practical Completion Date: |  |  |  |  |  |  |  |  |  | (as determined by agent) |  |  |  |  |  |  |  |  |  |
|  | REASONS FOR VARIANCE BETWEEN A2, A3 AND A4: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | OTHER COMMENTS REGARDING DELAYS, PROGRESS, ETC.: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  | FINANCIAL DATA: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B1 |  | Tender Amount (including VAT): |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |
| B2 |  | Anticipated Final Cost: |  |  |  |  |  | R |  |  |  |  | (From Financial report) |  |  |  |  |  |  |  |
| B3 |  | Subject to cost norms? |  |  |  |  |  |  |  |  |  |  |  | Yes / No |  |  |  |  |  |  |
| B4 |  | If Yes, will contract be completed within cost norm limits? |  |  |  |  |  |  |  |  |  |  |  | Yes / No |  |  |  |  |  |  |
| B5 |  | If No, furnish reasons for variation from tender norms reconciliation and corrective action to be taken: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B6 |  | Details of monetary and / or time claims received from Contractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  | NOMINATED / SELECTED |  |  |  |  |  |  | DEADLINE FOR NOMINATION |  |  |  |  |  |  |  |  |  | DATE OF TENDER |  |
|  |  | SUB-CONTRACTORS |  |  |  |  |  |  | TO AVOID DELAYS |  |  |  |  |  |  |  |  |  | ACCEPTANCE |  |
|  |  | CERTIFIED CORRECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CONSULTING ENGINEER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |
| NB |  | 1 | Financial report must be attached to this document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2 | Final account must be submitted to the department within 3 months after Practical Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PRINCIPAL AGENT / PROJECT MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |

PRM036civ/2

PRM036:  FINANCIAL REPORT

| PROJECT: |  |  |  |  | MONTH: |  |
| --- | --- | --- | --- | --- | --- | --- |
| PROJECT MANAGER: |  |  |  | WCS NO: |  |  |
| PRINCIPAL AGENT/ CONSULTANT: |  |  |  | REFERENCE NO: |  |  |

| DESCRIPTION |  |  | TENDER ANALYSIS A | PREVIOUS REPORT B | CURRENT REPORT C | CURRENT REPORT (B - C) | ACCUMULATIVE VARIATIONS (C - A) | REFERENCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | PRELIMINARIES |  |  |  |  |  |  |  |
| 2 | BUILDING WORK |  |  |  |  |  |  |  |
| 3 | PROVISIONAL ITEMS AND WORK MEASURED PROVISIONALLY |  |  |  |  |  |  | PRM036/1/3 |
| 4 | PROVISIONAL SUMS (EXCLUDING PROFIT AND ATTENDANCE) |  |  |  |  |  |  | PRM036/1/4 |
| 5 | PROFIT AND ATTENDANCE ON PROVISIONAL SUMS |  |  |  |  |  |  | PRM036/1/5 |
| 6 | VARIATION ORDERS (APPROVED) |  |  |  |  |  |  | PRM036/1/6 |
| 7 | VARIATION ORDERS, SITE INSTRUCTIONS AND OTHER NOT YET APPROVED |  |  |  |  |  |  | PRM036/1/7 |
|  |  | SUB-TOTAL A: |  |  |  |  |  |  |
| 8 | CPA (PROJECTED) |  |  |  |  |  |  |  |
|  |  | SUB-TOTAL B: |  |  |  |  |  |  |
| 9 | VAT |  |  |  |  |  |  |  |
|  |  | SUB-TOTAL C: |  |  |  |  |  |  |
| 10 | LESS CREDITS FOR OLD MATERIALS ETC. |  |  |  |  |  |  |  |
| 11 | ANTICIPATED TOTAL COSTS: |  |  |  |  |  |  |  |

PRM036/1civ/3

|  | WCS No: |  |
| --- | --- | --- |
| PROVISIONAL ITEMS AND WORK MEASURED PROVISIONALLY |  |  |
| DESCRIPTION | OMISSION | ADDITION |
| TOTAL: |  |  |
| NET ADJUSTMENT: |  |  |

PRM036/1civ/4

|  | WCS No: |  |
| --- | --- | --- |
| PROVISIONAL SUMS (EXCLUDING PROFIT AND ATTENDANCE) |  |  |
| DESCRIPTION | OMISSION | ADDITION |
| TOTAL: |  |  |
| NET ADJUSTMENT: |  |  |

PRM036/1civ/5

|  | WCS No: |  |
| --- | --- | --- |
| PROFIT AND ATTENDANCE ON PROVISIONAL SUMS |  |  |
| DESCRIPTION | OMISSION | ADDITION |
| TOTAL: |  |  |
| NET ADJUSTMENT: |  |  |

PRM036/1civ/6

|  | WCS No: |  |
| --- | --- | --- |
| VARIATION ORDERS (APPROVED) |  |  |
| DESCRIPTION | OMISSION | ADDITION |
| VARIATION ORDERS (SCHEDULED RATES) (not exceeding 50% of contract value excluding VAT) |  |  |
| VARIATION ORDERS (NON-SCHEDULED RATES) (not exceeding 5% of contract value excluding VAT) |  |  |
| TOTAL: |  |  |
| NET ADJUSTMENT: |  |  |

PRM036/1civ/7

|  | WCS No: |  |
| --- | --- | --- |
| VARIATION ORDERS, SITE INSTRUCTIONS AND OTHER INSTRUCTIONS NOT YET APPROVED |  |  |
| DESCRIPTION | OMISSION | ADDITION |
| TOTAL: |  |  |
| NET ADJUSTMENT: |  |  |

PRM036/1civ/8

|  | WCS No: |  |  |  |
| --- | --- | --- | --- | --- |
| PROFESSIONAL FEES (FEES ON CPA EXCLUDED) |  |  |  |  |
| DESCRIPTION |  |  | AMOUNT |  |
| CIVIL ENGINEER |  |  |  |  |
| OTHER(SPECIFY) |  |  |  |  |
| TOTAL: |  |  |  |  |

PRM036/1civ/9

PRM036:  COST NORM REPORT

|  |  | MONTH: |  |  |
| --- | --- | --- | --- | --- |
|  |  | WCS No: |  |  |
|  |  | REFERENCE No: |  |  |
| PROJECT: |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |
| PRINCIPAL AGENT/CONSULTANT: |  |  |  |  |

| DESCRIPTION | NORMS RECONCILIATION A | PREVIOUS REPORT B | CURRENT REPORT C | REFERENCE |
| --- | --- | --- | --- | --- |
| ANTICIPATED FINAL COST |  |  |  |  |
| ADD PROFESSIONAL FEES (EXCLUDING FEES ON CPA) |  |  |  | PRM036/8 |
| SUB-TOTAL A: |  |  |  |  |
| OMIT CPA (PROJECTED) |  |  |  |  |
| SUB-TOTAL B: |  |  |  |  |
| ADD RESERVE FUND 1 |  |  |  |  |
| ADD RESERVE FUND 2 |  |  |  |  |
| ADD RESERVE FUND 3 |  |  |  |  |
| TOTAL: |  |  |  |  |

RESERVE FUND ANALYSIS (TENDER PROVISION)

| RESERVE FUND 1 |  |
| --- | --- |
| RESERVE FUND 2 |  |
| RESERVE FUND 3 |  |
| TOTAL: |  |
| ACCUMULATIVE VARIATIONS (+ OR -) (CPA EXCLUDED) |  |
| SUB-TOTAL: |  |
| *ADJUSTMENT FOR OTHER SAVINGS OR LOSSES |  |
| BALANCE OF RESERVE FUND: |  |

| * DESCRIPTION: |  |  |
| --- | --- | --- |

| PRM036: ANNUAL CASH FLOW FOR BUDGETING PURPOSES |  |  |  |  |  |  |  | PRM036/1civ/10 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | DATE OF REPORT: |  |  |  |  |
|  |  |  |  | WCS NO: |  |  |  |  |
|  |  |  |  | REFERENCE NO: |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  | PRINCIPAL AGENT/ CONSULTANT: |  |  |  |

| DISCIPLINE | YEAR |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | YEAR 0 |  |  | YEAR 0+1 | YEAR 0+2 | YEAR 0+3 | YEAR 0+4 | YEAR 0+5 | YEAR 0+6 | YEAR 0+7 | YEAR 0+8 | YEAR 0+9 |  |
|  | AMOUNTS ALREADY PAID IN PREVIOUS FINANCIAL YEARS R X 1000 | AMOUNTS ALREADY PAID IN PRESENT FINANCIAL YEAR R X 1000 | ESTIMATED AMOUNT PAYABLE FOR REMAIN OF FINANCIAL YEAR R X 1000 |  | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 | R X 1000 |
| A CONTRACTORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 MAIN CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 SUB CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 SUB CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-TOTAL A: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B CONSULTANTS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 CIVIL ENGINEER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OTHER (SPECIFY) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-TOTAL B: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL (A + B): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| NOTE: | 1 | THE FINANCIAL YEAR OF THE PUBLIC SECTOR RUNS FROM 01 APRIL TO 31 MARCH |
| --- | --- | --- |
|  | 2 | (YEAR O) REPRESENT THE PRESENT FINANCIAL YEAR, YEAR (0 +1) REPRESENT THE FOLLOWING FINANCIAL YEAR, ETC. |
|  | (PLEASE INSERT THE APPROPRIATE YEARS AT TOP OF EACH COLUMN - E.G. IF THE PRESENT YEAR IS 93/94, (YEAR 0 + 1) IS 94/95, ETC.) |  |

PRM037civ/1

# PRM037:  VARIATION ORDER (Clause 36 & 37 of GCC 2004):
STEP BY STEP

1.0	STEP 1:  INCEPTION

The initiation is when the Consultant becomes aware of a potential variation order as a result of:

- Incomplete design

- Chance in scope

- Additional need

- Unforeseen work.

ACTION:	The Departmental Project Manager must be informed of the potential variation 	order.

2.0	STEP 2:  PRELIMINARY DESIGN AND DESIGN:  CONCEPT AND VIABILITY

The Consultant must prepare a design and bill of quantity for the Contractor to price similar to the tender document.

3.0	STEP 3:  DOCUMENTATION AND PROCUREMENT

3.1 	ISSUE SITE INSTRUCTION

A site instruction requests the Contractor to price the variation order.  The Contractor must provide sufficient information to enable the valuation of the rates.  The base date of the rates must be established.

3.2	SUBMIT VARIATION ORDER TO THE DEPARTMENTAL PROJECT MANAGER

The Variation Order must be submitted with:

- Covering letter from Consultant with analysis of rates and funding particulars

- Variation Order:  Motivation form

- Variation Order:  Form

- Bill of Quantity with rates

- Application for additional funds:  PRM 039 (even if additional funds are not required)

- Site Instruction with specification and Bill of Quantities

- Contractor’s rates for Bill of Quantities items and clarification of rates.  Clearly stating base month.

3.3	APPROVAL OF VARIATION ORDER

- Departmental Project Manager approve Variation Order

- Consultant issue instruction with approved Variation Order to Contractor.

3.4	REJECTION OF VARIATION ORDER

Consultant to inform Contractor.

PRM037civ/2

# PRM037:  VARIATION ORDER: MOTIVATION

| PROJECT MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONTRACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WCS No. |  |  |  |  |  |  |  |  | REFERENCE No. |  |  |  |  |  |  |  |  |  |  |  |  | TENDER No. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | VARIATION ORDER No. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.0 | REASON FOR VARIATION (Mark applicable block with ‘X”) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.1 | ADDITIONAL WORK |  |  |  |  |  |  |  |  | 1.2 | SPECIFICATION CHANGE |  |  |  |  |  |  |  |  | 1.3 |  |  | DESIGN CHANGE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.4 | OMITTED WORK |  |  |  |  |  |  |  |  | 1.5 | OTHER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 | MOTIVATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 | RATES FAIR AND REASONABLE |  |  |  |  |  |  |  |  |  | 3.1 | SCHEDULED RATES |  |  |  |  |  |  |  |  | 3.2 |  |  | NON-SCHEDULED RATES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.0 | FUNDS ARE AVAILABLE |  |  |  |  |  |  |  |  |  | 5.0 | ADDITIONAL FUNDS ARE AVAILABLE |  |  |  |  |  |  |  |  | 6.0 |  |  | NO FRUITLESS EXPENDITURE IS INVOLVED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 7.0 | FRUITLESS EXPENDITURE IS INVOLVED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FIRM |  |  |  |  |  |  |  |  |  |  |  | CONSULTANT |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACCEPTED FOR ISSUE TO CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FIRM |  |  |  |  |  |  |  |  |  |  |  | PRINCIPAL AGENT/CONSULTANT |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| APPROVED WITH RESPECT TO FINANCIAL POSITION RESULTING FROM VARIATION ORDER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DEPARTMENTAL DELEGATED OFFICER |  |  |  |  |  |  |  |  |  |  |  | OFFICIAL TITLE |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PW 778(1)E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PRM038 Motivation |  |  |  |  |  |  |  |  |  |  |  |  |

PRM037civ/3

# PRM037:  VARIATION ORDER

| CONTRACT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONTRACTOR: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WCS No. |  |  |  |  |  |  | REFERENCE No. |  |  |  |  |  |  |  |  |  |  |  |  |  | TENDER No. |  |  |  |  |  |  |  |  |
| VARIATION ORDER No |  | DESCRIPTION (with number of Site Instruction and date issued) |  |  |  |  |  |  |  |  | NON-SCHEDULED ITEM Mark ‘X” |  |  | ESTIMATE OF COST INVOLVED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIT |  | QUANTITY |  |  | RATE |  |  |  |  |  | ADD |  | OMIT |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R.c |  | R.c |  |  |
| NON-SCHEDULED ITEMS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SCHEDULED ITEMS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PLUS VAT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TOTAL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| THE ABOVE RATES ARE VALID AT …………/…………../………………… BASE MONTH (Delete if not applicable) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FIRM |  |  |  |  |  |  |  |  |  | CONSULTANT |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |
| ACCEPTED FOR ISSUE TO CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FIRM |  |  |  |  |  |  |  |  |  | PRINCIPAL AGENT |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |
| APPROVED WITH RESPECT TO FINANCIAL POSITION RESULTING FROM VARIATION ORDER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DEPARTMENTAL DELEGATED OFFICER |  |  |  |  |  |  |  |  |  | OFFICIAL TITLE |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |
| * VARIATION ORDER can only be issued after being signed by the DELEGATED OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PW 778(2)E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PRM037 Variation Order |  |  |  |  |  |

PRM039civ/1

| # PRM039: APPLICATION FOR ADDITIONAL FUNDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WCS: |  |  |  |  |  |  |  |  |  |  |  | Extension to contract time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| REFERENCE: |  |  |  |  |  |  |  |  |  |  |  | Approved |  |  |  |  |  |  |  |  |  | calendar days |  |  |  |  |  |  |  |
| ENQUIRIES: |  |  |  |  |  |  |  |  |  |  |  | Expected |  |  |  |  |  |  |  |  |  | calendar days |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |  |  | calendar days |  |  |  |  |  |  |  |
| project: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | Contract amount: |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.1 |  | Site Instructions, VO’s pending/approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Funds previously requested |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional funds required now |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.2 |  | Adjustment to Provisional Items and work measured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | provisionally: Funds previously requested |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional funds required now |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.3 |  | Adjustment to Provisional Sums (excluding profit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | and attendance): Funds previously requested |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional funds required now |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.4 |  | Adjustment to Profit and Attendance on Provisional |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | sums: Funds previously requested |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional funds required now |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.5 |  | Additional preliminaries – value +/or time related if applicable: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Funds previously requested |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional funds required now |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Total funds requested (excluding CPA) A |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.6 |  | CPA originally requested (if applicable) |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Additional CPA |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
|  |  | Total CPA B |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (Excluding VAT) |  |  |  |  |  |  |  |
| 1.7 |  | Total funds required: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Total (A + B) |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Plus 14% VAT |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | TOTAL FUNDS REQUIRED |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. |  | Additional funds (Total of previous and current requests excluding CPA and VAT): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Non-scheduled tariffs (1.1) |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (___% of contract amount) |  |  |  |  |  |  |  |
|  |  | Scheduled tariffs |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (___% of contract amount) |  |  |  |  |  |  |  |
|  |  | Adjustment (1.2, 1.3, 1.4 and 1.5) |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (___% of contract amount) |  |  |  |  |  |  |  |
|  |  | Total additional funds requested (excluding CPA & VAT) |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | (___% of contract amount) |  |  |  |  |  |  |  |
| 3. |  | Project is still within set cost norms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes / No |  |  |  | Approved cost norm, if |  |  |  |  |  |  |  |
| 4. |  | Please find summary of Variation Orders attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes / No |  |  |  | applicable |  |  |  |  |  |  |  |
| 5. |  | Practical Completion Certificate has been issued |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes / No |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| Signed: |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | PRINCIPAL AGENT / CONSULTING ENGINEER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Signed: |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PROJECT MANAGER /OPERATIONAL MANAGER 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Additional Funds: Approved / Not Approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Additional funds: Recommended / Not Recommended |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Client Budget Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Director: Major Projects |  |  |  |  |  |  |  |  |  | Date |  |  |
| * This form has to be signed by the Operational Manager for projects executed by a region |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM039civ/2

PRM039:  APPLICATION FOR APPROVAL TO EXCEED THE CONTRACT AMOUNT BY MORE THAN 5% FOR NON-SCHEDULED TARIFFS/50% FOR SCHEDULED TARIFFS *2 IN ORDER TO EXECUTE ADDITIONAL WORK BY MEANS OF VARIATION ORDER

PROCEDURE TO BE FOLLOWED

1.	Rule number one: Avoid the situation by appropriate, complete, correct and up to date tender documentation.

2.	Monitor and control the financial situation on the project continuously. The minimum form of control is the monthly contract status report prepared by the consultant with the Principal Agent. Approved and Proposed Variation Orders must be valued and reflected in these reports monthly. The percentage increase/decrease on the Contract Amount must be calculated and shown on each report.

3.	The restriction not to exceed 5% based on non-scheduled and 50% based on scheduled tariffs of the original contract amount in real terms is a State Tender Board regulation and is enforced by them as such. This regulation is to enforce proper planning and control, financially and otherwise, and to prevent contracts, particularly “alterations and additions” contracts, from running on unabated and unrestricted forever.

There is also a 15% limit which is a contractual condition to bind the Contractor to his rates for variations within the limit of 15% above or below the Contract Amount as set out in clause 50 of the General Conditions of Contract 2004 and which has nothing to do with the above issue.

4.	If it appears likely that proposed variation orders will exceed the 5% and/or the 50% limit then application must be made well in advance using the Standardised format attached. Approval must be obtained before instructions are given to the Contractor. Applications must be submitted to the Tender Committee via the Chief Director or Regional Manager.

5.	GUIDELINES FOR APPLICATION

ITEM 1 AND 2

The front page must contain all the basic information and calculation of percentages for every application. (Note: The extended completion date must only be shown if the extension has already been officially approved).

ITEM 3  BACKGROUND

Provide accurate and condensed background information. Refer to and attach supporting documentation if applicable and relevant (e.g. letter from Client Department).

If the application is as result of a request for additional accommodation, services or changes please confirm that approval has been obtained from Client Services/Port Folio Management and that norms have been adjusted.

Attach a copy of the latest contract status report (Summary page only).

Item 4  motivation

Give brief but convincing motivation. The motivation has to be very specific and should, inter alia, at least cover the following points:

- Why this requirement could not have been foreseen at the time when the work had been planned and documented originally.

- Why this intended work has to be done in this present contract and why it can not be done in a subsequent contract.

*2	The original contract amount may under no circumstance be exceeded by more than 5% where non-scheduled tariffs and 50% where scheduled tariffs are applicable and funds having been authorised.

PRM039civ/3

- It will have to be shown and proven beyond any reasonable doubt that the work will be done at the same rates as the original work tendered for. It is impossible to prove this on “lump sum” or “specification” contracts and therefore any additional costs will have to be dealt with as “non-scheduled tariffs”. The reasonability of such non-scheduled tariffs will have to be proven by some other means such as quotes from a sufficient number of other contractors.

- It has to be borne in mind that a large number of variation orders on a contract is normally perceived as indicative of poor planning and poor management. In point of fact, on “lump sum” or “specification” contracts there are supposed to be no variation orders at all due to the difficulty in establishing a fair price for the variation. In the private sector this is normally done by negotiation, but a civil servant will have to prove that he negotiated the best deal for the state and this is normally easier said than done. Hence the necessity for bill rates, quotations from different contractors, etc.

ITEM 5  ESTIMATED COST OF PROPOSED VARIATIONS

Give a breakdown of the elements involved with estimates for each element and the total estimated cost.

Confirm that the additional work will be done at existing rates in the Bills of Quantities if this is the case.

If not, explain how the estimate has been established e.g. rates to be negotiated but based on existing rates, calling for quotations via the Contractor).

If the estimate is based on quotation submitted by the Contractor confirmation is required by the quantity surveyor that the price is considered to be fair and reasonable for the work involved.

ITEM 6  RECOMMENDATION

See Standardised format.

Note 1:	Work carried out in excess of 5% based on non-scheduled and 50% based on scheduled tariffs without prior approval will be treated as unauthorised expenditure and will not be approved by the State Tender Board although such cases must be submitted to the Board.

Such cases will be reported to the Auditor-General by the Board with serious consequences for the Director-General and the Department.

An example of the application for approval to exceed the contract amount by more than 5% for non-scheduled tariffs/50% for scheduled tariffs in order to execute additional work by means of variation order is part of the PRM039 document on the DPW-website but is for Departmental use only.

Note 2:	The Departmental Tender Committee meets every Tuesday at 08:00.

Applications must reach the Tender Section not later than Thursday preceding.

PRM040civ/1

# PRM040:  APPLICATION FOR EXTENSION OF CONTRACT PERIOD

| CLAIM No. |  |  |  |  |  |  |  |  | WCS No: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | REFERENCE No: |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PRINCIPAL AGENT/CONSULTANT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Contract amount: |  |  |  |  |  |  |  |  |  |  |  | R |  |
| 2. | Contract commencement date: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. | Contract period: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. | Submission date of acceptable guarantee: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. | Date of site handover: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. | Original contractual completion date: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. | Extensions awarded prior to this application: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. | Adjusted contractual completion date as result of 7.: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. | Date on which cause of delay arose: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. | Date of contractor’s letter in which extension is applied for: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION: (See attached report for complete motivation including PRM040/2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submitted by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | PRINCIPAL AGENT/CONSULTANT/PROJECT MANAGER |  |  |  |  |  |  |  |  |  | DATE |
| Supported/Not |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Supported by |  |  |  | PROJECT MANAGER |  |  |  |  |  |  |  |  |  | DATE |
| EXTENSION AUTHORISED/NOT AUTHORISED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COMMENTS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D/MAJOR PROJECTS / D/E & D (……..) |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |

PRM040civ/2

PRM040:  EXTENSION OF TIME CLAIM

| PROJECT: |  |  |  |  |
| --- | --- | --- | --- | --- |
| CONTRACTOR: |  |  | REFERENCE No.: |  |
|  |  |  | WCS No.: |  |
| PROJECT MANAGER: |  |  | FILE No.: |  |
|  |  |  | TENDER No.: |  |

NOTE:	ALL CLAIMS HAVE BEEN MADE IN TERMS OF CLAUSE 47 AND/OR 48 OF GCC 2004 AND/OR CLAUSE 47.5 OF CONTRACT DATA (“Abnormal Rainfall”)

| Claim No. | Date of Event | Date of Application in Writing | Within 28 Days | Working Days claimed by Contractor | Working Days Recommended by Civil Engineer | Reason for Claim | Work Activity | Critical Path | Working Days Recommended by Project Manager | Reasons for Project Managers Decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

PRM040civ/3

| PRM040: SUBMISSION OF APPLICATION FOR EXTENSION OF TIME BY PRINCIPAL AGENT/CONSULTANT: CLAIMS _____ TO _____ (THIS FORM PROPERLY COMPLETED MUST BE ATTACHED TO EACH CLAIM SUBMITTED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT: |  |  |  |  |  |  |  |  |  |  | FILE No. |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | WCS No. |  |  |  |  |
| Claims for the extension of contract time must comply with the following requirements, information needed with regard to each case is marked with a X. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The required proof shall be submitted on or before |  |  |  |  |  |  |  | , failing which claims for extension |  |  |  |  |  |  | cannot be granted. |
| A new application, completed in the correct format with all necessary proof can be resubmitted for the same claim. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X | CLAIM No. |  | INFORMATION NEEDED |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Please note that applications for extension of the contract period must be processed in numerical sequence. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Contractor must, according to clauses 47 and/or 48 of the General Conditions of Contract 2004, formally apply in writing for extension. Contractor’s application must be appended. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Contractor must clearly indicate, in the claim, under which clause of the conditions of contract this application for the extension of time is made. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Each submission, regardless of the number of events, must have a cover page (PRM040/1). The Principal Agent must make a recommendation with regard to each event separately on the standard departmental form and sign it. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Different types of events must be handled as separate claims and must not be combined. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Specific dates for each claim must be provided. (From ______ to ____) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Each event (regardless of the period) must be submitted as a separate claim, not more than one event per form and all submissions must be summarized (PRM040/2). |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Letter of appointment of contractor must accompany the first application for extension of time. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Completed contract completion report must only accompany application for extension after first delivery. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Reasons motivating a claim must be attested where proof cannot be provided. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | CLAIMS AS RESULT OF VARIATION ORDER/SITE INSTRUCTION: Approved variation order/site instruction, with proof when contractor received the variation order/site instruction, is required. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | UNREST OR UNREST RELATED INCIDENTS: An original affidavit or attestation of the events by the SA Police must accompany the claim. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | INCLEMENT WEATHER: During which no work is possible (any rain). Weather Bureau statistics containing average rainfall figures per month for at least the previous 5 years as well as the average rainy days per month plus on site recorded rainfall figures must accompany each claim. Similar statistics to be presented for abnormal cold (climos) and wind (dust / wind-chill). Claims for consequential delays must, in addition, be fully motivated. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | LATE DELIVERY OF MATERIAL: Written declaration from the supplier, stating dates of order, original delivery and actual dates and reasons for late delivery. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | With each claim an updated construction program, indicating the effect of the delay on the project with the accordingly adjusted completion date, must be submitted also indicating if the event of the claim is on the critical path or not. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Should the delay be caused by an outside party e.g. the client, a letter from the party must accompany that claim. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PRM040/1: Application for extension of contract period |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PRM040/2: Summary form for claims |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PRM040/3: Information needed |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PRM043/1 TO -/3: Contract Completion Report at finalization of project |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Tel |  |  |  |  |  | Fax |  |  |  |  |
| Signed by (Principal) Agent/Consultant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |

NOTE:	Form to be utilised by:

- Principal Agent/Consultant to confirm that all necessary information has been submitted.

- Project Manager as a guideline to Principal Agent/Consultants and Contractors on correct procedures or requesting outstanding information.

PRM041/civ/1

| Department of public works |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # PRM041: CERTIFICATE OF PRACTICAL COMPLETION (Clauses 51.1 to 51.3 of the General Conditions of Contract) |  |  |  |  |  |  |
| REGION: |  |  |  |  |  | WCS No: |
| PROJECT: |  |  |  |  |  | Reference No: |
|  |  |  |  |  |  | Tender No: |
| CLIENT/USER DEPARTMENT: |  |  |  |  |  |  |
| dEPARTMENTAL PROJECT MANAGER: |  |  |  |  |  |  |
| CONSULTANT: |  |  |  |  |  |  |
| CONTRACTOR: |  |  |  |  |  |  |
| DATE OF PRACTICAL COMPLETION: |  |  |  |  |  |  |
| The Works have reached a stage (practical completion) that allows their use for their intended purpose without danger or undue inconvenience |  |  |  |  |  |  |
| DESCRIPTION OF WORKS: |  |  |  |  |  |  |
| OUTSTANDING WORK: - For outstanding work to be completed see Addendum A attached |  |  |  |  |  |  |
| CONSULTANT |  | CLIENT/USER DEPARTMENT |  | CONTRACTOR | dEPARTMENT OF PUBLIC WORKS |  |
| Representative |  | Representative |  | Representative | Representative |  |
| Signature |  | Signature |  | Signature | Signature |  |
| Date |  | Date |  | Date | Date |  |
| Note: In terms of the Conditions of Contract, only the Engineer certifies due completion of the Works. The other signatures indicate attendance at the inspection of the Works and witnessing of the Engineer’s signature |  |  |  |  |  |  |
| For: Director Special and Major Projects: __________________________ Date: _______________ |  |  |  |  |  |  |

PRM041civ/2

| Department of public works |  |  |  |  |
| --- | --- | --- | --- | --- |
| PRM041: ADDENDUM A: TO CERTIFICATE OF PRACTICAL COMPLETION OUTSTANDING Work TO BE completed |  |  |  |  |
| Item No. | Item Description | Action By | Proposed Completion Date | Actual Completion Date |
| Note: Failure to complete the above item(s) by the proposed date(s) specified above shall in terms of Clause 54(4) of the Conditions of Contract (GCC 2004), result in the Defects Liability Period being extended by the additional time required to complete work |  |  |  |  |

PRM041civ/3

| Department of public works |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # PRM041: CERTIFICATE OF COMPLETION (Clauses 51.4 to 51.6 of the General Conditions of Contract 2004) |  |  |  |  |  |  |  |  |
| REGION: |  |  |  |  |  |  |  | WCS No: |
| PROJECT: |  |  |  |  |  |  |  | Reference No: |
|  |  |  |  |  |  |  |  | Tender No: |
| CLIENT/USER DEPARTMENT: |  |  |  |  |  |  |  |  |
| dEPARTMENTAL PROJECT MANAGER: |  |  |  |  |  |  |  |  |
| CONSULTANT: |  |  |  |  |  |  |  |  |
| CONTRACTOR: |  |  |  |  |  |  |  |  |
| DATE OF COMPLETION: |  |  |  |  |  |  |  |  |
| The defects liability period of |  |  |  | months in accordance with the conditions of contract, |  |  |  |  |
| commences on the date of issue of Certificate of Completion |  |  |  |  |  |  |  |  |
| All other work specified, as well as all work issued per variation order, have been completed satisfactorily |  |  |  |  |  |  |  |  |
| CONSULTANT |  | CLIENT/USER DEPARTMENT |  |  |  | CONTRACTOR | dEPARTMENT OF PUBLIC WORKS |  |
| Representative |  | Representative |  |  |  | Representative | Representative |  |
| Signature |  | Signature |  |  |  | Signature | Signature |  |
| Date |  | Date |  |  |  | Date | Date |  |
| Note: In terms of the Conditions of Contract, only the Engineer certifies due completion of the Works. The other signatures indicate attendance at the inspection of the Works and witnessing of the Engineer’s signature |  |  |  |  |  |  |  |  |
| For: DIRECTOR SPECIAL AND MAJOR PROJECTS: __________________________ DATE: _______________ |  |  |  |  |  |  |  |  |

PRM042civ/1

# PRM042:  TERMINATION OF GUARANTEE

|  |  |  |  |  |  | WCS No: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | REFERENCE No: |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |
| CONTRACT No: |  |  |  |  |  |  |  |  |
| CONTRACTOR: |  |  |  |  |  |  |  |  |
| GUARANTOR: |  |  |  |  |  |  |  |  |
| AMOUNT OF GUARANTEE: |  |  |  | R |  |  |  | Amount in words: |
|  |  |  |  |  | ( |  |  |  |
|  |  |  |  |  | ) |  |  |  |

I hereby certify that:

a)	this project has been completed satisfactory and,

b)	there are no outstanding items.

c)	Date of first delivery is  ............................................................

CONTRACTS SECTION:

Kindly arrange for the release of the guarantee/surety.

| PRINCIPAL AGENT/CONSULTANT |  | PROJECT MANAGER |
| --- | --- | --- |
| DATE |  | DATE |

PRM042/2

PRM042:  CALLING UP GUARANTEE

(Contract Cancellation)

|  |  |  |  |  | WCS No: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | REFERENCE No: |  |  |  |
| TO: TENDER AND CONTRACTS ADMINISTRATION: |  |  |  |  |  |  |  |  |
| PROJECT: |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |
| CONTRACT No: |  |  |  |  |  |  |  |  |
| CONTRACTOR: GUARANTEE NUMBER: |  |  |  |  |  |  |  |  |
| GUARANTOR: |  |  |  |  |  |  |  |  |
| AMOUNT OF GUARANTEE |  |  | R |  |  |  | Amount in words: |  |
|  |  |  |  | ( |  |  |  |  |
|  |  |  |  | ) |  |  |  |  |

- Appended is a copy of the submission through which the cancellation of the contract was authorised.

- Appended is a copy of the signed letter of cancellation directed to the contractor.

- The guarantee must be immediately called up from the said guarantor.

| PRINCIPAL AGENT/CONSULTANT |  | PROJECT MANAGER |
| --- | --- | --- |
| DATE |  | DATE |

| RECEIVED |  |
| --- | --- |
| (Tender and Contracts Administration) |  |
| DATE |  |

Note: pro-forma also to be utilized by all regions directed to their Tender and Contracts Administration Section

PRM043civ/1

# PRM043:  CONTRACT COMPLETION REPORT

| A |  | CONTRACT PARTICULARS: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. |  | File No. HO / RO |  |  |  |  |  |  |  | 2. |  |  |  | WCS No. |  |  |  |  |  |  |  |  |  | 3. | Bid/Tender No. |  |  |  |  |  |
| 4. |  | Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. |  | Contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. |  | Contract sum |  |  | R |  |  |  |  |  |  |  |  |  |  | 11. |  | Extended practical completion date |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. |  | Tender acceptance date |  |  |  |  |  |  |  |  |  |  |  |  |  | 12. |  | Date of completion |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. |  | Contract period |  |  |  |  |  |  |  |  |  |  |  |  |  | 13. |  | Days completed late |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. |  | Original practical completion date |  |  |  |  |  |  |  |  |  |  |  |  |  | 14. |  | Penalty per day |  |  |  |  |  |  |  |  | R |  |  |
| 10. |  | Extensions approved (calendar days) |  |  |  |  |  |  |  |  |  |  |  |  |  | 15. |  | Penalty imposed |  |  |  |  |  |  |  |  | R |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Compulsary Attachments to this Report: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * |  | Certificate of Practical Completion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Copy of Acceptance of Bid/Tender |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) |  | JBCC / GCC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Copy of Minutes of Site Handover Meeting |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Copy of Certificate of Practical Completion |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Copy of WG04PE |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  | EXTENSIONS GRANTED PRIOR TO COMPLETION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tabulate incidents (attach supporting documents for extensions granted) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Days (calendar) |  |  |
| C |  | CONDONATIONS FOR CONSIDERATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tabulate incidents which can be taken into account when applying penalties (attach additional supporting documents, eg. Contractor's application, PM's recommendation, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Days (working/calendar) |  |  |  |  |
| ABBREVIATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HO | Head Office |  |  |  |  | DPM |  | Departmental Project Manager |  |  |  |  |  |  |  |  |  |  |  | D/MP |  |  | Director: Major Projects |  |  |  |  |  |  |  |
| RO | Regional Office |  |  |  |  | CD/DO |  | Chief Director: Development Operations |  |  |  |  |  |  |  |  |  |  |  | D/Maint |  |  | Director: Maintenance |  |  |  |  |  |  |  |
| RM | Regional Manager |  |  |  |  | CD/P+FM |  | Chief Director: Property and Facilities Management |  |  |  |  |  |  |  |  |  |  |  | C/RPM |  |  | Chief: Regional Project Manager |  |  |  |  |  |  |  |
| PS | Procurement Section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM043civ/2

| D |  | WORK PERFORMANCE OF CONTRACTOR (NOTE: Mark any negative aspect that has been or should be captured on the WCS with “X”. Attach or refer to correspondence.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. |  | Problems encountered: |  |  | (a) |  | Guarantee/Security |  |  |  |  | (b) | Priced BoQ |  |  |  |  |  |  | Site handover |  |  |  |  |  |  |  |
| 2. |  | Programming of work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. |  | Quality of work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. |  | Recommendation |  |  | (a) |  | Cannot be recommended for future (Motivate on seperate page) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | regrading: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (b) |  | Limited capabilities |  |  |  |  | Can manage contracts to the value of |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| E |  | SECTION A TO D COMPLETED BY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PRINCIPAL AGENT / PROJECT MANAGER (EXTERNAL IF ANY) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |
|  |  | SUPPORTED/COMMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | BY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | DEPARTMENTAL PROJECT MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |
| F |  | COMMENTS BY D/MP, D/Maint, C/RPM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | No delay, no penalty |  |  |  |  |  |  |  |  |  |  | Full penalty to be applied in terms of the Contract |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Penalty to be waived / reduced according to section C of this report |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | D/MP, D/Maint, C/RPM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |
| ABBREVIATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HO | Head Office |  |  | DPM |  | Departmental Project Manager |  |  |  |  |  |  |  |  | D/MP |  | Director: Major Projects |  |  |  |  |  |  |  |  |  |  |
| RO | Regional Office |  |  | CD/DO |  | Chief Director: Development Operations |  |  |  |  |  |  |  |  | D/Maint |  | Director: Maintenance |  |  |  |  |  |  |  |  |  |  |
| RM | Regional Manager |  |  | CD/P+FM |  | Chief Director: Property and Facilities Management |  |  |  |  |  |  |  |  | C/RPM |  | Chief: Regional Project Manager |  |  |  |  |  |  |  |  |  |  |
| PS | Procurement Section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM043civ/3

| G | DIRECTOR PROJECT MANAGEMENT SUPPORT, CD/PROF SERVICES & COO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Note: Only to be completed if there is a condoning of penalty |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (In the event of full penalty or no penalty (no delay) the DIRECTOR PROJECTS/DIRECTOR SPECIAL AND MAJOR PROJECTS/DIRECTOR PROFESSIONAL SERVICES/DIRECTOR PROJECT MANAGEMENT SUPPORT may act on behalf of the DDG Operations in signing off section G3 below without any reference to DIRECTOR PROJECT MANAGEMENT SUPPORT and CHIEF DIRECTOR PROFESSIONAL SERVICES.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Recommendation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CD/DO or CD/P+FM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |
| 2. | Decision: A penalty of |  |  | R |  |  |  |  |  | must be imposed for |  |  |  |  |  |  |  |  |  |  |  |  | days. |  |
|  | CD/P+FM or CD/DO or RM or D/MP or D/Maint |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |
| H | PROCUREMENT SECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | WCS updated re contractor’s performance (#WG07PU) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |
| 2. | WCS updated re penalty decision (#WG07PU) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |
| 3. | Contract completion report to DPM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |
| ABBREVIATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HO |  | Head Office | DPM |  | Departmental Project Manager |  |  |  |  |  |  |  |  | D/MP |  |  |  | Director: Major Projects |  |  |  |  |  |  |
| RO |  | Regional Office | CD/DO |  | Chief Director: Development Operations |  |  |  |  |  |  |  |  | D/Maint |  |  |  | Director: Maintenance |  |  |  |  |  |  |
| RM |  | Regional Manager | CD/P+FM |  | Chief Director: Property and Facilities Management |  |  |  |  |  |  |  |  | C/RPM |  |  |  | Chief: Regional Project Manager |  |  |  |  |  |  |
| PS |  | Procurement Section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM043civ/4

PRM043:  HANDLING OF CONTRACT COMPLETION REPORT

PRM043civ/5

PRM043:  DIRECTIVE PERTAINING TO THE HANDLING OF THE 
CONTRACT COMPLETION REPORT

- This report must be handled immediately after Practical completion Certificate (PW677 if applicable), Certificate of Practical Completion (JBCC) or Certificate of Practical Completion (GCC 2004) of the Works.

- The Principal Agent/Consultant (or Private Project Manager, if one was appointed) or Transaction Manager must complete sections A to D of the report which must be supported by the DPM.

- Thereafter the CD/APOPS, D/Projects & M, D/Spec Projects or D/Prof Services, depending on where the project was executed, comments on and signs the report.

- Should one of the following apply, the report does not necessarily need to be submitted to the DDG/Operations, but may be signed off in Section G by the D/Projects & M, D/Prof Services, D/PM Support, D/Spec Projects or TM without reference to the D/PM Support & CD/Prof Services:

  - When the contract was completed in time (no penalties).

  - When extension was granted for all delays (no penalties).

  - When extension was granted for part of the delays and no application was received for the waiver, reduction or condonation of the balance of the delays (penalties apply for the balance of the delays).

  - When delays occurred and no application was received for the waiver, reduction or condonation of these delays (penalties apply for the full delay).

- Should the contractor however apply for the waiver or reduction of all or any part of the penalties, the report must be referred to the DDG/Operations via D/PM Support & CD/Prof Services at HO for a decision.

- Applications for decisions by the DDG/Operations must be sent to the D/PM Support, who will forward same to CD/Prof Services and DDG/Operations.

- After the DDG/Operations’ decision, a copy must be filed on 4/2/30 at CR by the PA: DDG/Operations and a copy must be sent to CD/Fin for write off purposes. Thereafter the original report must be returned by the said PA to the Procurement Section at HO/RO who must update the WCS (#WG07PU) regarding the contractor’s performance and the decision on penalties.  A copy of the report is then submitted to the Dept PM by Procurement Section.  The original Contract Completion Report must be placed on the central file (HO or RO, which ever the case may be) of the project.

- After steps 4 and 7 (depending on the case) and on receipt of the copy of the Report, the Dept PM informs the Principal Agent/Consultant/Project Manager (Private), as well as the Quantity Surveyor, if any, of the decisions in the report to be implemented for inclusion in Final Account.

- The Dept PM informs the CIDB of the completion of the project.

Within 21 days after practical completion of project, the Contract Completion report of CIDB must be completed and submitted to CIDB.

| ABBREVIATIONS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| HO | Head Office | DPM | Departmental Project Manager | D/MP | Director: Major Projects |
| RO | Regional Office | CD/DO | Chief Director: Development Operations | D/Maint | Director: Maintenance |
| RM | Regional Manager | CD/P+FM | Chief Director: Property and Facilities Management | C/RPM | Chief: Regional Project Manager |
| PS | Procurement Section |  |  |  |  |

PRM044civ/1

# PRM044:  FINALISATION OF FINAL ACCOUNT AND CHECK LIST

1.   Prerequisites for Departmental approval of the final account:

| ACTION | YES/NO |
| --- | --- |
| - “Certificate of Completion” (PRM041/3civ) issued. |  |
| - “Certificate of Compliance and Indemnity by Consultants” (part 1 only) (PRM045civ) signed. |  |
| - “Final Statement” (PRM044/2civ) signed by all consultants involved. |  |
| - “Contract Completion Report” (PRM043civ) finalized (not necessary if nil report). |  |
| - “Geographical Targeted Procurement Management System” (GTPMS) compliance evidence handed in (relevant DF form). |  |
| - Guarantees, certificates, maintenance contracts and manuals |  |
| - When applicable submit guarantees e.g. roof, waterproofing, etc. |  |
| - Control and confirm that electrical certificate of compliance has been issued. |  |
| - Control and confirm that maintenance contracts are in place where this is contractually required (Ceded to the Department if required from a nominated sub-contractor). |  |
| - Where applicable, submit operational and maintenance manuals and maintenance specifications. |  |
| - When applicable, submit as-built drawings for mechanical installations provided by the contractor. |  |
| - Control and confirm that the original site instruction book(s) and site visitor book have been submitted to the Department. |  |

- Prerequisites for final payment to the contractor:

| ACTION | YES/NO |
| --- | --- |
| - Accepting the final account after approval by the Department in signing of the “Final Statement” by all parties including the contractor (resolution of signature from contractor required). The exception is that the final account shall be deemed signed by the contractor after three months if the contractor fails to object and sign subject to Clause 49.10 of the General Conditions of Contract 2004. Note: The Final Statement can only be presented to the contractor for acceptance subsequent to the acceptance thereof by the Departmental project manager and the Director-General of the Department of Public Works. |  |
| - “Final Approval Certificates” issued (PRM046/2civ). |  |

- Prerequisite for final payment to consultants:

| ACTION | YES/NO |
| --- | --- |
| - Signing of the “Final Statement” by the concerned consultant(s). |  |
| - Signing of the “Certificate of Compliance and Indemnity by Consultants” (PRM045civ Part 1 and 2) by the concerned consultant(s). |  |
| - Submission of “As Built” drawings on A size 0.08mm thickness polyester film marked “As Built” dated and signed by concerned consultant (principal). |  |
| - “Final Approval Certificates” (PRM046/2civ) issued. |  |
| - Compliance certified and reconciliation of the prescribed space and cost norms submitted when applicable, by the concerned consultant(s) (PRM019/1 and -/2). |  |

PRM044civ/2

PRM044:  FINAL STATEMENT

|  |  |  |  |  |  |  |  |  |  |  | WCS No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  | REFERENCE No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT MANAGER: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONSULTANT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contractor: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NET AMOUNT OF CONTRACT (EXCLUDING VAT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| APPROVED VARIATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | - |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | + |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| PLUS: CONTRACT PRICE ADJUSTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | + |  |
| LESS: CONTRACT PRICE ADJUSTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | - |  |
| COST OF WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| (1) LESS: Penalty for Late Completion (PW156 4.2) |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (2) LESS: Penalty for Non-Compliance with APP (PW156 4.3) |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  | + | R |  |  | - |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| VALUE ADDED TAX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | + |  |
| FINAL VALUE OF CONTRACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| * RETENTION RETAINED (INCLUDING VAT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| CONSULTING ENGINEER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DEPT. PROJECT MANAGER |  |  |  |  |  |  |  |  |  |  |  |
| DATE: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE: |  |  |  |  |  |  |  |  |  |  |  |
| PRINCIPAL AGENT / CONSULTANT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | pp DIRECTOR-GENERAL DEPARTMENT OF PUBLIC WORKS |  |  |  |  |  |  |  |  |  |  |
| DATE: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE: |  |  |  |  |  |  |  |  |  |  |  |
| I, the undersigned, duly authorised, accept the above statement as correct.: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CONTRACTOR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |  |  |  |  |
| * | Applicable for engineering contracts where 12 months retention period is required and retention amount also included in final value of contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FOR DEPARTMENTAL USE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract close out captured on WCS (WG10PU): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OPW: |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PRM045civ/1

# PRM045:  CERTIFICATE OF COMPLIANCE AND INDEMNITY BY CONSULTANTS

|  |  |  |  | WCS No: |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | REFERENCE No: |  |
| PROJECT: |  |  |  |  |  |
| DEPT. PROJECT MANAGER: |  |  |  |  |  |
| PRINCIPAL AGENT / LEAD CONSULTANT: |  |  |  |  |  |
| NAME OF CONTRACTOR: |  |  |  |  |  |

1.	I/We appointed (Engineers / Project Manager *) Consultants appointed to prepare the Final Account for this service, hereby certify that the final account has been prepared according to the following requirements:

(a)	That it has been prepared in accordance with the Department's example;

- Where schedule rates are applicable these have been used and non-schedule rates, where possible, have been based on schedule rates;

- Where it is not possible to use schedule rates, items have been priced by me/us in accordance with the appropriate clause of the Condition of Contract.  Calculations of non-schedule rates have been included with the final account and invoices, quotations, etc., where applicable are also attached thereto;

(d)	Copies of all invoices, receipted accounts, etc. mentioned in the final account are attached and are cross referenced to the items in the final account;

(e)	Fluctuations in cost are in accordance with the contract price adjustment provisions laid clown in the schedule of quantities;

(f)	All "daywork" sheets duly approved have been checked and attached to the final account;

(g)	All items included in the final account (except provisional items) are covered by the necessary approved variation orders or written site instructions;

(h)	All provisional items have been remeasured.  Where provisional items have been varied, a list of all such unvaried items has been included in the final account, stating that such items have not been executed as measured;

PRM045civ/2

(i)	All fruitless expenditure has been identified in the final account and a list of these items with their respective values, is attached thereto.  For the purpose of this subclause "fruitless expenditure" shall mean the value of the work carried out and subsequently altered as a result of negligence and/or defective planning, resulting in work already planned and executed in good faith being made undone;

(j)	All calculations and amounts have been checked;

(k)	No payments have been made to the contractor, which are not in terms of the Contract;

(l)	Unless otherwise instructed by the Department, penalties for late completion of the contract have been deducted from monies due to the contractor and the deduction shown on the final statement.

*	Delete which is not required

I/We indemnify the Department against any overpayment which was made in terms of the final account as a result of incorrect information provided by me/us unless I/we can prove to the reasonable satisfaction of the Department that there was no negligence on my/our part or on the part of anyone in my/our employ.  The Department shall be obliged, against payment to it in terms of this indemnity, to give cession to me/us of such claims as it may have against the contractor or any other party as may be necessary to enable me/us to recover from the contractor or any other party the amount paid over in terms of this indemnity.  This document shall not constitute any novation of my/our obligations towards the Department.

| SIGNATURE |  |  | DATE |
| --- | --- | --- | --- |
| FIRM / CONSORTIUM / FIRMS-IN-COLLABORATION |  |  |  |

PRM046civ/1

| Department of public works |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # PRM046: FINAL APPROVAL CERTIFICATE (Clause 52 of the General Conditions of Contract 2004) |  |  |  |  |  |  |
| REGION: |  |  |  |  |  | WCS No: |
| PROJECT: |  |  |  |  |  | Reference No: |
|  |  |  |  |  |  | Tender No: |
| CLIENT/USER DEPARTMENT: |  |  |  |  |  |  |
| dEPARTMENTAL PROJECT MANAGER: |  |  |  |  |  |  |
| CONSULTANT: |  |  |  |  |  |  |
| CONTRACTOR: |  |  |  |  |  |  |
| DATE OF FINAL APPROVAL: |  |  |  |  |  |  |
| This is to certify that the Final Approval Certificate of the above-mentioned service was issued on the above-mentioned date and that all defects have been rectified in accordance with Clauses 27, 51 and 53 of General Conditions of Contract 2004 |  |  |  |  |  |  |
| CONSULTANT |  | CLIENT/USER DEPARTMENT |  | CONTRACTOR | dEPARTMENT OF PUBLIC WORKS |  |
| Representative |  | Representative |  | Representative | Representative |  |
| Signature |  | Signature |  | Signature | Signature |  |
| Date |  | Date |  | Date | Date |  |
| Note: In terms of the Conditions of Contract, only the Engineer certifies due completion of the Works. The other signatures indicate attendance at the inspection of the Works and witnessing of the Engineer’s signature. |  |  |  |  |  |  |
| For: DIRECTOR SPECIAL AND MAJOR PROJECTS: __________________________ DATE: _______________ |  |  |  |  |  |  |