## Norms
COST LIMIT RECONCILIATION STATEMENT
PROJECT
TITLE: |  | ALBERTVILLE
POLICE STATION
WCS: |  | 012345 |  |  |  | REFERENCE NO: | 6032/1009/9/4
PROJECT COST BASED ON: |  | SKETCH PLAN ESTIMATE |  |  |  | DATE OF ESTIMATE: | 2003-07-01
RAND VALUE PER SCU AT DATE: |  | 2003-07-01 |  | 7287.47 |  | (BER BUILDING COST INDEX TABLE 2B)
SCHEDULE
CATEGORIES |  | SCU'S |  | RAND VALUE |  | COST LIMIT
Building Development |  | 3575.34 | @ | 7287.47 | = | 26055182.99
Site Development |  | 561.19 | @ | 7287.47 | = | 4089655.29
Security |  | 17.38 | @ | 7287.47 | = | 126656.23
Abnormal Soil Conditions |  | 936.75 | @ | 7287.47 | = | 6826537.52
Landscaping |  | 20 | @ | 7287.47 | = | 145749.4
Parking |  | 268.8 | @ | 7287.47 | = | 1958871.94
Work In Existing Building |  | 0 | @ | 7287.47 | = | 0
|  | 5379.46 |  |  |  | 39202653.37
PROJECT COST
CATEGORIES |  | SKETCH PLAN ESTIMATE |  | PLUS PRELIM'S |  | ADD VAT |  | RESERVES & PROF FEES
Preliminaries |  | 1573881 |  | [Included Pro-rata] |  | 14% | [R1] | 5%
Building Development | [6 empty] | [R2] | 5%
Buildings | 9872928 | [5 empty] | [PF] | 18.5%
Mech. & Electrical | 3295115
Lifts | 0
| Total: Building Development | 13168043 |  | 14155681.29 |  | 16137476.67 |  | 21083008.114
Site Development |  | 689002 |  | 740678.98 |  | 844374.04 |  | 1103143.0192
Security |  | 34730 |  | 37334.84 |  | 42561.72 |  | 55605.2911
Abnormal Soil Conditions |  | 4922972 |  | 5292208.01 |  | 6033117.13 |  | 7882041.2885
Landscaping |  | 507181 |  | 545220.93 |  | 621551.86 |  | 812034.1969
Parking |  | 1084122 |  | 1165434.04 |  | 1328594.81 |  | 1735759.297
Work In Existing Building |  | 578285 |  | 621657.91 |  | 708690.02 |  | 925876.9353
|  | 22558216 |  | 22558216 |  | 25716366.25 |  | 33597468.1419
PROJECT STATUS
CATEGORIES |  | COST LIMITS |  | ESTIMATE |  | DIFFERENCE
Building Development |  | 26055182.99 |  | 21083008.114 |  | -4972174.876
Site Development |  | 4089655.29 |  | 1103143.0192 |  | -2986512.2708
Security |  | 126656.23 |  | 55605.2911 |  | -71050.9389
Abnormal Soil Conditions |  | 6826537.52 |  | 7882041.2885 |  | 1055503.7685 | Exceeds Cost Limit!
Landscaping |  | 145749.4 |  | 812034.1969 |  | 666284.7969 | Exceeds Cost Limit!
Parking |  | 1958871.94 |  | 1735759.297 |  | -223112.643
Work In Existing Building |  | 0 |  | 925876.9353 |  | 925876.9353 | Exceeds Cost Limit!
|  | 39202653.37 |  | 33597468.1419 |  | -5605185.2281
COMPLIANCE STATEMENT: COST LIMITS
DOES THE PROJECT COMPLY WITH THE COST LIMITS? |  |  | YES/NO | YES
If not, provide reasons
COMPLIANCE STATEMENT: SPACE NORMS
ATTACH SPACE RECONCILIATION |  | (You may exceed the space norm by +2% and -10%)
DOES THE PROJECT COMPLY WITH THE SPACE NORMS? |  |  | YES/NO | YES
If not, provide reasons and motivation
Signed: _______________________
Dated: ________________________
Note on G9: PWH: This layout is the consolidated norms report - you must provide additional calculation sheets to suit you particular project. The data in the yellow cells are variables
Note on I23: PWH: Amounts in Col I [X] are calculated as follows: X=A*(1+R1)*(1+R2)*(1+PF), Where A is the amount from Col. G
Note on I24: PWH: Recommended discressionary design Reserve
Note on I25: PWH: Project Reserve
Note on I26: PWH: Professional Fees, which changes for General accommodation, for Hospitals and for Housing